## tasks in launch large
position | id | parent_task_id | title | purpose | description | actions | additional_resources | days_from_start_until_due | default_duration | created_at | updated_at | published | admin_notes
1 | 1 | 0 | PHASE I - PREPARATION | The purpose of Phase I is to get the ball rolling with the new church plant project. |  |  |  | 109 | 109 | 2015-02-03 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: standard 2020-12-23 name changed from "GETTING STARTED" --pb
2 | 2 | 1 | Milestone: Affirm the Calling | Use several different tools and resources to confirm and clarify God's calling to plant a church. | Church planting is one of the most demanding and faith-stretching things you can do. It is also one of the most rewarding and satisfying. But, it is not for everyone. Take time to study and learn about yourself and see how your gifts and strengths can be used to start a healthy church. Also, submit yourself to the review and opinions of church planting experts to confirm that you are qualified and prepared to plant a church. Most importantly, spend lots of time in prayer seeking God's confirmation of the calling. |  |  | 49 | 49 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-07-28 content validated & reformated& --pb 2019-11-22 content updated --pb 2020-12-16 changed Due in # Days from 7& to 28& & Duration from 90& to 28& --pb&
3 | 3 | 2 | Read this affirming the calling overview | Understand the importance of being called to plant a church and how to affirm that calling from God. | Before starting a church, you should have a clear calling from God. If there's anything else you can do and be happy, do that instead. Part of understanding a calling to plant a church is hearing the calling affirmed from other mature Christians. One of the best affirming processes available is a church planter assessment. In the post <a href="https://churchleaders.com/outreach-missions/outreach-missions-articles/138305-church-planters-who-succeed.html">Church Planters Who Succeed</a> from ChurchLeaders.com, the first 2 success factors are: calling, and assessment Assessment has become an industry standard. For many church planting networks, it is a non-negotiable. | Talk to mature Christians whom you respect. Get their wisdom and ask their feedback on your calling to plant a church. Talk to peers in ministry and ask their feedback on your calling to plant a church. Read <a href="https://voices.lifeway.com/church-ministry-leadership/are-you-actually-called-to-plant-a-church/">Are You Actually Called To Plant A Church?</a> by Daniel Im Watch the Passion for Planting training video "<a href="/resources/item/3">Affirm Your Calling</a>" featuring Ed Stetzer. This action is complete after you have finished watching the training video. |  | 1 | 1 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-07-28 content updated --pb 2019-11-22 content updated --pb 2020-12-11 changed Due in # Days from 7 to 1 2022-11-21 Replaced Are You Called To Plant (expired) by Ed Stetzer with the Daniel Im article --sc
4 | 4 | 2 | Select approximate geographic area for new church | Identify the approximate geographic area for the new church so you can begin proper planning. | God's call for you to plant a church will include being called to a people and/or a place. In the early stages of the plant, you may not have clarity on exactly where to plant, but you need to begin discerning roughly where God is calling you if you're to make any plans. Your approximate geographic area might be a region, a county, or a metro area. In some cases, the area is chosen by a sending church or church planting network before they even call you to plant with them. In other cases, you may identify the area collaboratively after you've been called by the church planting network. The location you settle on should be informed by prayer and initial demographic profiles/studies. Here are things to consider in selecting a location: The demographics - Who lives in the area? Who will you be reaching in the area? Population density - How many people of your target demographic live within a reasonable driving distance? Who you are - You will attract others like yourself. Other churches - What other healthy, growing churches exist in the area? Growth patterns - Over the past 5 years, has the area been growing or declining? What are the projections for the next 5-10 years? Other new churches - Are other church planting networks targeting the same area? Most church planting networks have a priority list of locations. God's calling - Is The Spirit leading you to a specific place? Setting - are your skills and experiences a better match for an urban, suburban, or rural setting? You will refine your target area in a subsequent PlanterPlan action. | Seek God's counsel for the general area the church is to be planted. Review and consider the factors listed above. Select a general area to target for starting the new church. This action is complete once you have prayerfully selected the general area for the church plant. | <a href="/resources/item/236">Selecting the Target Area</a> , a slide deck from Ed Stetzer | 7 | 7 | 2000-01-01 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard Need to move PPT resource to our server.& Pat will do.& --ds Resource id#236 2017-07-28 content & resource link updated --pb 2020-12-11 changed Duration& from 30 to 7 --pb 2019-11-22 content updated --pb
5 | 1278 | 2 | Assess your calling to church planting | Confirm and have rock-solid confidence in your calling to plant a church. | Church planting is so difficult that your calling will come into question at least once along the journey. You need to have an unshakable conviction, supported by evidence, that God has called you to plant this church. On the hard days, you will need to point back to that evidence and tell yourself, "This is so incredibly hard, but I know that God has called me plant this church because ______. I am not giving up." Assessment is a process that will give you that evidence. You'll typically go through an initial screening and then travel to an on-site assessment center. It is a multi-day panel interview of you and your spouse. It will culminate in mature Christian leaders giving you verbal and/or written affirmation of your calling. The following subtasks will guide you to: Assess your own passion for reaching lost people Complete self and pre-assessments Undergo a formal assessment Get a copy of your church planter assessment report No circumstance or earthly power will be able to steal away the affirmation you receive. It happened. It is fact. | Complete each of the subsequent child tasks. This action is complete when you have been positively affirmed by an established church planting assessment center. |  | 234 | 220 | 2019-10-14 04:00 | 2019-12-11 05:00 | 2000-01-01 05:00 | template: 2019-12-03 due date fields found empty --pb 2019-12-03 content updated --pb 2020-12-11 changed Due in # Days from 35& to 29 & Duration from 7 to 1 --pb
6 | 6 | 1278 | Complete self and pre-assessments | Complete several personality profiles to understand how you can best use your natural wiring & gifts to lead a church planting team. | Church planting is hard work. It requires a special person to be able to succeed. Several personality traits have been shown to be helpful to planters. The following list is adapted from a research project completed by Dr. Charles Ridely for 13 denominations on success factors for planters. (<a href="https://churchleaders.com/outreach-missions/outreach-missions-blogs/141404-10_church_planter_qualities.html">read more</a>) A good planter candidate: Can envision a desired future and sell the vision to others Is self-motivated Is able to create buy-in from others Is a successful evangelist Is a relationship builder Is more interested in health than quick growth Is an observer of the culture Is an equipper Is flexible and adaptable Is able to develop and empower teams Is resilient Has strong faith Complete several personality profiles to determine if you have the leadership skills required to launch a church. These profiles can be used as a tool to confirm God's calling. One excellent place to start is <a href="https://www.churchplanterprofiles.com">Church Planter Profiles</a> by Gateway Leaders. There you can complete several online personality profiles to determine suitability to church planting. Other helpful sites are: <a href="https://asburychurchplanting.com/eq-assessment/">Church Planter Self Assessment</a> (Asbury Seminary) <a href="https://www.namb.net/send-network/church-planting/assessment/">NAMB Assessment Process</a> <a href="https://courses.pathwaylearning.org/library/calling-course-33243/477427/about/">Pathway Learning</a> | Complete at least one of the planter-targeted personality profiles. This action is complete when the planter prospect has completed at least one personality profile. " | <a href="https://careynieuwhof.com/12-signs-youre-a-spiritual-entrepreneur/">12 Signs You're a Spiritual Entrepreneur</a> by Carey Nieuwhof Ephesiology Master Class: <a href="https://masterclasses.ephesiology.com/courses/movement-leadership">Releasing Your Leadership Potential </a> (led by Alan Hirsch) | 7 | 7 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-07-28 content & external links updated --pb 2018-12-12 additional resources subsection added --pb 2020-12-11 changed Duration from 14 to 7 --pb 2021-03-12 added Ephisiology& URL --pb 2022-11-21 Replaced EFCA& Church Planter Skill (Broken Link) and ACT 29 Assessment (used in later task) with Asbury& Self Assessment and updated Alan Hirsch Ephesiology& class --sc
7 | 285 | 1278 | Assess your own passion for reaching people far from God | Conduct a personal assessment to determine your own passion for reaching people far from God. | Creating an evangelistic DNA begins with the planter. You will have difficulty establishing an evangelistic DNA in the church if you don't have a personal passion for reaching people far from God yourself. Ask yourself the following questions to help assess your passion: How many people have you led to Christ in the last year? How many non-Christian friends do you have? How often do you spend time with them? Are non-Christians comfortable around you? Are you comfortable around them? Does it make you uncomfortable to be around non-Christians with obviously immoral lifestyles? How often do you pray for people far from God? Do you know your neighbors? Where do you spend time in the community to connect with people far from God? Also ask others to assess your passion for reaching people far from God - ask your coach, your spouse, former co-workers, etc. If you find yourself lacking in this area, start praying about it. Pray for God to give you a passion for people far from God. Pray for opportunities to talk with people and build relationships. Often a passion for people far from God develops out of relationships with those people. If others have identified this as a weakness in you, ask your someone to hold you accountable for developing this passion. | Ask yourself the above questions. Ask others to assess your passion for reaching lost people. Spend time in prayer asking God to burden you with a passion for people far from God. This action is complete when you have committed to being passionate about reaching people far from God. | <a href="https://seniorpastorcentral.com/234/if-the-senior-pastor-doesnt-evangelize-eventually-no-one-will-2/">If The Senior Pastor Doesn't Evangelize, Eventually No-One Will</a> [SeniorPastorCentral.com] | 7 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-06-02 content updated --pb 2019-05-01 additional resources subsection added --pb 2019-11-22 content updated --pb 2020-12-11 changed Due in # Days from 52 to 7
8 | 13 | 1278 | Undergo a formal assessment | Complete an assessment by an independent organization that specializes in discerning a leader's suitability for planting. | Placing enthusiastic people in posts for which they are unprepared or unqualified is extremely counterproductive. It often ends up even damaging them and their families. Assessment is the process of discerning two important factors in church planting: Qualification Readiness We're all wired up differently. Certain personality types do really well as lead planters. Some types are a bad match and attempting to plant will cause untold anxiety, stress and even emotional damage. And even those that have the natural temperament to plant may not have the life and ministry experience necessary to start a new church. A formal assessment will let you know where you stand on both of these counts. The assessment can be as short as one day, but is commonly 3-5 days in length. It's often done in a group setting with other potential planters and includes a combination of: interviews group exercises essays assignments The evaluation team observes you in a number of different situations. You will usually get a detailed report and an individual formal debrief. The report will include your strengths as well as developmental suggestions. It will make a clear recommendation as to your readiness to plant a church within the next 2 years. Assessment History For two decades, assessment has been used by church planting strategists across North America. Borrowing from experts like Dr. Thomas Graham and Dr. Charles Ridley, a process has been developed to help interested candidates determine their giftedness and readiness for church planting, either as the leader of a team, a member of a team, or as a 'solo' church planting pastor. Church planting assessment integrates several lenses of evaluation to help a couple or individual discover as much about healthy placement in church planting as possible. These lenses include: Written expression, in the form of an extensive questionnaire, a professional resume, exercises, and projects, are evaluated by the assessment staff Psychological instruments that are employed to identify any potential issues which impact individual wholeness, marital adjustment, and professional interaction Experienced practitioners observing candidates in simulation modules, team activities, and personal interviews to provide real-life perspective for potential church planting scenarios Peer assessments that provide each candidate with invaluable input from others with whom he/she works during the assessment Self assessment - perhaps the most important directional outcome of all. Processing all input available, the candidate (and spouse where applicable) is able to make a highly informed conclusion about placement and timing in church planting ministry. You have many options for attending an assessment center. <a href="https://church-planting.net/church-planter-assessment/">Passion for Planting</a> has an Assessment Center that holds assessments several times each year. Learn more about the Passion for Planting Assessment Center and check out upcoming dates: <a href="https://church-planting.net/church-planter-assessment/"> </a> Other assessment centers include: <a href="https://www.converge.org/church-planting/assessment">Converge Assessment Center</a> <a href="https://stadiachurchplanting.org/services/discoverycenter/">Church Planting Assessment Center (CPAC)</a> by Stadia Church Planting <a href="https://www.acts29.com/who-should-apply/">ACTS 29 Assessment</a> <a href="https://resources.pcamna.org/categories/assessment/">PCA - Mission to North America</a> | Choose an assessment event to attend. Register and complete assigned pre-work. Arrange for travel and childcare as appropriate. Participate in the event. This action is complete when the planter has undergone a formal assessment. |  | 14 | 14 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-08-29 content update --pb 2019-11-22 content updated & links verified --pb 2020-01-13 replaced broken gdurl& link to image --pb 2020-12-11 changed Due in # Days from 7 to 14 2020-12-11 changed Duration from 60 to 14 2022-11-21 deleted Church Planter Assessment Center by Lifeway& and Northwest Church Planting& and updated PCA& Assessment link--sc
9 | 14 | 1278 | Get a copy of your church planter assessment report | Get a copy of your assessment report for forwarding to church planting groups and drafting your own personal development plan. | Your assessment was an intense multi-day experience which combined interviews, presentations, and written evaluations by peers, assessors, and even yourself. The experience culminated in a written report with recommendations on your suitability to lead or participate in a church plant. Most planters find the feedback invaluable in preparing them for the challenges ahead. A subsequent PlanterPlan task will guide you through drafting a personal development plan to maximize the strengths identified in the report and select books & courses to compliment your training. If you are courting church planting agencies for collaboration and support, the assessment report may prove invaluable in establishing your readiness to plant with them. | Thank you assessors for their time & wisdom. Make sure you are clear on how and when you'll get a copy of your report. Save the report to your device and back it up in the cloud. This action is complete when you have received your assessment report. |  | 28 | 7 | 2015-02-03 05:00 | 2020-07-24 04:00 | 2000-01-01 05:00 | template: 2017-08-29 content updated --pb 2019-11-22 content updated --pb
10 | 59 | 1 | Milestone: Train for Church Planting | Learn as much as possible about disciple-making, church planting and leadership so you can maximize your God-given gifts and set the new church up for health. | Paul says in 1 Corinthians 9:25-27, "Everyone who competes in the games goes into strict training. They do it to get a crown that will not last; but we do it to get a crown that will last forever. Therefore I do not run like a man running aimlessly; I do not fight like a man beating the air. No, I beat my body and make it my slave so that after I have preached to others, I myself will not be disqualified for the prize." It is a principle of life that if you want to be good at something, you must practice and train. Professional athletes train hours every day just to stay good at what they do. They do it for the paycheck and the fame. The stakes for church planters are much higher - we are dealing with things eternal. Athletes compete against each other. Planters wage war against an unseen enemy who knows our every weakness. Seek out the best trainers available through books, conferences, and boot camps. Also develop a plan to continue your learning and training in order to stay at the top of your game. |  |  | 46 | 46 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-08-30 content updated --pb 2019-11-22 content updated --pb 2020-12-16 changed Duration from 90& to 45& --pb&
11 | 60 | 59 | Watch this PlanterPlan tutorial | Get comfortable using PlanterPlan to get the most out of it. | PlanterPlan is an online project management app built by church planters for church planters. It contains a library of well over 800 tasks related to church planting. By using this app, you'll minimize the risk of forgetting an important aspect of launching in-person worship gatherings. <a href="https://youtu.be/2UzvD7M2bHs?si=MB4WrSQnG0UFzGLo"> </a> Power Tips Invite Your Team: create user accounts for others on your team and invite them to collaborate on the project; with premium content, training on how to do each task is built in! Delegate: assign a task to a team member by changing their initials as the lead ; for volunteers not in the system, simply use the email button to shoot them the task (with the same built-in training) Communicate: use the built-in reports to send updates to your Management Team, church planting network and/or denomination Customize: you can add additional milestones and tasks from our extensive library or custom ones you create | Watch the PlanterPlan tutorial video above. This action is complete when the PlanterPlan tutorial has been viewed. |  | 1 | 1 | 2000-01-01 05:00 | 2025-03-14 19:49 | 2000-01-01 05:00 | template: standard Need to link in PlanterPlan Tutorial video when complete. &radic; 2017-08-30 content updated --pb 2020-12-11 changed Due in # Days & Duration from 3 to 1 --pb & 2020-01-24 content validated --pb 2025-03-14 updated video from Vimeo to YouTube --pb
12 | 63 | 59 | Attend church planter training | Prepare to plant a church by attending a church planter boot camp or completing a church planter residency program. | Church planting residencies are a great way to prepare to plant a church. Most church planters fail to see the need for such training because they don't know what they don't know. They are like the young engaged couple that don't understand why they should go through premarital counseling. In their minds they're in love and that's all they'll need to have a healthy marriage. However, they don't realize the hard work that lies ahead of them on their journey towards happily ever after. This is why pastors recommend young couples to go through premarital counseling, which offers them tools they can use to cultivate their relationship. Church planting training, like residencies and boot camps, do the same thing for church planters. They equip church planters with tools they can use to develop the systems and teams they'll need to make disciples and start a healthy church. Residencies vs. Boot Camps The big difference between residencies and boot camps is time. Residencies typically last 9-12 months, while boot camps are 3 to 5 days of intense classroom training. During a residency a church planter will not only learn from reading books and discussions with experienced church planters, they'll also learn from practical ministry experience. Boot camps are the quick way to gain much needed knowledge, but residencies allow participants to grow as leaders while practicing what they're learning in real life. You'll typically attend a boot camp or complete a residency after you've been affirmed by an assessment center. Costs to participate in a boot camp range from less than $200 to over $1,500. Residency programs usually range from $1,500 to $3,000. Many church planting networks offer their own boot camps and residency programs to prepare planters for the task which is before them. Each network's training is unique, reflecting the particular passions of that network. If you aren't a part of a network that offers church planter training, consider Passion for Planting's boot camp or distance residency program (info below). The bottom line is you need training. Why fly blind and make mistakes that are avoidable? Learn from others who have already walked in your shoes and develop your church planter toolbox which will help you complete the work God's called you to. <a href="https://church-planting.net/residencies/">Register Now</a> for our next Residency Cohort. <a href="https://church-planting.net/bootcamp/">Register Now</a> for our next Boot Camp event. If that doesn't meet your needs or timetable, consider contacting these training organizations to get an overview of their schedule and topics covered: <a href="https://www.acts29.com/acts-29-training-programs/">Acts29</a> <a href="https://www.nutsandbolts.org/">Nuts & Bolts</a> <a href="https://www.efca.org/resources/document/start-boot-camp">Evangelical Free Church of America (EFCA)</a> --> <a href="https://www.arcchurches.com/launch/">Association of Related Churches (ARC)</a> <a href="https://www.converge.org/church-planting/training-101">Converge Worldwide</a> <a href="https://churchmultiplication.net/launch">Church Multiplication Network </a> <a href="https://www.cmtcmultiply.org/">Church Multiplication Training Center</a> | Research training options and select which to attend. Register and adjust schedule to participate in training. Attend church planting training. This action is complete when you have attended training. |  | 46 | 46 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-08-30 content and hyperlinks updated --pb 2019-11-22 links validated & content updated --pb 2020-12-11 changed& title from "Attend a church plant boot camp" --pb 2020-12-22 updated the wording --SC 2022-11-21 deleted Value of Church Planter Training article link by Ed Stetzer& (broken)--sc
13 | 73 | 59 | Visit other new churches | Experience other new church plants firsthand in order to understand trends and new innovations for reaching people; this will also expand your paradigm of church beyond the limits of your personal past experience. | Close your eyes. Picture opening day of the new church. What does it look like? Chances are, the picture you see of the future looks very much like a picture from your past . Many planters start with what is familiar and ask, "What do I want to change?" What you get is a minor variation to the picture of the past. How do we start with a blank piece of paper and create a brand new picture? The first thing you need to do is to get the picture of past experience out of your mind. Commit that you will not let the past be the starting point for your future. Instead, take what is good from the past, and create a new thing. God is calling you to do a new thing. Next, look at what other new churches are doing to reach people. Gain an understanding of trends and innovative practices. This starts with learning from others who have come before you. Just as you are encouraged not to copy the paste, do not simply copy what others are doing. The goal is to understand what others are learning and doing as you begin to create a new picture. In breaking the paradigms of your past, it helps to understand the new things that others are doing. | Identify a list of new churches (planters) who have started within the past year. Review the websites and social media pages of new churches to determine new and innovative things that are being done to reach people. Contact and talk with as many planters as possible. Visit as many new churches as possible (anywhere in the country). If possible, visit existing churches in your target area to understand what others in the target area are doing to reach people. This action is complete after you have visited at least 5 young, growing churches to observe what they are doing to reach lost people. |  | 46 | 46 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-08-31 content validated --pb 2019-11-22 content updated --pb 2020-12-11 changed Duration from 90 to 45 --pb
14 | 75 | 59 | Attend church planting conferences | Attend a church planting conference to learn from church planting experts, network with other planters, and connect with church planting vendors. | Conferences provide you with a unique opportunity to accomplish several things at once. Training and Inspiration Church planting conferences feature sessions and breakouts on the best practices of church planting led by experienced church planting experts. Conferences provide a rare opportunity to connect with nationally known church planting experts in large and small group settings. You will be learning from the best of the best and will often have the opportunity to choose breakout sessions on specific topics of interest. Many planters receive an incredible amount of encouragement and motivation that provides energy for months to come. God often works through these speakers to confirm a call, encourage the disheartened, and inspire. The experience is similar in scope to the troops gathering before their generals in preparation for war. You will leave motivated and ready to fight the spiritual battles ahead of you. Networking In addition, the conferences are attended by other planters. This provides a great opportunity to develop networking communities to share in which planters gather either in person or online to share experience and provide support to each other. In 1 Kings 18:22, Elijah said, "I am the only one of the LORD's prophets left, but Baal has four hundred and fifty prophets" Many planters experience this same feeling of isolation. It is important to realize that you are not alone. In 1 Kings 19:18, God reminded Elijah, "Yet I reserve seven thousand in Israel, all whose knees have not bowed down to Baal and all whose mouths have not kissed him." A network of planters can be an invaluable source of spiritual encouragement. It can also be mutually beneficial to collaborate together on ideas for church planting. Resourcing Most church planting conferences have several vendors present as well. From website design to equipment to completing legal paperwork, there are many vendors who provide expert help to the planter. Take time to familiarize yourself with these vendors. Get contact information for each vendor you may want to work with. And of course register for all the free iPhones and giveaways the vendors have. Tom's Tips! Eight suggestions for making the most of conferences and training events. by Tom Herrick of Titus Church Planting Institute It is training and conference season. Continuing education is imperative, but too often the only take-away from such opportunities ends up on your bookshelf (eg. simply another how-to binder or the speaker's newly published work). Consider these tips to make the most of the time, energy and resources you are investing: Do your homework If your training program includes a pre-assignment to be completed before the event, do it! You want to start the learning process on the right foot, instead of feeling like you are playing catch-up from the get-go. (Pre-work also helps you to make the change from the work-to-learning mode in your brain.) Reflect on the outcome you want Why are you investing in this training? What kind of take-away do you need? Perhaps you want a new or improved skill. Or maybe you need to build your network of go-to associates. Knowing your preferred outcome improves your chances of attaining it. It also helps you make better decisions when you need to choose between a variety of workshops. Don't go alone Often, capturing the material presented at training events is like drinking from a fire hydrant; sometimes you just cannot catch everything being taught! Having colleagues or team mates alongside provide two purposes: more ears to hear means more information retained; and it is a great way to get the entire team on the same page-important in any ministry, but particularly in church planting and development. Stay "Out of Office" Be sure to turn off or silence your phone, shut down your email, and only open as many browser windows as are needed for the training. I know this sounds like heresy, but multi-tasking in a learning environment is otherwise known as distraction. Valuable information is missed when you take your focus on the presenter, and turn it to the technology calling your name. Know your learning style Do you know how you normally learn? If you are a visual learner, be sure to position yourself where you can easily see the presenter and any AV tools. Take good notes, so you can review and re-read them. If you are an auditory learner, grab a seat near the sound booth, where you are guaranteed to hear the speaker well. Perhaps ask the trainer if you can record the session, so you can listen to it again later. Are you a kinesthetic learner? Feel free to doodle away, to illustrate and reinforce your learnings. Create graphics and charts. Bring along colored pens and highlighters, too! However you learn best, be sure to find a very simple way to record your thoughts so you can retrieve them later when you're putting what you've learned into practice. Reflect with your team At breaks, or at the end of each day, carve out time to reflect on what you've heard. Ask three questions: What jumped out to you today? How is it helpful to your work? What will you do differently? Create an Action Plan Based on your desired outcomes and daily reflections, develop a plan that includes: Specific actions to take over the next X-number-of weeks/months When you'll take the actions Identify the reasons you want to take these steps Obstacles that might get in the way, and how you'll tackle the them How you'll reward yourself Get a Coach Having a coach to come alongside you is an effective way to accelerate your progress toward a goal. Having a coach keeps your desire outcome before you and helps you to develop the plan to get there. | Decide which conference(s) to attend. Register for the conference(s). Make travel arrangements. This action is complete when you have attended a church planting conference. |  | 46 | 46 | 2015-02-03 05:00 | 2022-05-09 04:00 | 2000-01-01 05:00 | template: standard 2017-08-31 content validated --pb 2019-11-22 content updated --pb 2020-12-11 changed Duration from 90 to 45 --pb 2022-05-09 removed hyperlink to Titus Church Planting as site & FB page are no longer valid --pb
15 | 78 | 59 | Develop a reading plan | Discipline yourself to read disciple-making, church planting and leadership books to learn from other experienced church planters. | There are an increasing number of good books available about church planting. It is difficult to wade through them all and choose the ones that will best apply to you and your situation. Although many milestones in PlanterPlan have recommended books you may find useful on a particular topic, this action calls out some of the best books for you to start with. You should work with your coach to determine the most appropriate books to read. Passion for Planting considers the following "must read" books for planters: <a href="https://a.co/g6fmiSZ">Planting Missional Churches</a> (Ed Stetzer) <a href="https://www.amazon.com/T4T-Discipleship-Re-Revolution-Planting-Community/dp/0974756210">T4T: a Discipleship Re-Revolution</a> (Steve Smith & Ying Kai) <a href="https://a.co/22xxu2O">It's Personal: Surviving and Thriving on the Journey of Church Planting</a> (Brian Bloye) <a href="https://multiplication.org/product/the-emotionally-healthy-church-planter/">The Emotionally Healthy Church Planter</a> (Pete Scazerro) <a href="https://www.amazon.com/Future-Church-Laws-Real-Growth-ebook/dp/B087RTBL71/ref=tmm_kin_swatch_0?_encoding=UTF8&qid=&sr=">Future Church</a> (Will Mancini) <a href="https://a.co/gXVhcLg">Church Unique</a> (Will Mancini) <a href="https://a.co/4ZdXGUa">Be Mean About the Vision</a> (Shawn Lovejoy) <a href="https://a.co/ep6HWxc">Preaching</a> (Tim Keller) <a href="https://multiplication.org/product/launch-strong/">Launch Strong</a> (Brett Andrews & Dale Spaulding) <a href="https://multiplication.org/product/becoming-a-level-five-multiplying-church/">Becoming a Level 5 Multiplying Church</a> (Todd Wilson) <a href="https://www.craiggroeschel.com/books/lead-like-it-matters">Lead Like It Matters</a> (Craig Groeschel) <a href="https://multiplication.org/product/discipleship-is-the-core-mission-of-the-church/">Discipleship is the Core Mission of the Church</a> (Bobby Harrington) <a href="https://a.co/9ldmqit">Helping without Hurting in Church Benevolence</a> (Steve Corbett & Bryan Fikkert) Find other great church planting books and blogs in Passion for Planting's annotated <a href="/resources/item/7">Bibliography of Church Planting Resources</a>. | Talk with your coach to determine which books to add to the reading plan. Create a schedule with deadlines and/or calendar reminders for each book. This action is complete when you have created a schedule of the selected books. | Ephesiology Master Class: <a href="https://masterclasses.ephesiology.com/bundles/cpi">Church Planting Certificate</a> (led by Jeff Christopherson) | 21 | 7 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-10-26 content & links updated --pb 2019-11-25 book list updated --pb 2021-03-12 additional resources subsection added with Ephesiology& link& --pb 2022-11-21 added Future Church and switched Lead Like It Matters for Courageous Leadership to reading list; updated Church Planting Certificate class link --sc
16 | 20 | 1 | Milestone: Solidify Planter Support Structures | Set up solid relational structures to support yourself in the church planting process. | This milestone covers 3 general support structures that will give you the best fighting chance at a healthy church plant: Coaching Spousal Support Management Team While being healthy personally as a church planter doesn't guarantee a healthy church plant, the planter becoming unhealthy through lack of support will almost certainly guarantee an unhealthy church plant. Create structures and set up support relationships that will promote health in both. The tasks in the milestone will walk you through engaging a church planting coach, getting your spouse plugged in to a support system, and calling together a Management Team. |  |  | 49 | 49 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-08-29 this milestone was formerly "Initiate Planter Coaching" but included WAY more than just coaching, so content has been updated to emphasize support (which includes coaching). --pb 2019-12-10 content validated --pb 2020-12-16 changed Due in # Days from 45& to 49& & Duration from 45& to 49& --pb&
17 | 184 | 20 | Partner with a church planting network | Actively pursue partnership with a church planting network for support and credibility. | Never plant alone. Church planting networks create community and common purpose around disciple-making and church planting. And there are secondary benefits as well. You Get Services Many church planting networks provide key services and support to the planter, such as: coaching assessment training bookkeeping project management administrative support spouse support etc. This could save you a great deal of time and effort, which would give you more time to spend in the target community with non-Christians. Starting a new church is not something you should try and do alone. Being part of a network brings the kind of of support that can help maximize the health of the new church. You Gain Credibility Church planting networks can also bring credibility to your plant. When you're fundraising, you can tell prospective supporters that you're part of a network and not going it alone. And when you're networking with other churches, businesses and nonprofits in your community, you have the brand of your network to lean on. Dozens to Choose From From the Exponential post <a href="https://outreachmagazine.com/features/church-planting/51456-10-church-networking-models-part-1.html">10 Models of Networks</a>, check out their directory of over 60 networks in the following categories: Collaborative Networks Regional Networks Cooperative Networks Franchise Networks Church-Based Networks City-Focused Networks Rural Networks Family of Churches Networks Specialty Networks Support Networks Explore a network's beliefs and planting approaches to determine if they are a good fit. There May Be Obligations Networks need to carry out their mission the same as any church, which requires involvement and resources. Most networks will have some kind of relational and financial participation requirement. Make sure you understand what those are before you sign on the dotted line. | Become familiar with the different church planting networks. Determine which groups seem to be a good fit. Contact networks that are a good fit to determine next steps. Partner with a church planting network, signing any required covenants or agreements. This action is complete when you have partnered with a church planting network. |  | 14 | 14 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content and links validated --pb 2019-01-11 Due in # Days changed from& 60 to& 31 --pb 2019-12-10 content updated --pb 2020-12-11 changed Due in # Days from & 31 to 14 & Duration from 21 to 14 --pb 2022-11-21 updated Network link --sc
18 | 21 | 20 | Read this coaching overview | Understand why having a coach should be a non-negotiable. | Coaching has become a 'best practice' of church planting and is required by the majority of church planting networks and denominations. In fact, according to the Leadership Network, planters who have a coach are twice as likely to plant a healthy church that survives . As in double. Coaches offer an experienced perspective on the unique tasks and experiences you'll go through. Better than just providing sage advice, your coach will help bring out the best in your thoughts and planning process: coaching is not telling people what to do and how to do it. Coaches are trained to listen and not impose their experience on you. Coaches also hold you accountable. When a planter has committed to making 10 networking appointments by the end of the week, does he really want to call his coach and admit that he didn't do it? We all need this kind of motivation for time to time. Coaches can also be your confidante. You can tell your coach anything. You can share honest thoughts, feelings, and emotions about what is happening in the new church. People who will do that for you are rare in the life of any planter, but so very needed. After experiencing the support of a coaching relationship, many leaders will continue to intentionally seek out a coach for the rest of their time in ministry. Christian Coaching Here are some basic assumptions of Christian coaching: People have unique visions and values People have a need to discover individually what God wants them to do The Holy Spirit provides the Christian with personal guidance Each person has a unique background, knowledge, experience, insight and setting Christians need to lead according to a unique calling from God If you discover it yourself, you own it better A coach is not the expert on your life and won't tell you what to do People are more committed to what they help create God leads each of us uniquely to unique paths Prayer is our most powerful tool A Tale of Two Coaches Andre had to pick between launching worship gatherings in February at a decent location, or waiting until April to launch in a fantastic location. He didn't know how to choose between buying more time before the first summer and waiting for the better location. Through conversations with his coach, he was able to determine the best choice for his church. Without the counsel of someone who has 'been there and done that', Andre wouldn't have had anyone with experience to help weigh the options. Chris had a different problem: people he invited to join the Launch Team kept telling him, "Let us know when you've started weekly services, then we'll come be a part of what you're doing." His frustration grew and he couldn't figure out how to gain traction. To save money, he had chosen not to hire a coach, but he really needed someone with experience to process this landmine and figure out how to diffuse it. You may be tempted to save money and not hire a coach. Don't cut corners on this one! Make hiring a coach a non-negotiable for yourself. | <a href="/resources/item/208">View the training video by Dr. Ed Stetzer</a>. This action is complete when you have viewed the training video. |  | 1 | 1 | 2000-01-01 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-08-29 content updated --pb 2019-12-10 content validated --pb 2020-12-11 changed Due in # Days & Duration from 7 to 1
19 | 22 | 20 | Select your coach | Find a church planting coach to help you through the planting process. | Have you ever noticed that Steph Curry, LeBron James, and Tom Brady all have coaches? Doesn't it seem like players of that caliber wouldn't need a coach? Whether in sports, business, or church planting, everyone needs a coach. In sports, the coach's primary role is to bring out the best in the athlete, and in team sports to get all the players working together. In church planting these two goals still apply: bringing out the best in you, the church planter, and getting you working with God. The coach accomplishes these goals through asking the right questions and challenging you to think God-thoughts and make Godly decisions. This can include: Training and empowering you Bring you wisdom, experience and external perspective Being your cheerleader Helping you see your blind spots Helping you navigate the stress of being an entrepreneur with the demands of of a healthy family life Providing a safe place for you to have doubts and ask questions Asking you the tough questions Qualifications To be effective, the coach should have personally planted a successful church or have other similar personal experience with church planting. Since you probably haven't planted a church before (usually), the coach's experience is a great way for the church planter to learn from someone else, both the good and the bad. Choosing the right coach is critical. Sometimes church planting networks train and select coaches for the church planter. Other times you choose your own coach. Regardless, you need a coach you respect both personally and professionally. And you need to share fundamental beliefs. As an absolute minimum, the coach should be available for a monthly conference call. A more ideal arrangement is a biweekly 1-hour phone call with the church planter. The coach should commit to working with the Church Planter for 1-2 years. Whenever possible, you should be involved in choosing your coach. Gain Wisdom Building a church is complicated. It requires a great deal of broad knowledge that few church planters possess. Instruct a wise man and he will be wiser still; teach a righteous man and he will add to his learning. - Proverbs 9:9 The way of a fool seems right to him, but a wise man listens to advice. - Proverbs 12:15 We all need someone to bounce ideas off. Get a coach. | Check with your church planting network to see if they provide a coach. If not, consider contracting with Passion for Planting for a <a href="https://church-planting.net/coaching/">church planting coach</a>. Interview potential coaches over the phone or face to face. Ask for (and check) references. Select your coach. Establish a formal agreement with the coach to make sure that expectations are explicit. This action is complete when you establish a formal agreement with the church planting coach. |  | 13 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-08-29 content updated --pb 2019-12-10 content updated --pb 2020-12-11 changed Due in # Days from 14 to 13 & Duration from 14 to 7 & --pb
20 | 23 | 20 | Schedule regular meetings with your coach | Set up a recurring calendar appointment to facilitate meeting with your coach on a regular basis. | Sometimes the hardest part of developing a coaching relationship is simply beginning the relationship. Once you've selected a coach, take the lead to contact the coach and set up an initial meeting. This meeting will probably happen by phone or video call. If you can swing it, meet with the coach in person the first time around. The first meeting should open a dialog about what both parties hope to gain from the relationship. It is also important at this time to set expectations on what a typical meeting will entail. Spend some time casting vision about the new church for the coach, too. The most important thing to accomplish at the first meeting is to set up the ongoing rhythm of calls. It's common for that to be biweekly or semi-monthly, but planting a church is a fast-moving target, so Passion for Planting recommends meeting no less than once a month with your coach. | Set initial meeting agenda. Conduct initial meeting. At that meeting, schedule ongoing meetings. Add the new schedule to your calendar as a recurring appointment. This action is complete when regular meetings have been scheduled with the coach. |  | 21 | 7 | 2015-02-03 05:00 | 2019-12-10 05:00 | 2000-01-01 05:00 | template: standard 2017-08-30 content updated --pb 2019-01-11 Due in # days& corrected from 7 to 21 --pb 2019-12-10 content updated --pb
21 | 24 | 20 | Show your coach how to use PlanterPlan | Train the coach on the use of PlanterPlan so that coaching calls can focus on the big issues that you face. | The coach should review the project status via PlanterPlan prior to any coaching calls or meetings to understand the current status of the church plant. This will enable the coach to focus on the most important issues facing the planter. Integrated into PlanterPlan are scheduled coaching calls and coaching checkpoints. The coaching call tasks equip the coach with questions to ask that are pertinent to the planter within the timeline of the launch plan. The coaching checkpoints allow the coach to provide input and affirmation of critical strategy documents the planter creates. The coach may also see trends in the planter's work patterns and determine adjustments need to be made. | Grant the coach access to your PlanterPlan project by clicking "Manage Team" in the Project menu. Encourage the coach to watch the PlanterPlan tutorial. If necessary, the coach can <a href="https://church-planting.net/">contact Passion for Planting</a> for further instruction. This action is complete when the coach understands how to use PlanterPlan. |  | 28 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard Action #3:& http://www.church-planting.net/contact.htm& is a 404. Changed to& <a href="http://www.church-planting.net">http://www.church-planting.net</a> 2017-08-30 content validated and hyperlink updated --pb 2019-01-11 Due in # days corrected from 7 to 28 (Due & Duration were swapped) --pb 2019-12-10 content updated --pb
22 | 25 | 20 | Call your coach about your assessment report | Open a conversation with your coach about what to do with your Assessment Team's recommendations. | After receiving the formal report from the Assessment Team, review all their developmental recommendations. Work with your coach to develop a plan of attack to address each one. Be sure to include concrete dates and measurable goals. Sample issues to process with your coach: Which recommendation will be the hardest to address Which recommendation gave you the strongest emotional response Which order to address them in Which recommendation will give you the biggest return on investment | This action is complete when have called your coach to start kicking around your plan to address the Assessment Team's developmental recommendations. |  | 14 | 1 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-30 updated content, changed audience to coach --pb 2018-04-20 updated content, changed audience to planter --pb 2019-12-10 content updated --pb 2020-12-11 changed Due in # Days from 28 to 14 & Duration from 7 to 1 --pb
23 | 26 | 20 | Write your personal development plan | Create a plan to implement the health and improvement recommendations made by your church planter assessment team. | No planter is the perfect candidate for planting a church. We are all human and naturally have strengths and areas of weakness. Part of the benefit of assessment is increasing our awareness of these areas. As a part of the final assessment report, you should have been provided with a list of developmental suggestions to maximize your effectiveness as a planter. We all want to be the best stewards of the gifts and resources that God has given us. It's important to develop a plan to implement the recommendations given by the assessment team. | Go over the assessment recommendations and give yourself an honest evaluation in each area. Write out a plan and timeline for addressing each of the recommendations. Put due dates on your calendar for completing each recommendation. Ask a coach or mentor to hold you accountable to the plan you have created. This action is complete when you have developed an action plan from the assessment recommendations. |  | 28 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-08-30 content updated --pb 2019-12-10 content updated --pb 2020-12-11 changed Due in # Days from 36 to 28 --pb
24 | 27 | 20 | Coaching Checkpoint: review and affirm planter's Developmental Plan of Action | Ensure that the planter's Developmental Plan of Action covers the bases while remaining realistic. | The planter got some very specific feedback through the assessment process. His Developmental Plan of Action should include actionable steps to maximize his identified strengths and shore up any gaps they pointed out. Help the planter avoid the 2 extremes of being overly ambitious or distractedly negligent. | Review the planter's completed Developmental Plan of Action. Provide feedback to the planter. Affirm to the planter that the plan is actionable and realistic. This action is complete when you, the coach, have reviewed and affirmed the planter's Developmental Plan of Action. |  | 35 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2018-11-02 content updated --pb 2019-12-10 content validated --pb 2020-12-11 changed Due in # Days from 43 to 35 --pb
25 | 28 | 20 | Make sure your spouse has a support system | Get the church planting spouse connected to a support system. | You are being supported by coaches and mentors, but who is caring for your spouse? Planting a church is difficult for the planter's family, too. What a tragedy it is when a planter ends up with a successful church, but a failed marriage. Many church planting networks provide spousal support ministries. | Get your spouse connected to the support system your church planting network has for church planting spouses. This action is complete when the planter's spouse has joined a spouse support network. | <a href="https://thetruthrepublic.com">The Truth Republic</a> --> <a href="https://alongsidepastorswives.com">Alongside: A Ministry for Pastors' Wives</a> <a href="https://anchor.fm/waypointpw">The Waypoint Pastors' Wives Podcast</a> <a href="https://multiplyvineyard.org/how-to-be-married-to-a-church-planter/">How to Be Married to a Church Planter</a> on multiplyvineyard.org <a href="https://www.thegospelcoalition.org/article/5-fears-truths/">5 Fears of Church-Planting Wives (and 5 Truths to Face Them)</a> on thegospelcoalition.org <a href="https://www.newchurches.com/resource/three-relationships-church-planting-wives-need-to-cultivate/">3 Relationships Church Planter Spouses Need to Cultivate</a> by Christine Hoover <a href="https://www.christianitytoday.com/women-leaders/2016/october/13-tips-for-women-church-planters.html?paging=off">13 Tips for Women Church Planters [and their husbands]</a> on christianitytoday.com | 14 | 7 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: 2017-03-08 link to churchplantingwives.com takes user away from PlanterPlan, tried to update link to open new window --pb 2017-08-30 link target fixed, content validated --pb 2019-12-10 content updated --pb 2020-02-24 additional resources subsection added --pb 2020-05-26 new additional resource added --pb 2020-06-11 new additional resource& added --pb 2022-03-31 new additional resource& added --pb 2022-11-21 new additional resource added --sc
26 | 29 | 20 | Form a Management Team (oversight) | Put oversight and accountability mechanisms in place for the new church. | It's a bad idea for new churches to put local Biblical Elders in place too soon. Resist installing elders before the 2nd anniversary of launching worship gatherings. You'll end up installing leaders with pre-existing agendas or moving new believers too quickly into leadership. But holding off places an increased burden of responsibility on you. During this critical time, you need spiritual coverage and wise counsel. In the absence of a Biblical Eldership, you need a trusted group of godly people to provide oversight. Where a Biblical Eldership is not in place, Passion for Planting recommends forming a Management Team. Management teams typically: Provide counsel Define the church plant's scorecard Approve big-decision items like staffing, facilities, budget, etc. Keep the new church true to its vision, values and beliefs Provide accountability for progress toward defined goals and expectations Provide spiritual prayer coverage for the new church Ensure the planter is maintaining healthy boundaries Consist of 3 to 7 people Include one representative from each group that is providing significant financial support Remain in place until local Biblical Eldership is put in place (and they have a say in the timing of this) and/or the new church is financially self-sufficient Are recognized in the church's Bylaws as the initial leadership team for the new church Meet at least 2 times per year during the first 2 years; Passion for Planting recommends meeting monthly where possible The tricky part is that though you my have invited them to serve on the team, you are placing them in a collective position of authority over you. Build a team of people who can speak the hard truth to you in love and not simply rubber stamp everything. Resist the temptation to skip a Management Team. You need the spiritual coverage and wise counsel of Godly people who are committed to you and the new church. | Put a Management Team or similar oversight structure in place using the guidelines above. Have the Management Team read the brief post <a href="https://www.churchplantingtactics.com/when-does-a-management-team-win/">When Does a Management Team Win?</a> Meet for the first time. This action is complete when the Management Team has convened their first meeting. |  | 21 | 21 | 2015-02-03 05:00 | 2022-11-15 05:00 | 2000-01-01 05:00 | template: standard 2017-08-30 content updated --pb 2022-11-15 nick wrote in a comment, nothing else --nz
27 | 31 | 20 | Call your coach about church planting goals and expectations | Open a conversation with your coach about how you will measure pre-launch health and live up to what your sending church or church planting network expects of you. | Your management team (oversight) is charged with defining the church plant's scorecard and holding you, the planter, accountable to goals for each metric. They should also ensure that the expectations of the sending church or church planting network are being met. Tap into your coach's wisdom and experience to explore setting your own church planting goals and meeting all of the expectations placed on you. Sample issues to process with your coach: The management team's desired outcomes (the scorecard) The sending church or church planting network's expectations Uncovering assumptions Making sure everyone is on the same page about your model or approach to planting How to negotiate changing something that's expected of you | This action is complete when you have called your coach about your goals and expectations. |  | 35 | 7 | 2015-02-03 05:00 | 2021-01-25 05:00 | 2000-01-01 05:00 | template: standard 2017-05-30 content updated, audience changed to coach --pb 2019-12-10 content updated --pb 2020-12-11 changed Due in # Days from 45 to 35 --pb 2021-01-25 content updated --pb
28 | 30 | 20 | Get your stakeholders to agree on a scorecard and other expectations | Get your Management Team to unite around what needs to be accomplished in the planting process. | Your entire Management Team needs to be in complete agreement on the desired outcomes of the church plant. An effective way of getting there is to create a scorecard for the pre-launch season. In that process you'll have to decide on what to measure and how much to shoot for in each of those metrics. Measure what's most important to the DNA of the new church. What gets measured gets done. Broadly, that might include: people finances groups multiplication etc. On top of that, your sponsoring church or church planting network will have expectations of you, the planter, and of the new church. You may have had to agree to something in writing, or the expectations may be implicit. If those were put in place before your Management Team was formed, each of them need to know what those things are and be in alignment with them. Possible expectations could include: When to launch in-person worship gatherings The basic approach or model for planting the church Location Attendance Goals or other metrics Fundraising Goals Style of Worship Date for the planter to move on location Governance of the new church An expectation to complete an assessment and/or training A "tithe back" or other financial participation in the network Kinds of marketing that should(n't) be used Whether expressed or implied, now is the best time to get the expectations out in the open. Neither side wants surprises here. | Prayerfully draft a scorecard for the church plant, both categories to measure and goals for each. Request a written list or summary of expectations from your sending church or church planting network. All parties, including the planter and coach, should agree to these expectations. This action is complete when written expectations have been agreed upon by all parties. |  | 42 | 14 | 2015-02-03 05:00 | 2022-12-23 05:00 | 2000-01-01 05:00 | template: standard 2017-08-30 content updated --pb 2019-01-11 Due in # Days changed from 45 to 52 --pb 2019-12-10 content updated --pb 2020-12-11 changed Due in # Days from 52 to 42 --pb 2021-01-25 content updated --pb
29 | 32 | 20 | Coaching Checkpoint: Review and Affirm the planter's church planting scorecard | Ensure that the planter is measuring the most important things in support of the vision of the new church plant. | The church planter, along with the Management Team, gets to set the DNA of this new congregation. To some degree, the planter gets to start with a blank slate as far as what gets measured. The traditional scorecard of the church in the West has been attendance, offerings, and square footage, which is an incomplete scorecard at best. A healthy scorecard for the pre-launch season will have approximately 6 metrics with goals set for each. Dozens of things could be measured, but to save hiring more staff just to measure stuff, only the most important things should be tracked at this point. | Review the planter's proposed scorecard. Provide feedback to the planter. Instruct the planter to present it to the Management Team for deliberation and approval. This action is complete when you, the coach, have provided feedback on the proposed church planting scorecard. |  | 49 | 7 | 2015-02-03 05:00 | 2021-01-25 05:00 | 2000-01-01 05:00 | template: standard 2017-08-30 content updated, audience of task changed to coach --pb 2018-08-21 title tweaked, content tweaked --pb 2019-01-11 Due in # Days changed from 45 to 52 --pb 2019-12-10 content updated --pb 2021-01-25 content update --pb 2020-12-11 changed Due in # Days from 52 to 49 --pb
30 | 33 | 1 | Milestone: Develop an Intercessory Prayer Team | Recruit and communicate regularly with a prayer team to provide spiritual covering for your disciple-making efforts. | William Temple said, "When I pray, coincidences happen, and when I don't pray, they don't." Making new disciples is a spiritual act. No matter how gifted and talented the church planter is, he/she will fail without being rooted in prayer. The tasks in this milestone will walk you step-by-step through building a strong prayer team with healthy rhythms. |  |  | 14 | 7 | 2015-02-03 05:00 | 2019-11-22 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated --pb 2019-11-22 content updated --pb
31 | 34 | 33 | Read this Prayer Team overview | Gain an understanding of the importance of having a prayer team and create a strategy to bathe the church plant project in prayer. | Making disciple-makers is a spiritual exercise. Fundamentally, you will be storming the gates of hell. You have to spend time in prayer yourself AND recruit others to be a part of praying for the project. This milestone will walk you through crafting an Intercessory Prayer Team Strategy and provide you with some very practical tools and disciplines to make communicating prayer requests to your team easy. | View the <a href="/resources/item/212">Initiate Prayer Team Training Video</a> by Dr. Ed Stetzer. This action is complete when you have watched the prayer team training video. |  | 8 | 1 | 2000-01-01 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated --pb 2018-11-02 content updated --pb 2019-11-22 content updated --pb 2020-12-11 changed Due in # Days from 14 to 8 & Duration from 7 to 1 --pb
32 | 35 | 33 | Craft an Intercessory Prayer Team strategy | Create a strategic approach to recruiting a prayer team and keeping them updated with regular communications. | No partner is more important than prayer partners. Making new disciples and planting a church is a big deal. Satan does not want you to succeed. Surrounding yourself and your team with prayer partners is the single best thing you can do to ensure success. Many planters underestimate the amount of spiritual warfare they will face. You have to make prayer a priority. Do not be shy in asking people to join the prayer team. Consider how you can use prior church relationships to recruit people. Maybe you'll ask supporting churches to give you e-mail lists/groups to invite people to join in prayer. But be careful not to SPAM or sign people up who are not interested - only invite people to join the team. Contact as many friends and relatives as possible and ask them to be part of the team. Ask each of them to recruit additional prayer team members. The goal is to get hundreds (or thousands) of prayer team members actively praying for the new church. The prayer update is a great communication tool for keeping people informed and requesting prayer. An Inner Circle Consider inviting a small handful of prayer warriors into an inner circle relationship. Your prayer update will be going out to hundreds of friends, family & supporters. When that hard day comes when you feel like quitting, and it will, you need people praying for you, but you may not want to broadcast that to your entire distribution list. Set a Schedule You Can Maintain It is easy to get busy and forget to send updates to your prayer team. Set an expectation for how often you will send updates for each method of communication you've chosen. Set a recurring appointment in your calendar to serve as a reminder. | Take time away with God, seek His wisdom and counsel on how best to engage an army of prayer warriors committed to covering this project. Download Passion for Planting's Prayer Team Strategy Template (<a href="/resources/item/329">MS Word</a> or <a href="/resources/item/376">Google Doc</a>). Fill in the blanks to craft your own Prayer Team Strategy. This action is complete when all subordinate actions have been completed. |  | 14 | 7 | 2000-01-01 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated, new resource link added& --pb 2018-06-01 content updated,& gdoc& template added --pb 2019-11-22 content updated --pb 2021-01-28 merged in content from task "Develop a schedule for communicating with the prayer team" --pb
33 | 36 | 35 | Brainstorm list of potential Prayer Team partners | Recruit an army of people to pray for the you, your family, and the new church. | In 30 minutes, sit down and compile a list of every person you know who would pray for the church. Utilize tools you already have such as your address book, Facebook, etc. Consider the following groups of people to include in your list: Family and extended family Friends Neighbors Co-workers, previous co-workers, and other Christians in the work place Current and previous church memberships Other church memberships | Brainstorm a list of potential prayer partners. Compile their names and email addresses in a spreadsheet, address book, closed social media group or email marketing app (Mailchimp, ConstantContact, etc). This action is complete when you have brainstormed a list of potential prayer partners. |  | 14 | 7 | 2015-02-03 05:00 | 2019-11-22 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated --pb &
34 | 37 | 35 | Determine Prayer Team communication method(s) | Determine the best way to communicate prayer needs in order to minimize your admin burden and maximize the team's engagement. | Group email programs allow members to easily signup to receive emails and for planters to email large numbers of people in a single email. Most group email apps also allow tracking to determine what percentages of emails are being opened. Passion for Planting recommends <a href="https://mailchimp.com/">Mailchimp</a>. It is a powerful yet easy-to-use app that produces professional-looking group emails. It has numerous pre-designed templates. Social media also provides a simple and often real-time way to communicate with your prayer team. If you are active on social media like Facebook, create a closed Group and add your prayer team members. Blogging is also an effective way to update the prayer team. Simply subscribe the prayer team to receive emails of each blog post. This will keep them in the loop and help them know how to pray. Writing letters or sending pictures from time to time is also effective. This can give your intercessory prayer team something to stick on the fridge as a daily reminder to pray. At the end of the day, you need to pick a method that will not be so labor-intensive that you stop using it when your schedule gets busy. Sending a 280-character tweet every week beats a monthly newsletter that never gets written. | Determine the easiest and most widely used way(s) to communicate with the prayer team. Create an account or group. This action is complete when you have determined the best way to communicate with the prayer team. |  | 14 | 7 | 2015-02-03 05:00 | 2019-11-22 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated, preferred vendor changed from ConstantContact to Mailchimp --pb 2019-11-22 content updated --pb
35 | 39 | 1 | Milestone: Implement Intercessory Prayer Team Strategy | Put into practice what you decided to do when crafting your Prayer Team Strategy. | If you can create a culture that communicates that God is leading this whole venture, your team will be more likely to seek God's wisdom and counsel on the pieces they are responsible for. In addition, a prayer culture will spill over into the life of the church as it grows and becomes more established. That helps create a leadership team and church that truly understand that, "it's not about us." This starts by getting the Intercessory Prayer Team praying regularly for you and the plant. If you are not a detail-oriented person, consider asking your coach to hold you accountable to the plan, or recruit a prayer team champion who will take responsibility for communicating to the prayer team. |  |  | 30 | 16 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated --pb 2019-11-22 instructions for adding custom tasks removed --pb 2019-12-03 content updated --pb 2020-12-16 changed Due in # Days from 35& to 30& & Duration from 21& to 16& --pb&
36 | 42 | 39 | Recruit prayer partners | Invite people to opt in to your Prayer Team and increase the prayer covering of your church plant. | Allow people to opt in to your intercessory Prayer Team updates rather than spamming them and forcing them to opt out. It honors them to give them a choice in the matter. One or two initial email blasts or social media invitations to invite people to join is appropriate. Decide how you'll send out invitations and what expectations you'll communicate, both for them and for you. Get a minimum of 10 people praying regularly immediately. Especially approach those individuals who are known to be consistent prayer warriors. Then grow your list to several dozen or even several hundred . | Use the contact list you brainstormed in a previous PlanterPlan action. Contact them about being on your prayer team. Add an online sign-up form to your supporter website or social media page so that people can continue to join. This action is complete when you have received commitments from at least 10 people to pray on an ongoing and regular basis for you, your family and the new church. But set your sights on 100. |  | 28 | 14 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated --pb 2019-11-22 content updated --pb 2020-12-11 changed Due in # Days from 14 to 28 & Duration from 7 to 14 --pb
37 | 52 | 39 | Initiate regular Prayer Team updates | Initiate regular Prayer Team updates so that they can most effectively present your requests to God. | Passion for Planting recommends weekly communication with the prayer team. This is frequent enough to stay in the minds of the team members, but not so frequent as to be annoying. The weekly update is a great way to celebrate wins and God's provision and to keep people informed of needs. Suggested initial prayer requests: You - You need God's wisdom, patience and strength Your family - specifically balance and health in your marriage and family Protection - Satan will attack you, your family, and anyone who wants to join you Vision - that God would guide your planning and give you a clear vision for the new church Finances - only God can provide Consider rotating through the following in your ongoing, regular updates: Completed milestones from your launch plan (especially big decisions like choosing a name or selecting a facility) Unexpected blessings and provisions (key contacts and relationships in the community, unexpected financial donations, etc.) Answers to prayers (finding a location to meet) Upcoming launch plan actions Your biggest celebrations and your biggest concerns Financial status Staffing status Facilities status Spiritual warfare issues Be consistent. You absolutely have to send updates regularly, so keep the system lightweight. If you are not a detail-oriented person, consider recruiting a prayer team champion who will own communicating to the Prayer Team. | Craft a simple communications template that you can easily reuse in sending out regular updates. Send out the first prayer team update. Recruit someone to hold you accountable to sending regular updates. This action is complete when you have set up each medium and sent the inaugural prayer update. |  | 30 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated --pb 2019-11-22 content updated --pb 2020-12-11 changed Due in # Days from 35 to 30 --pb
38 | 238 | 1 | Milestone: Set Up Personal Accountability | Put a system of accountability in place to protect yourself from spiritual attack and to limit temptation. | Do not underestimate the spiritual implications of starting a new church. The enemy does not want to see new churches started. You will face spiritual attack and often at your most vulnerable point. This milestone will help you create a system of accountability. One of the best things you can do for yourself and your family is to set up accountability to protect them and yourself. The worst service you can do to yourself, your family, your church, and ultimately the Kingdom is to ignore these simple steps and set yourself up to be yet another pastor embroiled in scandal. Nothing will destroy the new church faster. |  |  | 45 | 45 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-09-26 content updated --pb 2019-11-22 content validated --pb 2020-12-16 changed Due in # Days from 60& to 35& & Duration from 14& to 35& --pb&
39 | 237 | 238 | Plan downtime for move | Schedule time in your calendar to take care of everything associated with moving to your target community. | Inevitably, moving takes more time than you plan for. There's the packing of boxes, scheduling a moving truck, forwarding mail, getting new license plates and driver's license, unpacking, etc. Rather than stressing about what you are not accomplishing, set aside days on the calendar to take care of all the moving details. Schedule other church planting tasks to be done later. You should try to live within your target area. Avoid living in a much nicer home/neighborhood than the average family you will be reaching. There is also no better way to begin forming a core group on-site than through relationships with neighbors. You may consider renting a home or apartment in the area prior to buying in order to gain a better understanding of the area and where your target demographic lives. | Determine your move date. Estimate reasonable time required for move (both packing and unpacking at least one to two weeks where you plan not to work). Add moving dates to the church calendar. Review your Launch Plan schedule to determine schedule conflicts. Adjust schedule as necessary to provide adequate time for move. This action is complete when you have scheduled time off to move. |  | 7 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: 2020-01-24 content updated --pb 2020-12-11 changed Due in # Days from 56 to 7 & Duration from 14 to 7 --pb
40 | 239 | 238 | Call your coach about personal accountability | Open a conversation with your coach about your own personal accountability systems and structures. | Every Christian needs to have accountability. You are no exception. Too many pastors have failed morally or otherwise, in part, because they never put good accountability in place. Sample issues to process with your coach: How to balance family and ministry time, especially evening meetings Leaving margin in your calendar for sabbath and renewal Staying spiritually alive amidst the busyness of planting How to remain engaged in meeting people who do not know God Leadership reproduction accountability mechanisms Creating a culture of accountability among staff | This action is complete when you have called your coach about accountability. |  | 14 | 1 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-30 content updated, audience changed to coach --pb 2019-11-22 content updated --pb 2020-12-11 changed Due in # Days from 53 to 14 & Duration from 7 to 1 --pb
41 | 240 | 238 | Develop a personal accountability plan | Create an intentional plan to support your own personal accountability. | Its the fourth quarter of the Super Bowl. Your team is driving down the field for the go-ahead points. Your right guard has a broken hand and on the last play he went down with a knee injury. With no one to back him up he stays in the game. The defense comes to the line and is showing blitz. Can you take a guess at who they are coming at with the bull rush? It doesn't take a football expert to know that right guard is going to be tested. In the same way, the forces of darkness will test your spiritual life. Part of being human is to have a bent towards sin. It is why Jesus died for us. Each of us has our own unique struggles with sin. It is what Paul called the thorn in his side . But Scripture teaches us that, "No temptation has seized you except what is common to man. And God is faithful; he will not let you be tempted beyond what you can bear. But when you are tempted, he will also provide a way out so that you can stand up under it." 1 Corinthians 10:13 NIV . One of the ways that God provides a way out is through a plan of accountability. This plan will function as a safeguard. You wouldn't play pro football without pads and a helmet, and you shouldn't try and live the Christian life without accountability. Your personal accountability plan should include the following topics: Sabbath rest: This one made it in the 10 commandments, so its probably important. Honor God by resting. What day will you rest? Who will hold you to it? How will you remind yourself and protect the day? Personal Relationship with God : Take time to write out your habits for spiritual disciplines. What are your areas of strength? What areas do you need to improve? What steps can you take to grow closer to God through disciplines? Family Life : If you are married and if you have kids, they are your first church. What healthy boundaries will you put in place to ensure you are spending time with them? How will you fulfill your responsibilities to them? Building relationships with those that don't know God yet : Your people won't follow where you don't lead. What are you personally doing to build bridges with those who don't know God? How are you putting yourself in places to come in contact with not-yet-believers? Reproducing leaders and teams : Who are your "disciples"? Who are the leaders you are investing in to build the church? Launch Plan : Who is holding you accountable to complete the tasks of the launch plan to ensure a healthy church launch? Internet Accountability : What Internet monitoring or filtering software are you using? Who gets the reports? (see subsequent PlanterPlan task for help) Mentoring : Who is your mentor? Who is the person whom you confide in about your temptations and weaknesses? Who is your Nathan that will call you out if you fail? The Team : How will you provide accountability for your staff and other leaders in the church? | Read through each of the areas above and create a written plan for each topic. Brainstorm additional areas in your life for which you need to be held accountable. Add a written plan for each of those areas. Send the plan to your coach or mentor for review and feedback. This action is complete when you have developed a written plan of accountability. | <a href="https://careynieuwhof.com/some-thoughts-on-why-megachurch-pastors-keep-falling/">Some Thoughts on Why MegaChurch Pastors Keep Falling</a> by Carey Nieuwhof Billy Graham's <a href="https://billygrahamlibrary.org/on-this-date-the-modesto-manifesto/">Modesto Manifesto</a> on billygrahamlibrary.org <a href="https://careynieuwhof.com/episode253/">The New Rules for Men and Women in the Workplace</a> on the Carey Nieuwhof Leadership Podcast | 28 | 7 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-09-26 content validated --pb 2019-11-22 content validated --pb 2020-12-11 changed Due in # Days from 60 to 28 --pb 2022-11-21 updated links --sc
42 | 241 | 238 | Install an internet filtering or accountability app | Install internet monitoring or filtering software to set a good example and to help with your own online integrity. | Pornography is predatory. Even if you haven't had an addiction in the past, the Enemy would like nothing better than to get you caught up in porn during the crazy-difficult season of planting a church. You need to have an extra layer or two of prevention on all of your electronic devices. A secondary reason to protect all your devices is to set a precedent for your staff & key volunteer leaders. Also, some of the services below give you the side benefit is having documentary evidence/history if you're ever accused of porn use. There are 3 main avenues to secure your devices: Accountability & Filtering Software Accountability software doesn't prevent a user from viewing inappropriate content, but instead sends a report to an accountability partner. Filtering software attempts to prevent the user from visiting those sites, and will also send reports. Current best options (Fall 2019): <a href="https://x3watch.com/x3watch-plan-features/?v=2.1">X3Watch</a> - $70/yr individual or $100/yr family plan <a href="https://accountable2you.com/pricing">Accountable2You</a> - $70/yr individual, $120/yr family, or $120/yr + $67/yr per user group license <a href="https://everaccountable.com/plans/">EverAccountable</a> - $70/yr individual or $100/yr family plan <a href="https://www.covenanteyes.com/how-it-works/">CovenantEyes</a> - $192/yr group (10 users) Parental Control Software These are really designed to help parents with the kids' online activity. This could serve a 2-fold purpose if you set your spouse up as the admin and you don't have the password. Current best options (Fall 2019): <a href="https://www.qustodio.com/en/premium/">Qustodio</a> - $55/yr for 5 devices <a href="https://www.netnanny.com/alt/">NetNanny</a> - $55/yr for 5 devices <a href="https://www.bark.us/#pricing">Bark</a> - $99/yr for unlimited devices Router-Based Filters These are economical because you don't have to purchase or install an app on every connected device. Any device that connects to the router gets only filtered internet. The downside is that as soon as you leave the house or decide to use cellular data, the router is circumvented. Some of the services below are beginning to write mobile apps to address that. Consider using a router solution along with one of the other solutions above. Current best options (Fall 2019): <a href="https://www.bark.us/learn/router-limits-bark-home/">RouterLimits</a> - $80 for the router (1-time), free subscription <a href="https://meetcircle.com/">Circle</a> - $129 for the router and first year (1-time), $120/yr for 10 devices <a href="https://cleanrouter.com/pricing/">CleanRouter</a> - $180 upgrade option (1-time), requires $120/yr basic subscription or $180/yr premium subscription None of these solutions is bullet-proof: a savvy user will be able to defeat or circumvent the app. And you still need to install at least one of these safeguards on every internet-connected computer, tablet & phone. | Choose an accountability software and install it on all computers you use. Install it on all your phones and tablets. If you chose a monitoring software, ask an accountability partner's permission to receive your reports. This action is complete when you have installed internet filtering or accountability software. |  | 28 | 7 | 2015-02-03 05:00 | 2024-02-13 14:23 | 2000-01-01 05:00 | template: standard 2019-11-22 content & links verified and updated --pb 2020-12-11 changed Due in # Days from 60 to 28 --pb
43 | 242 | 238 | Initiate a mentoring/accountability relationship | Find someone who is more interested in supporting you than in the progress of your church plant project. | You're about to face many trials and temptations. Being a pastor can be a very lonely job. But it doesn't have to be. Seek out a mentoring relationship with someone who understands the unique trials a church planter faces. This person should be someone you trust and someone who can speak truth and wisdom into your life. You should feel like you can tell the mentor anything and that he will treat you with love and grace. "Though one may be overpowered, two can defend themselves. A cord of three strands is not quickly broken." Ecclesiastes 4:12 . | Brainstorm a list of people who could serve as your mentor. If needed, ask others whom a good candidate might be. Ask that person to serve as your mentor. Give them a copy of your plan of accountability. Set up a regular schedule to talk. This action is complete when you have a regular schedule in place to talk to you mentor. |  | 28 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-09-26 content validated --pb 2019-11-22 content updated --pb 2020-12-11 changed Due in # Days from 60 to 28 --pb
44 | 243 | 238 | Coaching Checkpoint: review and affirm personal accountability plan | Review the planter's accountability plan and provide feedback where necessary. | After completing the accountability plan, the planter will send it to you for review. Read and review the plan and ensure that it covers the essentials, including: Sabbath rest Personal relationship with God (including spiritual disciplines) Family Life Building relationships with those that don't know God yet Reproducing leaders and teams Executing the Launch Plan Internet accountability Mentoring Staff accountability | Receive an accountability plan from the church planter. Read and ensure the above areas have been addressed by the plan. This action is complete when the coach has reviewed and affirmed the planter's accountability plan. |  | 35 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-09-26 content validated --pb 2019-11-22 content validated --pb 2020-12-11 changed Due in # Days from 60 to 35& --pb
45 | 1280 | 1 | Milestone: Articulate Your Disciple-Making Strategy | Create a document that will explain in plain language how your church will go about fulfilling Jesus' Great Commission to make disciples of all nations. | There has been a much-needed rebirth of conversation around disciple-making in the United States. Throughout PlanterPlan, you will see it referred to as "disciple-making" and not "discipleship" because of the baggage and sometimes ambiguity that comes with that term. It's safe to say that Jesus was the best disciple maker of all time. The things we see him doing in the Gospel accounts should inspire how we approach discipleship and how we create environments and processes that multiply disciples. This milestone will walk you through doing the hard work of digging back into scripture with fresh eyes for Jesus' disciple-making genius. |  |  | 234 | 220 | 2019-10-14 04:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: 2020-12-11 changed Duration from 7& to 1& --pb 2021-03-12 Ephesiology& URL& added --pb 2022-11-21 updated links --sc
46 | 1281 | 1280 | Read this evangelism & disciple-making overview | Understand the key elements of a Disciple-Making Strategy and how it relates to evangelism. | Planting churches was not Jesus' Great Commission. That's challenging. He sends us to make disciples of all nations, baptizing them in the name of the Father and the Son and the Holy Spirit, and teaching them to obey everything He commanded us. When we see making disciple-makers as our job, then everyone we meet is someone we can help on their journey to becoming a disciple-maker themselves: If they aren't already trusting and following Jesus, then they need to hear the Good News and be challenged to respond If they trust Jesus but aren't a disciple-maker, they need tools, experiential training and loving accountability If they're an obedient disciple-maker, then they're an ally and co-laborer When disciple-making multiplication takes hold, churches inevitably result. "As wise stewards of the mystery of Christ, we must subscribe to a definition of biblical church planting as evangelism that results in new churches. Or, to communicate it in other terms: disciple-making that results in new churches." <a href="https://vergenetwork.org/2013/09/09/why-jesus-never-commanded-us-to-plant-churches/">J.D. Payne</a> The danger we fall into is wanting to plant churches so that we can reach people for Christ. That's completely backwards. "Don't plant churches for evangelism. Plant churches through evangelism." unknown Especially because the Western Church hasn't done this well for years, perhaps generations, you need to be clear about your disciple-making process. It needs to scriptural, prayed through, and easily reproducible. The tasks in this milestone will help you write down your disciple-making process, which will include getting out there and 'evangelizing' your community (identifying new disciples). | Watch Jim Putman's video <a href="https://www.youtube.com/watch?v=fDE-uVpMqzM">Discipleship at the Core</a> by Exponential. This action is complete when you have watched the video and read the overview above. " | Bill Hull's video <a href="https://www.youtube.com/watch?v=1x3cIie-xEk">Making Disciples</a> by Exponential Dann Spader's <a href="https://likejesus.church/our-philosophy/">Like Jesus Resources</a> book and videos Ephesiology Master Class: <a href="https://masterclasses.ephesiology.com/courses/identity-based-discipleship">Identity Based Discipleship</a> (led by Michael Cooper and Andrew Johnson) | 15 | 1 | 2019-10-14 04:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: 2019-10-14 new task --pb 2020-12-11 changed Due in # Days from 14& to 21& --pb
47 | 1282 | 1280 | Call your coach about evangelism & making disciples | Open a conversation with your coach about making disciples that make disciples. | You may or may not have ever experienced healthy disciple-making, the kind that reproduces generations of disciple-making disciples. You may have to learn some new skills and unlearn a few old habits or assumptions. You need to come into this church plant with a clear & compelling vision for making disciple-makers, along with a simple, reproducible process for getting it done. Sample issue to process with your coach: The relationship between evangelism and disciple-making The difference between information and obedience How to get to the 3rd generation of disciple-makers before launching weekly worship gatherings Ways that the coach has experienced Biblical disciple-making | This action is complete when you have called your coach about evangelism and disciple-making. |  | 21 | 7 | 2019-10-14 04:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: 2020-12-11 changed Due in # Days from 28& to 43& --pb
48 | 1274 | 1280 | Craft a Disciple-Making Strategy | Draft a comprehensive strategy for launching a disciple-making movement. | How you make disciples is ultimately how your disciples will make them, too. Now is the time pray & think through what you're going to do and how. Making disciples is the Church's God-given mandate. Devoted disciples attract people outside the church because of the change others see in their Christ-like lives. And they reproduce themselves in others, refusing to be the last link of the chain stretching all the way back to the first Disciples. The purpose of this Disciple-Making Strategy is to imagine and implement a biblical process to empower Christians to be more like Christ as they intentionally develop relationships with not-yet-believers. It's safe to say that Jesus was the best disciple maker of all time. The things we see him doing in the Gospel accounts should inspire how we approach discipleship and how we create environments and processes that multiply disciples. Using the Disciple-Making Strategy Template (<a href="/resources/item/321">MS Word</a> or <a href="/resources/item/361">Google Doc</a>), you will work through the following: Why disciple-making? Disciple-making in the Bible Disciple-making at your church Disciple-making in our community Your approach The tools you'll use Digital Tools When someone comes to faith at your church, what resource(s) do you offer them to help them take next steps in their spiritual development? Many churches are seeing the benefit of offering new believers a spiritual starter kit to guide them towards maturity and challenge them to put their new faith into practice. (For the early church it was simple creeds) Will your church have such a resource to help new believers invest in their relationship with God? While this resource could be a physical book or pamphlet, we recommend you equip people with a digital resource, so they can easily access it, not worry about misplacing it, and freely share it with their friends. Here are some examples: <a href="https://www.startingwithgod.com">Starting With God</a> <a href="https://thechapel.com/site/assets/files/6625/yourfirstweekdevotional_2020.pdf">Your First Week As A Disciple</a> <a href="https://www.bible.com/reading-plans/13502-start-here-first-steps-with-jesus">Start Here</a> - Bible Reading Plan Resources like these are not intended to take the place of personal, relational discipleship, but could serve as an initial guide for that discipleship relationship and as a springboard to help new believers begin feeding themselves and others spiritually. Develop this resource yourself or use content that's already been created. | Download Passion for Planting's Disciple-Making Strategy Template (<a href="/resources/item/321">MS Word</a> or <a href="/resources/item/361">Google Doc</a>). Work through the content above and the subsequent PlanterPlan subtasks; record your thoughts & decisions in the template. Interview leaders of other disciple-making movements you respect about their structure and systems. Finalize your Disciple-Making Strategy. Send the completed Disciple-Making Strategy to your coach for feedback. This action is complete when you have submitted your written Disciple-Making Strategy to your coach. |  | 234 | 220 | 2019-10-14 04:00 | 2021-07-27 04:00 | 2000-01-01 05:00 | template:
49 | 1385 | 1274 | Take a fresh look at disciple making in the Bible | Examine with fresh eyes what God's word shares with us about making disciples and carrying out the Great Commission. | Jesus didn't leave any doubt as to what the mission of His church is: make disciples. That's our number one mandate. What's less clear is how do we do it? How do we obey Jesus' last command? Are disciples made through attending worship gatherings? Are they produced by attending a small group or serving on a ministry team? Are they developed by practicing spiritual disciplines like praying and reading God's word? What will your church do to help people take next steps in their relationship with God and live on mission for him? That's what you'll need to be clear about and the best place to find the answer to that question is the Bible. Revisit the gospels to see what Jesus did to make disciples. Then look in the book of Acts and Paul's epistles for clues about how Jesus' first disciples took what they learned from him and then imparted to others in their efforts to make more disciples. From this investigation you'll want to articulate the following: How you see the Bible defining discipleship What a disciple looks like in the Bible The disciple-making process you see in scripture The major stages of spiritual development in the life of a disciple | This action is complete when you've investigated Jesus' method for making disciples and can articulate what discipleship looks like in the Bible. | <a href="https://www.christianbook.com/discipleshift-steps-your-church-make-disciples/jim-putman/9780310492627/pd/492627?en=google&event=SHOP&kw=church-supplies-0-20%7C492627&p=1179710&dv=c&gclid=CjwKCAiAz4b_BRBbEiwA5XlVVnkbRiQjgiJxBCb7BxcAKG2s-PNXHUuD-Bsa8xhHeGv40-lvn192rhoCtI0QAvD_BwE">DiscipleShift: Five Steps That Help Your Church to Make Disciples Who Make Disciples</a> <a href="https://www.amazon.com/T4T-Discipleship-Re-Revolution-Planting-Community/dp/0974756210">T4T: A Discipleship Re-Revolution</a> <a href="https://www.christianbook.com/master-plan-evangelism-2nd-edition-abridged/robert-coleman/9780800788087/pd/788087?en=google&event=SHOP&kw=church-supplies-0-20%7C788087&p=1179710&dv=c&gclid=CjwKCAiAz4b_BRBbEiwA5XlVVgHphb9-SHVey8cnxsroVH3VavlyObuHcR-EKM5ZED2Mtj6FTTfOOxoCgcMQAvD_BwE">The Master Plan of Evangelism</a> <a href="https://multiplication.org/product/revisiting-the-master-plan-of-evangelism/">Revisiting The Master Plan of Evangelism</a> | 36 | 14 | 2021-01-15 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: 2022-11-21 updated resources --sc
50 | 1386 | 1274 | Create a contextual definition of 'disciple' | Develop a concise definition for what a disciple is in your church. | Many churches talk about making disciples, but what is a disciple of Jesus? As a church planter you may have an idea in your head as to what a disciple is, but how can you communicate that in a way so everyone in your church knows what a disciple is and share that truth with others? The easy way to complete this task is to define a disciple as a follower of Jesus. That definition passes the concise test, but it's also vague and uninspiring. Think about developing a definition of a disciples like developing a mission statement for your church. Your mission as a church is to make disciples, but that's probably not your mission statement, right? Why? Because it's not compelling or contextual, unique to what God's doing in you and around you. Review your notes from the previous task and spend time in prayer asking God to reveal to you what a disciple is in your context. Here are some examples: A disciple is someone who hears God's voice and follows A disciple is someone who trusts and follows Jesus A disciple is someone who lives to obey the commands of Jesus A disciple surrenders everything they have to obey Jesus' call on their lives A disciple is someone who yields the God's spirit and produces His fruit A disciple imitates daily the grace and generosity of Jesus A disciple lives and loves like Jesus daily and helps others do the same | This action is complete when you have defined what a disciple is in your context. |  | 36 | 14 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template: 2022-11-21 updated link --sc
51 | 1387 | 1274 | Identify tools and training resources for disciple making | Develop a list of tools your church will have at its disposal to help produce and multiply disciples. | For over two thousand years Jesus' church has been making disciples. They used many different tools to help them accomplish this mission. Before the New Testament was written church leaders develop simple creeds which helped believers understand basic truths about Jesus and share it with others. In that way they served as discipleship tools. They helped the early church make disciples who made disciples. We see some of these creeds in the Bible (Philippians 2:6-11; 1 Corinthians 15:3-10; 1 Timothy 3:16). Notice how short these creeds were. It's not until hundreds of years later that we get the much longer Ecumenical creeds like the Apostle's Creed and the Nicene Creed. While these creeds are packed with theological truth and meaning, they aren't the most effective tools when attempting to make disciples who make disciples. Think about these disciple-making tools as resources you'll offer believers to help them grow in their relationship with God and invite others to follow Jesus. Just as the tools of a carpenter have specific purposes for specific jobs, so too disciple making tools should be tailored to help believers based where they are on their spiritual walk. Most likely a brand-new believer will need different tools and training resources to help them take next steps in their faith journey than someone who's been following Jesus for years. As you think about disciple-making tools and resources, you may find it helpful to break them into two different categories: short-term discipleship resources and long-term discipleship resources. Short-term resources should include a simple list of commands every believer should learn to obey after coming to faith. Examples of these commands are: Share your story Pray Read God's Word Live in community Give and serve Share the gospel Once you have a short list of commands you see God's word calling us to obey, develop simple ways to train new believers to obey them. Make sure the process is simple and reproducible, so ordinary, everyday believers can train new believers to obey these commands and the process can be passed along to multiple generations of disciples. Long-term discipleship (or ongoing discipleship) tools and training resources will be what your church offers disciples to help them continue to grow in their faith and surrender in obedience after they've been trained in the short-term tools. Long-term discipleship is focused on helping disciples stay connected to Jesus for a lifetime and grow in their love for Jesus after the initial spiritual high runs dry. For more on the difference between short-term and long-term discipleship read <a href="https://www.everywhere2everywhere.org/articles/short-term-discipleship-plan">Short Term Discipleship Plan</a> by Everywhere 2 Everywhere. | Research discipleship tools and resources. Consider which ones make most sense for your context and align with your vision. If you can't find any tools that fit your context or vision, adapt existing tools to meet your church's needs. This action is complete once you've developed a list of tools and resources your church will utilize to help you make disciple who make disciples. | <a href="https://www.movements.net/411">Movements.net 411</a> <a href="https://docs.google.com/document/d/1OvA0LG7gWBA949BPyoYcVoR42mSSGlgPPvT3jtkmVTY/edit">7 Commands of Christ</a> <a href="https://thechapel.com/site/assets/files/6625/yourfirstweekdevotional_2020.pdf">Your First Week as a Disciple</a> <a href="https://www.amazon.com/T4T-Discipleship-Re-Revolution-Planting-Community/dp/0974756210">T4T: A Discipleship Re-Revolution</a> | 36 | 14 | 2021-01-15 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template:
52 | 1284 | 1280 | Coaching Checkpoint: review and affirm planter's Disciple-Making Strategy | Review the planter's Disciple-Making Strategy document to provide feedback and ensure it will be simple and reproducible. | The Disciple-Making Strategy document should incorporate all of the following: Why disciple-making is important Scriptural support for disciple-making How disciple-making will be woven into everything at the new church A plan for making disciple-makers in their community A simple pathway for people to become disciple-makers Tools and training resources to be used | Review the planter's Disciple-Making Strategy document. Provide feedback to the planter. This action is complete when you, the coach, have reviewed and affirmed the planter's Disciple-Making Strategy. |  | 43 | 7 | 2019-10-14 04:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: 2019-10-14 new task --pb 2019-12-16 content updated --pb 2020-12-11 changed Due in # Days from 28& to 22 & Duration from 7 to 1 --pb
53 | 286 | 1280 | Write down your Personal Evangelism Plan | Write out a plan for how you as the lead planter will lead by example and reach people who are far from God. | After assessing you passion for reaching people far from God, develop a personal plan of evangelism to help deepen your passion and practice. To some, evangelism comes naturally. Their heart aches for those who don't know God yet. For the rest of us, we have to be intentional about making connections with people who are far from God. Too often pastors preach about evangelism, but never actually engage in evangelism themselves. You have to lead the way in reaching out to people far from God if the church is to have an evangelistic DNA. A strategy is important, but it's just theory. A plan requires action items with dates, doers and dollars attached. It's time to get really practical with evangelism. Part of any personal evangelism plan should be practical ways to be on mission in everyday life. For example, rather than spending time at home working, frequent the same coffee shop or restaurant to do work. You will get to know the employees and regulars. When you gas up, rather than paying at the pump, go inside to the counter. Avoid drive-throughs. Take the time to go inside and interact with people. Go the grocery store at the same time each week and go to the same cashier. This type of intentional living will help you build relationships. A regular diet of prayer for the lost is also important. Have a list of names to pray for, and pray for a burden for lost people. Also spend time where people far from God spend time. For example, join the gym and go daily at the same time in order to connect with the same people. | Make a list of all the stores and businesses you frequent on a regular basis. Determine how you can be more intentional in how you visit each of those places. Create a prayer list of people you're praying for. Pray for more passion for the lost. Determine where you can spend time that will put you in an environment to connect with the lost. Write those things down and set yourself a monthly reminder to revisit the plan and evaluate how you're doing. This action is complete when you have written out a Personal Evangelism Plan. |  | 51 | 7 | 2015-02-03 05:00 | 2019-11-25 05:00 | 2000-01-01 05:00 | template: standard 2017-06-02 content validated --pb 2019-11-25 content updated --pb
54 | 667 | 1280 | Embed ongoing disciple-making training | Continually promote disciple-making and empower your people to talk to others about Jesus. | Now is the time to embed disciple-making and evangelism deep in the DNA of the new congregation. Making disciples is the mission that Jesus gave us. But an overwhelming number of North American Christians have never been discipled, so they are not making disciples themselves. But that doesn't mean creating a system to give them more information . That approach has gotten us to where we are. The easy part is making disciple-makers of new believers. They'll get it faster and won't have the baggage the rest of us have to undo. The more challenging part is making disciple-makers of churched people. They don't need to sit through another chemistry class; they need time in the lab to practice. Regardless, your training needs to be heavy on practice and light on information. It has to include some version of, "I'm training you so that you can train the next disciple. We're going to practice it right now so you'll be ready." Evangelism is part of making disciples. Provide training on how to do evangelism naturally through everyday relationships. This will equip and empower your people to reach their friends, family, neighbors and co-workers. The expectation from the beginning should be that all Christians figure out some way to make disciples. Your Disciple-Making Strategy needs to be an ongoing element of your church culture for the life of your congregation. | Determine how you'll get people practicing disciple-making and evangelism in practical ways. As appropriate, pick a few simple tools. Put your strategies into motion. This action is complete when your first trainee begins training someone else. | <a href="https://www.movements.net/411">2-Minute Testimony, 3 Circles and Oikos Map</a> by www.movements.net <a href="https://www.navigators.org/resource/the-wheel-illustration/">The Wheel Illustration</a> by www.navigators.org T4T's <a href="https://www.mychurchmovement.com/index.php/live-church-movement-sanantonio/discipleship/7-commands-of-christ">7 Commands of Christ</a> as reposted by www.mychurchmovement.com <a href="https://exponential.org/disciple-maker-assessment/">Disciplemaker Assessment</a> by exponential.org and discipleship.org <a href="https://churchmarketinguniversity.com/evangelism-strategies/">Ten Strategies for Prioritizing Evangelism at Your Church</a> by www.churchmarketinguniversity.com | 51 | 7 | 2015-02-03 05:00 | 2020-07-30 04:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content & links updated --pb 2018-04-20 moved to Launch Team milestone --pb 2019-02-13 additional resources subsection added --pb 2019-04-29 content updated --pb 2020-01-13 content updated --pb 2020-12-14 changed Due in # Days from 110& to 120& & Duration from 7 to 30& --pb&
55 | 162 | 1 | Milestone: Develop Fundraising Strategy | Set a realistic fundraising goal and strategize how to go about raising those funds. | Money follows vision. Start with the vision that God is giving you for the church plant and use that to reverse engineer the required fundraising goal. Fundraising requirements will be different for a different size churches. Big cities may require more funds that a smaller town. Number of initial staff and other considerations all play into the fundraising goal. Many planters aren't natural fundraisers, but most also become quite proficient once they try. The tasks in this milestone will walk you through crafting a solid, actionable strategy and getting feedback from your coach. The subsequent Milestone: Implement Fundraising Strategy will walk you through: Crafting a prospectus (Launch Vision) Developing other promotional materials Setting up online giving and publishing a simple supporter site Drafting scripts, pitches and letters Implementing systems to organize and support fundraising efforts |  |  | 46 | 25 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-30 content updated --pb 2019-11-19 content updated --pb 2020-12-16 changed Due in # Days from 45& to 43& & Duration from 31& to 22& --pb&
56 | 1286 | 162 | Read this fundraising overview | Understand the fundamentals of fundraising so that you can begin the fundraising journey well-prepared. | There's a smart way to go about raising funds, and there are ways that will waste your time, energy, and emotions. Be smart. Attitude & Theology Ask your coach to help you uncover any objections or hang-ups you have about fundraising. Almost no one is a natural-born fundraiser; we all have junk we have to deal with in this process. If you don't start here, your hang-ups will undermine almost everything you do in raising funds. Relationship & Vision Raising funds is really more about casting vision than it is about the money. You're not asking them for money - you're inviting them to partner in the work that God is doing through you. Paint a picture of what this new church could accomplish. Describe what the church will look like. Imagine how the city will be different because of this new church. Invite your supporters into the vision. And fundraising is definitely more about relationships than funding your ministry. If you don't treat it as a one-time transaction, there will be opportunities to pastor and encourage your supporters along the way. All of your tools & tactics should drive toward relationship, not replace it. Helpful Tools & Good Design If you were a carpenter, you'd want to show up to work with the tools you need in your toolbox, right? You should be no less prepared when you meet with people to invite them to join in supporting the church plant. You're going to need things like: appeal letters phone scripts fliers or brochures a meeting outline presentation slides a business plan (to assure high-capacity donors) online giving option(s) basic financial systems notification and thank you systems Don't underestimate the effect the quality of your designs will have on your donors. In our era of graphic design and &uuml;ber-marketing, your print and digital publications need to respectable. You may want to go so far as hiring a graphic designer, especially if you're after tens of thousands of dollars in support - a few hundred dollars will be money well spent. Regardless, don't let your materials be sloppy. That communicates something about how you're going to lead this ministry. Consistency is Key Time and again we have seen novice fundraisers with discipline and consistency raise more funds than gifted, charismatic fundraisers who don't stick with it. Talent is common; hard work is rare. Create a sustainable system that will keep you keeping on. | Read the content above. Commit to writing down a simple, effective fundraising strategy. Commit to working your fundraising strategy even when it gets hard. This task is complete when you have read the content of this overview. |  | 22 | 1 | 2019-10-14 04:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: 2020-12-14 name changed from "get 501c3 nonprofit status"; & changed Due in # Days from 142 to 150& & Duration from 30& to 14& --pb 2021-01-28 merged in content from prior child tasks "Complete the IRS& 501c3 Application" and "Submit the IRS& 501c3 Application" --pb
57 | 163 | 162 | Call your coach about fundraising | Open a conversation with your coach about raising funds for the church plant. | Ministry takes money. Every church planter raises funds in some way, shape or form. Now is your chance to pick the brain of someone who has been there & done that. Sample issues to process with your coach: Setting a fundraising goal Identifying and overcoming my own hesitations Finding new prospects Which print pieces are really necessary Whether to ask for specific dollar amounts How to close a deal How to follow up with 'maybes' Secondary staff fundraising requirements Building a fundraising team | This action is complete when you have called your coach about fundraising. |  | 28 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-30 content updated, changed audience to coach --pb 2018-04-20 updated content, changed audience to planter --pb 2019-12-10 content updated --pb 2020-12-11 changed Duration from 14& to 7& --pb
58 | 166 | 162 | Craft a Fundraising Strategy | Write down a clear fundraising strategy to ensure that you truly and effectively pursue the resources that God has set aside for His work. | Budgeting and fundraising can be two of the most daunting things that church planters face. This doesn't have to be the case. In simple terms, your overall goal is to determine what God is calling you to do (budgeting) and to discover how God will provide for it (fundraising). After initial planning, most church planters discover they need more money to accomplish what they would like to do. You have three options: raise more money spend less money or some combination of the two. The fundraising strategy will address how/when you'll raise the resources you need. | Download the Fundraising Strategy Template (<a href="/resources/item/322">MS Word</a> or <a href="/resources/item/363">Google Doc</a>). Work the subtasks that follow to assist you in completing the template. Send your completed Fundraising Strategy to your coach for feedback. This action is complete when you have an actionable fundraising strategy for the new church. |  | 46 | 17 | 2000-01-01 05:00 | 2021-10-06 04:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' and updated hyperlinks --pb 2018-05-07 added& google& doc template version --pb 2018-11-02 content updated --pb 2020-12-11 changed Due in # Days from 45& to 36& --pb 2019-11-19 title changed from "Issue Written Fundraising Strategy" --pb
59 | 1301 | 166 | Address your personal objections to fundraising | Name and overcome your own personal objections to inviting others to join you financially. | You have assumptions and preconceived notions about fundraising. You may even have faulty theology around finances. Whatever your baggage is, own it. And prayerfully begin working on overcoming it. Because if you don't, your hesitation will keep you from doing the work. And your insecurity will come across clearly when you make an 'ask'. And your results will be predictably insufficient. Common Objections You may find yourself thinking any of these things: I don't like asking people for money It feels weird asking people to pay for my salary I don't come from money, or don't know people of means The Church shouldn't be about money Jesus didn't need to raise funds Fundraising is a secular idea I'm just not naturally good at fundraising Money is the root of all evil (which is a misquote BTW) I don't want this to hurt my relationships Fundraising is embarrassing I can't handle the rejection of people saying no My extended family aren't Christians (so no one will want to give) These are all misconceptions, excuses, or outright lies. If you resonate with any of them, you've got some work to do! | Spend time in prayer and ask Jesus to reveal your objections and misconceptions. Process that list with your coach and your mentor or discipler. Write down the truths from scripture that counter each one of your objections. Pray for grace to overcome and/or heal from any fears, insecurities or doubts you have. This action is complete when you have begun prayerfully overcoming your personal objections to fundraising. " | <a href="https://read.amazon.com/kp/embed?asin=B007QTM8Z8&preview=newtab&linkCode=kpe&ref_=cm_sw_r_kb_dp_QNe1DbGWAPS7V">People Raising</a> by Bill Dillon <a href="https://read.amazon.com/kp/embed?asin=B00CIKKBX6&preview=newtab&linkCode=kpe&ref_=cm_sw_r_kb_dp_xOe1DbSC5Z90A">The God Ask</a> by Steve Shadrach | 36 | 7 | 2019-11-01 04:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: 2019-12-10 date fields found empty 2019-12-11 date fields re-entered manually --pb 2020-12-16 changed Due in # Days from 181& to 167& & Duration from 142& to 128& --pb&
60 | 167 | 166 | Make a list of potential fundraising partners | Brainstorm a list of every possible fundraising support partner including friends, family, churches, and organizations. | Pursue every partnership opportunity possible. God often works through unsuspected relationships. While brainstorming, think about every person you've had a positive relationship with (both past and present): friends family neighbors pre-ministry jobs ministry connections college buddies etc. Don't forget to include your spouse's friends, family and coworkers as well. And really include everybody - don't say no for them by excluding them from your list. | Download Passion for Planting's Fundraising Worksheet Template (<a href="/resources/item/324">MS Excel</a> or <a href="/resources/item/364">Google Sheet</a>). Use it to create an exhaustive list of potential fundraising support partners. This action is complete when the list of potential fundraising support partners is created. |  | 36 | 7 | 2000-01-01 05:00 | 2019-12-10 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content & resource links updated --pb 2018-05-07 added& google& doc template version --pb 2019-12-10 content validated --pb
61 | 174 | 166 | Develop partner expectations | Be prepared to answer the question, "So what do you want?" when you talk to potential partners about any type of support. | Demonstrating preparedness and being able to call people to commit will be powerful tools in your fundraising effort. There are different types of support that you can raise as you start the fundraising effort. For instance, someone on your list may not be able to give financially, but maybe they have an extensive network of friends, colleagues, and acquaintances that might give if he referred and endorsed the you. You'll have different expectations for the different types of donors: individuals churches church planting networks It will be easier for your supporter to buy in if you have provided clear expectations and open communication. Agreeing on expectations in advance gives each party something to hold the other accountable to, and it forms a strong foundation of trust. The greater the commitment (whether in dollars or other resources), the more specific the expectations should be. For example, if a church is giving you $25,000, they may be expecting a seat on your Management Team. Also, having clear expectations for when and how you will receive that donation is crucial for budgeting purposes. There is a huge difference between $1,000 per month for 25 months and one $25,000 check written now. | Write out supporter expectations, answering "who, what when, where, why and how?" Make sure you are asking the right thing from the right person or group. Write out what supporters can expect from you. Put yourself in the shoes of the supporter and ask yourself what you would expect. Optional: put expectations for both sides in a pamphlet or on a commitment card to be able to hand to potential supporters. This action is complete when you have jotted down partner expectations and you're able to explain all of them from memory. |  | 36 | 7 | 2015-02-03 05:00 | 2020-01-24 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated --pb 2018-11-02 content updated --pb 2019-11-19 content updated --pb
62 | 182 | 162 | Coaching Checkpoint: review and affirm Fundraising Strategy | Ensure that the fundraising strategy is both reasonable and realistic. | The Fundraising Strategy needs to be well thought through, both in terms of an amount as well as how the planter is going to go about raising the funds. It needs to contain the following elements: An overall fundraising goal Decisions on which fundraising collateral they'll develop A process to follow to get to "the ask" Thoughts of following up after the ask and maintaining ongoing communication Details on how donors will make their contributions Identify gaps in the planter's strategy and help them think through pitfalls they are likely to encounter based on your experience. | Review the completed fundraising strategy. Provide feedback to the planter. This action is complete when you, the coach, have reviewed and affirmed the planter's Fundraising Strategy. |  | 43 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated --pb 2018-11-02 content updated --pb 2019-11-19 content updated --pb 2020-12-11 changed Due in # Days from 52& to 43& --pb
63 | 1310 | 0 | PHASE II - SETTING DNA | [6 empty] | 2020-11-25 05:00 | 2021-01-15 05:00 | 2000-01-01 05:00 | template:
64 | 290 | 1310 | Milestone: Exegete Your Community | Intently study the community God is calling you to reach in order to uncover Gospel opportunities. | You need to understand your community so that you can contextualize the Gospel and how you will "do church" so that it makes sense to them. The tasks in this milestone will walk you step-by-step through becoming an expert on your community. |  |  | 99 | 84 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-09-26 content validated --pb 2019-11-22 content updated --pb 2020-12-16 changed Due in # Days from 91& to 99& & Duration from 63& to 84& --pb&
65 | 291 | 290 | Read this demographics overview | Understand why it's important to articulate the key distinctives of your community and contextualize the Good News. | The language you use, the stories you tell, and the metaphors you employ won't work in every context. For instance: Sharing stories about your hunting escapades to an anti-gun crowd Wearing a suit and tie to church in Hawaii Saying y'all just about anywhere in New England Talking Yankee-fast and bypassing conversational pleasantries in the South Having a cookout anywhere west of the Rockies Hosting a BBQ anywhere east of the Rockies but serving only hot dogs More than that, you need to understand what really makes the locals tick. What's their worldview? What are their idols? And where do you find elements of the Gospel already woven into the community? Learning your culture and your context is one of the primary jobs in the early days of the church plant. Demographics are a great starting point, especially when when you follow them up with personal investigation and experience. | Watch the Passion for Planting training video "<a href="../../../resources/item/271">Understand Your Focus Group</a>" featuring Ed Stetzer. This task is complete when you've read the description and listened to the training resources above. |  | 30 | 1 | 2000-01-01 05:00 | 2024-07-09 17:37 | 2000-01-01 05:00 | template: standard Valid once videos are transferred over.& ----ds 2017-09-26 content updated --pb 2019-09-03 additional resources subsection added --pb 2020-12-11 changed Due in # Days from 56& to 30 & Duration from 7 to 1 --pb 2019-11-22 content updated --pb 2021-01-28 took out& Additional Resource article Why Contextualization Trumps& Methodology In Church Planting because the link was broken and I couldn't find it& elsewhere --sc 2022-11-21 updated links --sc
66 | 292 | 290 | Call your coach about exegeting your community | Open a conversation with your coach about doing the missionary homework required to exegete your community. | Making disciple-makers has the power to break through every social, racial and economic barrier. You need to quickly learn how to present the Gospel in a contextual way, one that makes sense to the people in your community. Sample issues to process with your coach: The fastest way to understand your community How to discover the community's top needs Describing the average family living in your community Differentiating this new church from other healthy churches and church plants in the community Cross-cultural discomfort and apprehension | This action is complete when you have called your coach about exegeting your community. |  | 36 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-30 content updated, audience changed to coach --pb 2019-11-22 content updated --pb 2020-12-11 changed Due in # Days from 56& to 36& --pb
67 | 293 | 290 | Define your target area | Maximize your impact by drawing a boundary line around the geography where you will concentrate your evangelism and your outreach, community service & marketing resources. | You don't have unlimited resources. As much as you'd like to do everything and serve everyone, you won't have enough money and manpower to do it. At this point, you've already identified your approximate geographic area. You know which city, metro area or region you'll be planting in. But even that geography is too broad to reach everyone. So you'll have to make some tough choices. It's better to focus your resources like a laser than to spread yourself thin like a shotgun spray. Defining your target area is a back-and-forth process of refining your understanding about: the people group God has called and equipped you to reach (average target family) where they live (geography) where there are available facilities for worship gatherings You will want to refine your target area in parallel with crafting your Target Area Report (see subsequent PlanterPlan action). As you learn more about your adopted people group(s), you will have a better understanding of where they live. As you learn more about your community, you will have a better understanding of where your people group is concentrated. Plot out the things you're learning either on a large paper map or an online digital map. Pray that the Spirit would reveal common patterns and connections that make it clear which side of town or specific geography to focus your initial efforts on. When you're done with this action, you'll have a literal boundary drawn on a literal map. It will be the area where you'll commit to focus your time, talent & treasure in the early years of the church. That's not to say that you can't ever do anything outside of the target area, given compelling circumstances. But your default will be reaching the people group God has called you to within that geography. However, all the demographics in the world are meaningless without God's calling. God's leading should not be put aside for better demographics. The demographics are a great indicator of your potential impact, but ultimately if God is leading you to a different area, you must follow His will. Bathed this entire process in prayer. | Review all the data you've collected & validated to this point. Get counsel from your coach and others that are familiar with your situation. Seek God's will for whom you are to target. Draw a literal boundary on a map defining where you will target your resources. This action is complete when you understand your target area well enough to draw a line on a map surrounding it. |  | 78 | 14 | 2015-02-03 05:00 | 2019-11-22 05:00 | 2000-01-01 05:00 | template: standard 2017-10-23 content updated --pb 2019-11-22 content updated --pb
68 | 294 | 290 | Craft a Target Area Report | Produce a summary report documenting your demographic findings and cultural exegesis. | To get a full picture of your target area and average target family, you must answer the following questions: Who lives there? What is their worldview? What hobbies, personal preferences and values do they have? And what are both the felt needs and real needs? What is important locally (e.g. golf, aviation history, etc)? What history, heritage and other local factors shape this (e.g. location of the annual Master's Golf Tournament, home town of the Wright Brother's, etc)? What are the 'hot topics' that either divide or unify people there? Where and how is the city planning to grow? How many dwellings are in the geography? What are the commuting and major traffic patterns? Where are the major commercial and retail stores locating to? What other churches are in the area? Any other new churches starting? Location? Reputation? What real and felt needs are they trying to meet? How effectively? Style? Niche? What is the media writing about the area? Which businesses are influencers in the region? How are the neighborhoods different? What is the spiritual temperature? You'll work through these questions in the subsequent subtasks here in PlanterPlan. After completing each of the subtasks, compile the results into a written Target Area Report. This biography of your community will be used in formulating your church's Vision Frame (subsequent Milestone in PlanterPlan). Also pull in information learned through the community needs assessment (covered in the Networking milestone here in PlanterPlan). | Download Passion for Planting's Target Area Report Worksheet (<a href="/resources/item/345">MS Word</a> or <a href="/resources/item/380">Google Doc</a>). Work through each of this task's subtasks. Compile and summarize your results. Send your completed Target Area Report to your coach for feedback. This action is complete when you have written a descriptive Target Area Report. |  | 92 | 77 | 2000-01-01 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-10-23 task updated --pb 2017-10-23 title changed --pb 2018-06-01& gdoc& template added --pb 2019-11-22 content updated --pb 2020-12-11 changed Duration from 45& to 77& --pb
69 | 296 | 294 | Get several demographic report(s) | Collect demographic information to do your missionary homework and become an expert on both your community and the people God is calling you to reach there. | As you read these reports, ask the Holy Spirit to identify important variables (ages, incomes, single parents, race, etc.). There will be so many to choose from, it could get overwhelming. Read the reports with intentionality and allow for surprise inspiration. Paid Demographic Reports America's Big Data now tracks virtually everything about each household's spending habits. They cross reference that against US Census data and other sources to know a startling amount about us. The paid reports below will contain both hard demographics (age, income, race) and soft demographics (for example: how 'green' they are, how tech-savvy they are, their preferred brands, etc.). These vendors specialize in providing demographics to churches: Percept's <a href="https://www.ministryarea.com/">Ministry Area & First View Reports</a> MissionInsite's <a href="https://www.acstechnologies.com/missioninsite/tools/surveys-reports/">Demographic Surveys & Reports</a> and <a href="https://www.acstechnologies.com/missioninsite/solutions/local-churches/">Radius Reports</a> Barna's <a href="https://access.barna.com/faithview/#options">FaithView</a> database of spiritual profiles of Americans Free Demographic Reports Though sometimes you get what you pay for, these sites still offer a surprising amount of information that will help you understand your community better. Hard Demographics: Passion for Planting's <a href="https://church-planting.net/free-demographic-report/">Free Demographics Report</a> Data USA's <a href="https://datausa.io">Community Profiles</a> <a href="https://data.census.gov/cedsci/profile?g=0100000US">US Census Bureau</a> City-Data <a href="https://www.city-data.com/">Demographic Reports</a> US Small Business Administration's <a href="https://www.sba.gov/business-guide/plan-your-business/market-research-competitive-analysis">various demographic reports</a> Soft Demographics: Experian's <a href="https://www.segmentationportal.com/mosaic7/">Mosaic&reg; segmentation portal</a> Maps: Data USA's <a href="https://datausa.io/map">Demographics Maps</a> Barna's <a href="https://www.barna.com/research/2017-bible-minded-cities/">2017 Most Bible-Minded Cities</a> Barna's <a href="https://www.barna.com/research/post-christian-cities-2019/">2019 Most Post-Christian Cities</a> US Census Bureau's <a href="https://www.census.gov/quickfacts/fact/map/washingtoncitydistrictofcolumbia,US/PST045221">QuickFacts Maps</a> MelissaData's <a href="https://www.melissa.com/v2/lookups/mapzip/zipcode/">Zip Code Maps</a> and <a href="https://www.melissa.com/v2/lookups/mapcart/zipcode/">USPS Carrier Maps</a> Theographics: Pew Research Center's <a href="https://www.pewresearch.org/religion/religious-landscape-study/">Religious Landscape Study</a> ARDA's <a href="https://www.thearda.com/data-archive/browse-categories">various US Surveys</a> Wikipedia's data-packed article on <a href="https://en.wikipedia.org/wiki/Religion_in_the_United_States#ARIS_findings">Religions in the United States</a> Hartford Institute for Religion Research's <a href="http://hirr.hartsem.edu/">various theographic reports</a> Pew Research Center's <a href="https://www.pewresearch.org/fact-tank/2016/02/29/how-religious-is-your-state/?state=alabama">How Religious Is Your State?</a> Specialty: MelissaData's <a href="https://www.melissa.com/v2/lookups/mapschool/name/">School District Maps</a> and <a href="https://www.melissa.com/v2/lookups/school/name/">Public Schools Lookup</a> (reaching families with kids?) GreatSchools' <a href="https://www.greatschools.org/">Demographics by School</a> Corroborate the Data Statisticians in offices on the other side of the county can only get so much right. You need to test the data against the real world. Network in the Community: Come to local leaders and influencers with the posture of a student and be genuinely interested in learning about the history, strengths & weaknesses of your community. Use Passion for Planting's Networking Strategy Template (<a href="/resources/item/182">MS Word</a> or <a href="/resources/item/358">Google Doc</a>) to craft an approach to meeting the most strategic people in your community. Psychographics: People are funny. There are factors that won't show up on any demographics reports. These become important when narrowing your target area, and specifically in the location of your facility. Consider: Which way do people "face" in their attitudes and affinities? It is often toward the biggest city in the region - they work & shop in that direction and rarely venture in the opposite direction What boundaries won't they cross? Things like rivers, railroads and interstate freeways can be boundaries, but sometimes it's an invisible line marking a certain neighborhood | Pull various demographic report(s). Review the data to spot trends and insight into the people living within the area. Summarize your findings in your Target Area Report Template (<a href="/resources/item/345">MS Word</a> or <a href="/resources/item/380">Google Doc</a>). Be prepared to summarize the data for the Average Target Family exercise (a subsequent PlanterPlan task). This action is complete when you have reviewed the demographic reports. |  | 29 | 14 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-09-14 content completely overhauled based on free download "Demographic Information for Your Church Plant" --pb 2017-09-14 all hyperlinks verified --pb 2018-05-07 added google doc template version --pb 2019-11-15 links verified & content updated --pb 2020-12-11 changed Due in # Days from 42& to 29& --pb 2020-08-17 links updated --pb 2022-11-21 updated links --sc
70 | 298 | 294 | Research local community information and history | Understand how your community's history and heritage shapes its values. | To really say you know your area, you need to understand: What are the values of a specific geographic area? What history, heritage, and other local factors shape these values? Are there any 'hot topics' that either divide or unify the people living in the area? What is the predominant worldview? Discover and understand social forces shaping your community. This is your chance to do an old fashioned essay/book report. You'll go through a data-gathering phase and a report phase. To collect data, consider doing the following: Find community history and links to local government, businesses, media etc. Most cities & towns have some history documented on <a href="https://en.wikipedia.org/">wikipedia.org</a> Contact the local Chamber of Commerce. Obtain any information they have available. Ask if any local books or literature have been written about the area. Many communities have historians. Ask around and contact him/her to request an interview. Check the county/city web site. Often they have a history section. Contact the local library and ask if they are aware of any local history books or resources. Find long-term residents in the area and interview them. Seek them out - they are a wealth of information. After gathering the data/information, turn your findings/conclusions into a written biography of the local area. Consider turning this action into a family action. Have members of your immediate family help with the research and writing. | Make a list of sources to pursue and get go after them. Summarize the history and heritage of the local area in your Target Area Report . Include a discussion of how this history shapes the community and whether there are any 'hot topics' rooted in this history that affect the community today. This action is complete when you have included your findings in your Target Area Report . |  | 29 | 14 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-10-24 content validated --pb 2019-11-25 content updated --pb 2020-12-11 changed Due in # Days from 42& to 29& --pb
71 | 303 | 294 | Subscribe to local newspaper, blogs and user groups | Sign up for local news & content to become an expert on what is happening in your community and what social forces are shaping it. | Become a ongoing student of your community. There are some simple ways to do this regularly: Read the local newspaper (or community section of a larger paper) religiously. Even better, also get to know the editor and/or any reporter who covers community events. Subscribe to your newspaper's blog or online version Subscribe to the blog of the self-proclaimed expert on your community (there's usually somebody) Get on <a href="https://nextdoor.com/">www.nextdoor.com</a> Join <a href="https://www.facebook.com/groups/explore/">Facebook user groups</a> about your community Follow community groups on <a href="https://www.tumblr.com">www.tumblr.com</a> Whenever possible, sign up for push notifications so that you remember to stay current by at least skimming their updates. | Subscribe to at least one of the local resources described above. This action is complete when you have subscribed to local news and updates. |  | 36 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-10-24 content udpated --pb 2019-11-25 content updated --pb 2020-12-11 changed Due in # Days from 42& to 36& --pb
72 | 299 | 294 | Get copies of community growth and land use studies | Research where recent growth has occurred in your community and where new growth is planned. | Your community is headed somewhere. Growth doesn't just 'happen'. Someone has been planning for years, conducting studies, issuing reports and proposing plans. Cities and/or counties create and maintain a Comprehensive Plan (also called a General Plan , Land Use Study or Master Plan ). This study shows the long-range plan for development of your area. They show future roads, schools, developments, malls, industry, etc. It will answer questions like: What does the local county/city Comprehensive Plan show are the key growth areas over the coming years? Where has the most growth occurred during the past 5-10 years? Where is the most growth expected to occur over the coming years? Are there any special projects that will affect traffic patterns or growth projections (e.g. new Town Center, etc)? | Do an internet search on "[name of my city] comprehensive plan". Alternately, search using its synonyms (above) and/or the name of your county. Review the land use plans for your area, noting where recent growth has been and where projected growth will be. This action is complete when you have obtained the studies and reviewed them. |  | 43 | 14 | 2015-02-03 05:00 | 2019-11-25 05:00 | 2000-01-01 05:00 | template: standard 2017-10-24 content validated --pb &
73 | 300 | 294 | Get initial carrier route maps / information | Discover how many "front doors" (dwellings) are within your target area. | What are carrier route maps? A carrier route is the group of addresses to which an individual postal carrier (mailman) delivers mail. There are usually multiple carrier routes (and therefore mail carriers) in a ZIP code. They will show you how many residences (both single- and multi-family dwellings) are in your target area. Why are carrier route maps important? It's for more than just mail. Carrier route maps offer several benefits: Budgeting for outreach and marketing. You can make better plans if your know how many front doors are in your target area. You'll know, for example: how many event invitations you'll need to print how many door hangers you'll need to order what it costs to send a postcard to every home Discovering natural geographic boundaries. Carrier routes are often broken down by natural geographic boundaries (e.g. subdivisions, roads, rivers, interstates, etc). These are the same barriers that many people are hesitant (or unable) to cross to attend church. Concentrating outreach events. Carrier routes are a great tool to help define the boundaries for outreach. You don't have unlimited resources, so participating in or hosting events in the same area you'll eventually market to will help you maximize both. Getting lowest postage rates . To get the lowest postage rates, you have to put a postcard in every mailbox on a carrier's route (a saturation mailing ), but you don't have to hit an entire zip code. Knowing the routes in your area will help you define a tight strategic area for your marketing. How do I get carrier route maps? <a href="https://www.melissa.com/v2/lookups/cartzip/zipcode/">Melissa Data</a> offers free carrier route information at their site. They also provide a map of each route. Or you can work with a direct mail vendor that specializes in serving churches (there are several). This is a great way to do an initial interview to see if you'd want to work with them later on marketing. | Identify the most important information of interest. Use one of the means above to get carrier route information and maps. Review the reports and strategize your target area. This action is complete when you have received and reviewed carrier route maps for your target area. |  | 50 | 14 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-10-24 content & links validated --pb 2019-11-25 content updated --pb 2020-12-11 changed Due in # Days from 42& to 50& --pb 2022-11-21 updated link --sc
74 | 301 | 294 | Research commuting and major traffic patterns | Investigate factors that influence which direction(s) people are likely to drive to a worship gathering. | Simply targeting people in a 5 mile radius around your worship facility does not take into consideration barriers that may exist that hinder people from traveling to your worship gatherings. You have to understand these commuting and traffic patterns when considering where to hold your worship gatherings, as well as where to do your outreach. People in your target community have commuting habits and preferences. There are both physical and psychological barriers that keep people traveling to certain areas within a geographic area. Psychological Barriers: Familiarity: What is their normal commuting pattern to work, stores, the movie theatre, etc? Often the direction people commute to work is the same direction they'll go to do their shopping and recreation. Traffic/Congestion: People often avoid certain roads and parts of town simply because of the traffic. Distance: People will only travel so far to a destination place (e.g. church, movie, store). Crime, Safety & Cleanliness: What reputation does a given area have? Do people feel safe there? Physical Barriers: Bridges Lakes/rivers Train tracks Parks Interstate highways/Toll roads Divided highways Understanding existing commuting habits and traffic patterns will help you define the best: Worship gathering facility options Office locations Outreach event locations Placement of street signage Facilities that are located along major commuting routes and near high population density centers are often the best worship gathering locations. Useful tools to help: <a href="https://datausa.io/">DataUSA</a> demographics include average commute statistics for your community <a href="https://www.freemaptools.com/how-far-can-i-travel.htm">FreeMapTools</a> will show you a drive time map around a potential facility | Use a map to: Identify the key destination locations (e.g. shopping centers, movie theatres, etc) in a given geographic area. Identify major commuting routes in the geographic area. Identify key population centers (place circles on the map) ranking them from highest population density (households per square mile) to lowest population density. Identify any natural physical barriers (lakes, bridges, train tracks, etc). This action is complete when you understand and can articulate the commuting patterns of your community. |  | 70 | 14 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-10-24 data validated & new links added --pb 2019-11-25 content updated --pb 2020-12-11 changed Due in # Days from 90& to 70& --pb
75 | 306 | 294 | Learn where the major neighborhoods are and what makes them different | Create a list or map of neighborhoods to understand your community and better plan events. | Most cities are made up of neighborhoods - boroughs, builder's subdivisions, etc. Each neighborhood will have different characteristics. For instance, real estate prices alone will significantly influence the community makeup. Some neighborhoods will have very active home owners' associations that regularly plan events for the community. Maybe that gives the neighborhood a more friendly feel. Other neighborhoods may feel very aloof. In addition to creating a map, take some basic notes on each neighborhood such as: Its reputation in the area Average price of homes Regular community events <a href="https://www.greatschools.org/school-district-boundaries-map/">Schools</a> (their quality/caliber) Knowing your neighborhoods well helps with: Discovering concentrations of your average target family Strategizing your events Strategizing marketing efforts Bringing new staff up to speed quickly Real estate agents are a wealth of information when it comes to learning about the key distinctives of each neighborhood. | Purchase a poster-sized map of your city, or create a <a href="https://www.churchplantingtactics.com/church-plant-target-area-map/">custom Google map</a> for online collaboration. Draw a polygon around the boundaries of each neighborhood. Write in the name of the neighborhood. Note the key distinctives for each neighborhood. This action is complete when you have a completed map of each neighborhood in your target area with key distinctives noted. |  | 70 | 14 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-10-24 content updated --pb 2019-11-25 content updated --pb 2020-12-11 changed Due in # Days from 77& to 70& --pb
76 | 307 | 294 | Conduct a prayer walk | Perceive the spiritual dynamics of your community through on-site prayer. | The last level of demographics you need to understand in your community is its spiritual dynamic. Church planting is a spiritual undertaking, after all, and going in blind to the spiritual forces at work could spell disaster. Walking through your community and listening to the Spirit will give you spiritual insight that no demographics company can provide. Praying through the various neighborhoods and interceding for people will help you gain God's heart for your community. | Using the map you've developed, plan a route for a prayer walk. Put on a pair of good shoes and go walking. Spend time listening to what the Spirit has to say. Spend time praying for the people that you are passing by. Journal or record your thoughts and impressions as soon as you are done. This action is complete when you have recorded the results of your prayer walk. |  | 77 | 21 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-10-24 content validated --pb 2019-11-25 content updated --pb 2020-12-11 changed Duration from 7& to 21& --pb
77 | 302 | 294 | Research other churches in the area | Investigate existing churches in your community and whether any other new churches are about to be launched. | Every congregation has its own personality, and every church will reach different types of people. You need to know the personalities of nearby churches and be able to articulate how God is uniquely crafting your congregation's personality. Networking with other churches will usually reveal: opportunities for Kingdom collaboration on community service projects facilities that may be available and new friends in ministry. Set up a meeting with each Senior Pastor to establish a relationship, discover who they're reaching, and share your vision/plans for reaching the lost in the area. This exercise is also a great initial test of which churches show up on the first page of search engine results. Search online and make a list of churches in your area. In most cases, you can get a good sense of who the churches are reaching by visiting their websites. Getting to know other church planters in the area will also be invaluable in coordinating launch timing, facilities, community service events, etc. | Make a list of all the large and/or active churches in your target area. Obtain contact information at each church (name of Senior Pastor and phone number). For each church on the list, identify the following: Whom are they targeting (via advertising, programs, etc.)? Who are they reaching (as measured by who attends)? What unique/special programs are offered to reach their target? What music style and culture does the church have? Write a short summary of the people groups already being reached in your community and how they're being reached. Now write a short list of the people groups that are not being reached. This action is complete when you've included the summaries described above in your Target Area Report . |  | 86 | 30 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-10-24 content updated --pb 2019-11-25 content updated --pb 2020-12-11 changed Due in # Days from 90& to 86& --pb
78 | 309 | 294 | Define your Average Target Family | Develop a profile of the average family in your target area to articulate your understanding of the people you are beginning to reach. | You have to have a clear understanding of who lives in the target area or you're not going to be able to reach them well. There are 3 key things to keep in mind: The makeup of the community is what it is. You can't change it; you must understand it. The previous series of actions leading up to this got you to really learn who lives in the area. You tend to reach those most like yourself. Understand and candidly consider who you will most naturally reach. Consider how you compare with the average person living in the area. Discern whether you will be targeting a subculture within the culture. Plant the church your community needs. Is the church you've been envisioning the kind you like , or will it fit the people who live in your area? When a missionary is sent overseas, one of the first expectations is that they learn the language and culture of those they will be reaching. In the same way, you have to understand the language and culture of those you are reaching. People in urban situations are different than those in rural. Those in California have a different culture than those in the South. You need to understand what makes your target unique and how you can best reach them. After getting some demographic data and proving it out with your own research, define as specifically as possible the characteristics of the 'average' family in your target area. Write a description of the typical person and/or family you are beginning to reach. This process will help you better understand how to reach your community. What is an 'average target family'? A qualitative description of the average family you are trying to reach in specific terms. The description should be as detailed as possible, including age, marital status, family size, income, hobbies, likes/dislikes, employment, etc. Why is defining an average target family important? With a clear understanding and description of the average family, you'll be able to focus on how best to reach the people in your community. Marketing, outreach, music, staffing, and a host of other strategies will be shaped by the definition of who you are trying to reach. With your new-found focus, you'll be able to allocate resources based on which opportunities/strategies will be most effective. Of course you're not going to close the door on people that don't match up with your Average Target Family! But understanding who the target really is will allow you to better form effective strategies. | Review all the data you've compiled so far about your target area. Seek counsel from trusted people who live in the target area. Download Passion for Planting's Average Target Family Worksheet (<a href="/resources/item/11">MS Word</a> or <a href="/resources/item/379">Google Doc</a>). Fill in the blanks to describe your own Average Target Family. This action is complete you have written out a concise description of your average target family. | <a title="Sample Average Target Family Document" href="/resources/item/10">Sample Average Target Family</a> from Passion for Planting | 92 | 21 | 2000-01-01 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-10-26 content updated --pb 2018-06-01 additional resources subsection added,& gdoc& template added --pb 2019-11-25 content updated --pb 2020-12-11 changed Duration from 7& to 21& --pb
79 | 311 | 290 | Coaching Checkpoint: review and affirm demographic findings | Ensure that both the planter's Target Area Report and Average Target Family documents are thorough and actionable. | The Target Area Report should include hard demographics, soft demographics, and the results of surveys and personal interactions in the community. The Average Target Family can be narrative or bullet points, but it needs to be thorough enough to get inside their heads and hearts. After you, the Coach, have reviewed the planter's Community Profile and Average Target Family documents, provide the planter with feedback. Challenge the planter to do more research, and/or confirm that the planter is a good match to reach that specific target. | Reviews the planter's Target Area Report and Average Target Family documents. Provide feedback to the planter as appropriate. This action is complete when you, the coach, have reviewed and affirmed the planter's Target Area Report and Average Target Family documents. |  | 99 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2019-11-25 content updated --pb 2020-12-11 changed Due in # Days from 97& to 99& --pb
80 | 1388 | 290 | Describe the gospel in your context | Define how the good news of Jesus changes everything in your context. | The gospel of Jesus never changes, even though it can be defined in many different ways. Simply put the gospel is the good news that Jesus has bridged the gap between God and man. However, good news is only good news because of bad news. The bad news is sin not only resulted in separation between man and God, it's also led to a breakdown in every other relationship in the world. Since sin, the bad news, is felt all throughout our world, so too must the gospel. It ought to saturate every crack and crevice of our broken world as well. The role of a church planter is to communicate the gospel in a way that it becomes good news in their life and transforms them. Since sin has infected every human heart and has also spilled over to infect entire communities and cultures your goal as a church planter is just to preach good sermons, baptize people, and send them out with the reassurance that their sins have been forgiven. You get to invite your people to partner with God as he restores all things through Jesus. For instance, if your community is segregated and divided by racial tension, your church can take the gospel to the community by working to heal these divisions, so the community experiences the reconciling power of God's grace. If half of your community is addicted to heroin, the gospel your church can offer the community should speak to freedom from drug addiction. If half of your community is divorced, your church can help people find healing and train people to love each other like Christ loves his bride. The gospel is not just Jesus died on the cross from your sins, so you can go to heaven someday. The gospel brings heaven to earth. For this to happen it must be contextualized to penetrate the darkness starting in people's hearts and spilling over into their community. | Read <a href="https://gccollective.org/article/relevance-is-not-the-primary-goal-of-contextualization/">Relevance Is Not The Goal of Contextualization</a> by Brian White After studying your community think about what aspects of your community don't reflect the Kingdom of God. What's broken in your community that the gospel of Jesus can fix (marriages; poverty; homelessness; racism; drug addiction; promiscuity; etc.)? Write out (either in a list or a paragraph) how you see the gospel mending what's broken and offering your community hope. This action is complete once you have written out that description of the gospel's ramifications in your context. |  | 99 | 7 | 2021-01-15 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template:
81 | 157 | 1310 | Milestone: Set Opening Day Expectations | Dream about what the Opening Day of worship gatherings will look like and discover how that will both benefit your leadership and propel the launch team toward a successful launch or regular worship gatherings. | A clear understanding of what the worship gathering will be like on Opening Day enables you to stay focused on what needs to be done during the pre-launch phase. The vision for the future (what Opening Day looks like) will shape our actions today. This milestone will take you through the exercises of envisioning what Opening Day looks like, assessing where the launch team is currently, and making specific goals for how to get from Point A to Point B. |  |  | 46 | 25 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-06-01 content validated --pb 2018-11-02 content updated --pb 2019-12-17 content updated --pb 2020-12-16 changed Due in # Days from 45& to 42& & Duration from 24& to 21& --pb&
82 | 1285 | 157 | Read this Opening Day Expectations overview | Understand why it's important to have the end in mind and set expectations for the Opening Day of worship gatherings. | You already have a vision for what the first worship gathering will be like. Whether near or far, that's the "Opening Day" (aka "Launch") of your worship gatherings. It's the picture on the puzzle box that helps everyone put the pieces in the right order to complete the puzzle. It's not really the opening day of the new church itself ; you should have other elements of what it means to be a church in place well before you start worship gatherings. In that sense, you've already "opened". Elements/Activities of the Early Church from Acts 2:41-47 repenting & believing, baptizing, making disciples, leadership (implied) teaching, fellowship, breaking of bread, prayer common awe, signs & wonders by leadership, worship (implied) love & fellowship sharing financial resources corporate worship, meeting in homes, sharing meals favor in the community, making disciples The Opening Day for the tasks in the Milestone refers to the start of worship gatherings . The Opening Day Expectations document will walk you through the process of getting the visions and dreams out of your imagination and onto paper. If you don't have a clear description of Opening Day , it's like giving your team a bag of 1,000 puzzle pieces but no box lid for them to know what the assembled puzzle should look like. The document helps you get everyone on your Launch Team on the same page. Because here are the 2 kinds of people that will be joining your Launch Team: people with no church background that have little a frame of reference for worship gatherings churched and de-churched people that come with their own preconceived notions about what worship gatherings should look like Get everyone shooting at the same target and pulling in the same direction by giving them the puzzle box cover for Opening Day of worship gatherings. | Read the content above. Watch the Passion for Planting training video <a href="/resources/item/82">Opening Day Expectations</a> featuring Ed Stetzer. Commit to writing down your expectations for the Opening Day of worship gatherings. This action is complete when you have read the content of this overview. |  | 22 | 1 | 2019-10-14 04:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: 2020-12-11 changed Due in # Days from 28& to 22 & Duration from 7 to 1 --pb
83 | 158 | 157 | Call your coach about Opening Day Expectations | Open a conversation with your coach about your expectations for Opening Day of worship gatherings. | Imagining and quantifying what the opening day of worship gatherings looks like will be critical to your ability to communicate about it and inspire others. If you don't know where you're going, any old road will do. Sample issues to process with your coach: Ways of 'doing church' that will alienate people in your community How to deconstruct elements of a church service in order to translate them into the local context Realistic numeric expectations How each element connects with the target audience | This action is complete when you have called your coach about your Opening Day Expectations. |  | 28 | 7 | 2015-02-03 05:00 | 2020-01-06 05:00 | 2000-01-01 05:00 | template: standard 2017-05-30 content updated, audience changed to coach --pb 2019-12-16 content updated --pb&
84 | 160 | 157 | Craft your Opening Day Expectations | Clarify vision and focus your teams by writing down dreams and expectations for the Opening Day of worship gatherings. | Having a clear understanding of what the worship gathering will be like on Opening Day enables you to stay focused on what needs to be done during the pre-launch phase. The vision of that preferred future (what Opening Day of worship gatherings looks like) will shape your actions today by pointing you at the right target. There are many different approaches and philosophies to planning. No matter which approach you use, planning is simply a means to an end. Planning lays out what has to be done to get from where you are today to where you want to be in the future. No matter what planning approach you use, the basic steps include: Define a clear picture of a preferable future (Opening Day of worship gatherings) Vision is all about painting a picture of a preferable future, and then moving deliberately forward in pursuit of that vision. The preliminary launch plan starts with this end in mind: "We believe God's vision for the Opening Day of worship gathering looks like [fill in the blank]." By defining a picture of the future, you can then name the specific actions to move in that direction. Understand where we are today Before you can put a plan together for moving to where God wants to be in the future, you have to be sober about where you are today. This second step of planning leads you through the process of understanding where you are. For planters, the starting point is typically to a blank canvas, starting from scratch. A big help in understanding where you are today is having gone through a planter assessment process. Plan of action for moving from where you are today to where you want to be After describing a clear vision for the future and assessing where you are today, the final step in planning is identifying steps to get you where you want to be. Consider the process of building a new house. The first step is to draw up blueprints. What do you want the finished product to look like? Developing a clear picture of the new house influences every aspect of turning the vision into reality. It affects your choice of builder, lot, how long it will take to construct, and the cost. You just can't develop a good plan without a clear vision of the end. The picture does not need to be perfect. Just get it roughly right based on what you sense God is leading your church to be. The Opening Day Expectations Template (below) helps you work through specific aspects of the Sunday morning gathering. The template identifies over 50 characteristics of a Sunday morning experience for you to consider. This helps you write out a description with specific/concrete expectations for what the church will look like on the Opening Day of worship gatherings. NOTE: This description of Opening Day is not the final product. The church may end up looking different than this first draft. This task simply gets you thinking through Opening Day and setting an initial target. | Download Passion for Planting's Opening Day Expectations Template (<a href="/resources/item/197">MS Word</a> or <a href="/resources/item/374">Google Doc</a>). Answer each question as a guided daydream about what your Opening Day of worship gatherings will be like. Send the completed template to your coach for feedback. Present the completed template to your Management Team to make sure everyone is on the same page. This action is complete after you fill out the template to produce a written description of the opening day of worship gatherings. | <a href="/resources/item/196">Sample Opening Day Expectations</a> from Passion for Planting | 35 | 7 | 2000-01-01 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-06-01 content & resource links updated --pb 2018-06-01 additional resources subsection added,& gdoc& template added --pb 2019-12-16 content updated --pb 2020-06-21 content updated --pb 2020-12-11 changed Due in # Days from 45& to 35& --pb
85 | 161 | 157 | Coaching Checkpoint: review and affirm Opening Day Expectations | Ensure that the planter has clearly defined expectations for both Opening Day of worship gatherings and the period immediately following. | The planter's Opening Day expectations need to be well thought through and frequently communicated. The planter should also have a plan for how to prepare the launch team for the challenges and opportunities of both the launch of worship gatherings and post-launch Milestones . | Review the written Opening Day Expectations. Provide feedback to the planter. This action is complete when you, the coach, have reviewed and affirmed the planter's Opening Day expectations. |  | 42 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-06-01 content validated --pb 2018-11-02 content updated --pb 2019-12-16 content updated --pb 2020-12-11 changed Due in # Days from 52& to 42& --pb
86 | 1136 | 1310 | Milestone: Publish Your Launch Strategy | Publish a printed Launch Strategy document that will help you with fundraising, networking and Launch Team recruitment. | At some point, your visionary ideas will need to be implemented, or they will remain wishful thinking. The first step in the implementation process is writing things down. Creating a Launch Strategy document is exactly that. The tasks in this Milestone will help you: Open a conversation with your coach about crafting a Launch Strategy Hammer out the various building blocks of a Launch Strategy and compile it into a single, useful document Get your coach's feedback on the Launch Strategy |  |  | 135 | 113 | 2017-09-01 04:00 | 2019-10-14 04:00 | 2000-01-01 05:00 | template: New Milestone 2018-04-20 updated content, changed audience to planter --pb 2019-12-03 content updated --pb
87 | 1279 | 1136 | Read this Launch Strategy overview | Understand what a Launch Strategy document is and how it helps you. | The Launch Strategy document is something like a business plan or battle strategy. The process and discipline of creating this document will spark new ideas and reveal flawed assumptions. The document itself can be used to raise major funds from savvy donors who want to know that you've done your homework. And it will crystallize your thinking about various aspects of the church plant. It is like a Launch Vision booklet, but is more detailed with less color and fewer images. It's typically a 12+ page description of how you're going to plant the church, an initial manifesto of why and how you'll go about it. We'll give you a template to make the task easier. Will everything turn out exactly as you've strategized? No, but, "In preparing for battle, I have always found that plans are useless, but planning is indispensable." -Dwight D. Eisenhower, US President & planner of the D-Day Invasion of Normandy | Subsequent PlanterPlan tasks will walk you step-by-step through the process of creating your Launch Strategy document. Read the description above. Review sample Launch Strategies from other church planters. This action is complete once you've read the brief description and reviewed at least 1 sample Launch Strategy. |  | 29 | 1 | 2019-10-14 04:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: 2020-12-16 changed Due in # Days from 35& to 51& & Duration from 28& to 37& --pb&
88 | 1137 | 1136 | Call your coach about crafting a Launch Strategy | Open a conversation with your coach about creating a Launch Strategy document. | The Launch Strategy document is like a business proposal, the kind of thing you would take to the Shark Tank to pitch venture capitalists on investing in a new business. You need to have a strategy that is concrete enough to execute. Creating a Launch Strategy document disciplines you to make important decisions and choose language to communicate your strategy. It's going to be a lot of work. Sample issues to process with your coach: Hidden obstacles that will stall completion How the coach used his/her Launch Strategy document in practical ways What not to include or say in the Launch Strategy How much time to commit to creating a Launch Strategy | This action is complete when you have called your coach about crafting a Launch Strategy document. |  | 36 | 7 | 2017-09-05 04:00 | 2019-12-03 05:00 | 2000-01-01 05:00 | template: New Milestone 2018-05-07 added& google& doc template version --pb 2019-12-03 content validated --pb
89 | 1138 | 1136 | Craft a Launch Strategy document | Create a detailed document that lays out the various strategies that will be used to launch the new church. | A Launch Strategy document will be a 12+ page detailed description of your approach to planting the new church. The document itself may prove very helpful in the fundraising process, but the exercise of working through each item below will better prepare you to actually plant the church. The Launch Strategy contains the following sections: Vision, mission & values Target area Opening Day expectations Timeline Budget Key strategies PlanterPlan will walk you through crafting each of these sections. | Download Passion for Planting's Launch Strategy Template (<a href="/resources/item/144">MS Word</a> or <a href="/resources/item/365">Google Doc</a>). Work through each of the sub-tasks in PlanterPlan, filling in the corresponding section of the template as you go. Send the document to your coach for review & feedback. This action is complete when you have sent your Launch Strategy to your coach. |  | 63 | 21 | 2000-01-01 05:00 | 2019-12-03 05:00 | 2000-01-01 05:00 | template: New Milestone 2018-01-15 changed to child task of #1138 --pb 2019-02-12 changed "philosophy of ministry document" to "vision frame" --pb 2019-12-03 content updated --pb
90 | 181 | 1138 | Set intended launch date | Select a target launch date for your worship gatherings so you can set expectations for supporters, team members and the community at large. | Setting a date for the launch of regular worship gatherings will help you lots of ways. Most of the strategies and actions in your Launch Strategy document are dependent on the launch date. You'll need to know at least 6 months in advance just so you can take care of the basic details like facility & equipment. If it's really early in the planning process, you might choose to set a tentative date and then finalize the date at a later time. That's fine as long as you consistently communicate clear expectations to your launch team. Launch team members can get frustrated when they don't know when the new worship gatherings will officially begin. Defining a launch date (the date of the first public worship gatherings) is important for several reasons: Launch team morale People are inspired by a clear and compelling vision of the future. A launch date brings clarity to the launch process and helps people see that milestone in the future. Launch team members look forward to launch and are anxious to 'become a real church'. After all, the purpose of a launch team is to launch. You must constantly cast vision for what Launch Sunday is going to look like and give a reasonable time estimate. Strategic planning All the teams and team members need to have a target for when their piece of the planning and preparation need to be complete. People work best with a deadline and tend to procrastinate without one. Financial support Prior to launch, the church has expenses. Your financial supporters want to know when the launch is going to happen for lots of reasons. Communicated poorly, having no launch date can give the impression that you don't know what you're doing. That could be a real barrier for supporters. There are lots of factors you need to consider when selecting a launch date: Natural back-to-church times It's no secret that church attendance typically drops during summer months. Launching in June will all but guarantee letting the air out your tires at the starting line. Late winter (Feb/Mar) and back-to-school time (Sep/Oct) are the two proven windows. Beware of Easter Easter seems like an obvious choice. It might get you the biggest turnout. But that attendance will be triply inflated: you'll have well-wishers, people that only come on Easter and all of your launch team there together. Attending church once or twice a month is the new normal even for dedicated Christians, so the very next Sunday, you may have only 2/3 of your team and all the well-wishers and Easter-onlys will have vanished. Your Sunday-after-Easter attendance could be less than half. What would that do to your team's excitement and momentum? Passion for Planting has observed it may be better to launch 3-4 weeks prior to Easter so that you can build on the momentum of the launch into the Easter boost. Be mindful of holidays Both national holidays, like Labor Day, and local holidays can significantly impact church attendance. Watch out for school breaks! Does the local district have a modified traditional schedule with a week off in October? Are they a year-round district? Local sporting events If the first home game of a professional sports team is 11am on Sunday, that could pose a significant barrier to prospects. Regional weather In the far north, launching in January or February would be very risky if snow is likely. Being delayed a week due to snow can significantly hinder people's likelihood of attending. But how hot is it still in September in Phoenix? Super Bowl Sunday and Spring Daylight Savings Time Change These two happen one right after the other, which always creates a challenge for spring launch timing. Other things to watch out for Keep your heads up for hunting season, major festivals (ex: Mardi Gras), and other similar events in your local culture. A Whole Launch Month? Many planters are finding planning for a month of Grand Opening, as opposed to a single launch Sunday, to be a good strategy: You may gain more momentum than from a single launch Sunday People who have to be out of town on the first Sunday haven't missed it It's culturally normative: new stores have their grand openings for extended periods of time People who come the first Sunday and get excited have the extended 'excuse' to invite their friends & family to come back with them If you decide to take this approach, make the 'whole month' concept extra clear on all your marketing. | Check for holidays, local events and other calendar conflicts. Check the local school calendars. Seek advice from other planters, a coach and other church leaders. Prayerfully consider the options. Select a date, or at least a month. This action is complete when you have selected a launch month or launch date. |  | 46 | 7 | 2015-02-03 05:00 | 2019-12-03 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated --pb 2018-11-02 content updated --pb 2019-12-03 content updated --pb
91 | 1139 | 1138 | Summarize vision, mission and values | Create a short and sweet version of your Vision Frame (philosophy of ministry) for inclusion in the Launch Strategy. | At this stage of the plant, you may be working on your church's Vision Frame (philosophy of ministry) at roughly the same time as creating your Launch Strategy. Summarize what you've created in <a href="/projects/project-tasks/[[project_id]]/all-tasks/268">Milestone: Define Church Vision</a> : Your mission statement answers the irreducible question: what are we supposed to be doing? Your short list of values answer the irreducible question: why do we bother? Your strategies answer the irreducible question: how do we 'do' the mission? And your measures describe what a mature disciple looks like, answering the irreducible question: when are we successful on an individual level? The vision should be living language, a colorful narrative that paints a picture of what the future will hold if we follow God in carrying out these things. It will be less of a rigid statement and more of a story or inspirational speech. | Summarize the key components of your Vision Frame . Include that summary in your Launch Strategy document. This task is complete when you've included your vision, mission, values, etc. in your Launch Strategy Template (<a href="/resources/item/144">MS Word</a> or <a href="/resources/item/365">Google Doc</a>). |  | 56 | 14 | 2000-01-01 05:00 | 2019-12-03 05:00 | 2000-01-01 05:00 | template: New Milestone 2018-01-15 changed to child task of #1138 --pb 2019-12-03 content validated --pb
92 | 1140 | 1138 | Summarize target area | Create a compelling overview of your target community for inclusion in the Launch Strategy. | Doing the missionary homework of really getting to know your community is a critical step in the church planting process. It should inform almost everything about how you 'do church'. Here it also helps you make a case for why it's important to plant a new church in your community at this point in time. You need to include a more in-depth look at your community than you did in your Launch Vision booklet, but don't go into the weeds too much. Find the handful of stats that will make it obvious why we need another church, or will highlight the strategic timing of planting now. Use rounded figures when you include numbers. | Review all of your demographic reports and research. Draft at least a page's worth of compelling stats about your community. Include that summary in your Launch Strategy document. This task is complete when you've included your target area summary in your Launch Strategy template. |  | 56 | 14 | 2017-09-05 04:00 | 2019-12-03 05:00 | 2000-01-01 05:00 | template: New Milestone 2018-01-15 changed to child task of #1138 --pb 2018-05-07 added& google& doc template version --pb 2019-12-03 content updated --pb
93 | 1141 | 1138 | Summarize Opening Day Expectations | Create a condensed version of your Opening Day Expectations document for inclusion in the Launch Strategy. | Your Opening Day Expectations document quantifies the near-term target you're shooting at. It's a facilitated daydreaming exercise to help you envision the launch of regular worship gatherings. Extract the highlights from your Opening Day Expectations document and include it in your Launch Strategy document so your audience can catch a glimpse of the dream. | Summarize your Opening Day Expectations. Include that summary in your Launch Strategy document. This task is complete when you've included your vision, mission, values, etc. in your Launch Strategy Template (<a href="/resources/item/144">MS Word</a> or <a href="/resources/item/365">Google Doc</a>). |  | 56 | 14 | 2000-01-01 05:00 | 2019-12-03 05:00 | 2000-01-01 05:00 | template: New Milestone 2018-01-15 changed to child task of #1138 --pb 2019-12-03 content updated --pb
94 | 1142 | 1138 | Articulate planting timeline | Create a planting timeline for inclusion in the Launch Strategy. | No Launch Strategy is complete without a clear timeline of your church planting process. Depending on your model, that may be a fixed date or a series of checkpoints/milestones. But you need to demonstrate that you're not just flying by the seat of your pants. Don't include too little or too much detail. Aim at filling a page with your timeline, whether it's list-style or designed with graphics. Hit the major milestones and seasons. Demonstrate that you've thought through timing and have a solid plan. | Create a list timeline or visual timeline of your church plant. Include that timeline in your Launch Strategy document. This task is complete when you've included your planting timeline in your Launch Strategy template. |  | 56 | 14 | 2017-09-05 04:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: New Milestone 2018-01-15 changed to child task of #1138 --pb 2019-12-03 content validated --pb
95 | 1143 | 1138 | Create a summary budget | Create a medium-level-detail budget summary for inclusion in the Launch Strategy. | Every new ministry and business venture requires resources. Ones that survive have a financial plan for the near and mid-term future. For your Launch Strategy, you need to include about a page's worth of budget data - both where the money's coming from and what you'll spend it on. Don't go into too much detail, but don't gloss over the finances. If you've used Passion for Planting's Church Plant Budget Worksheet Template , you can simply use the Summary page/tab. All the math is already done for you! | Copy the Summary page from your Church Plant Budget Worksheet Template (<a href="/resources/item/25">MS Excel</a> or <a href="/resources/item/366">Google Sheet</a>) or otherwise summarize 3+ years of budgetary figures. Include that summary in your Launch Strategy document. This task is complete when you've included your budget summary in your <a href="/resources/item/144">Launch Strategy template</a>. |  | 56 | 14 | 2000-01-01 05:00 | 2019-12-03 05:00 | 2000-01-01 05:00 | template: New Milestone 2018-01-15 changed to child task of #1138 --pb 2019-12-03 content updated --pb
96 | 1144 | 1138 | Draft key strategies to launch worship gatherings | Create summary versions of several key strategies you'll employ so you can include them in the Launch Strategy. | Ultimately, you'll work up entire strategy documents for each of the following (with PlanterPlan's help): Prayer Team Strategy Fundraising Strategy Disciple-Making Strategy Launch Team Development Strategy Church Groups Strategy Leadership Multiplication Strategy Community Networking Strategy Staffing Strategy Outreach Strategy Church Multiplication Strategy Facility & Equipment Strategy Marketing Strategy Ministry Teams Strategy Assimilation Strategy Right now you just need the short versions of each of these. If you've already completed one of the full strategy templates, then just hit its highlights as you fill in the Launch Strategy template. Most of the strategies you won't have fully hammered out yet, so just take a quick stab at a summary. Those summaries will become the seeds of your full-blown strategies down the line. | Using the Launch Strategy Template, fill in the boxes to summarize the key components of each of the strategies. This task is complete when you've filled in all the fields in the How We're Going to Do This section of your Launch Strategy template. |  | 56 | 14 | 2017-09-05 04:00 | 2019-12-03 05:00 | 2000-01-01 05:00 | template: New Milestone 2019-12-03 content updated --pb 2020-12-11 changed Due in # Days from 58& to 63& --pb
97 | 1145 | 1136 | Coaching Checkpoint: review and affirm planter's Launch Strategy | Review the planter's Launch Strategy document to provide feedback and ensure that it covers the bases. | The Launch Strategy document is the culmination of an entire Milestone worth of tasks in PlanterPlan. It is the business plan for launching the new church. It should incorporate all of the following: Vision, mission & values Target area Opening Day expectations Timeline Budget Key strategies | Review the Launch Strategy document. Provide feedback to the Planter. This action is complete when you, the coach, have reviewed and affirmed the planter's Launch Strategy document. |  | 63 | 7 | 2017-09-05 04:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: 2018-04-20 new task --pb 2019-11-26 content validated --pb 2020-12-11 changed Due in # Days from 56 to 36 & Duration from 7 to 14 --pb&
98 | 268 | 1310 | Milestone: Define Church Vision | Create clarity around your church's mission, values, beliefs and measures. | Your Philosophy of Ministry defines who you are and what you do, as well as what you don't do. It is the manifesto of the uniqueness of your church. It is your filter for making every important decision. Each Planter lives out a Philosophy of Ministry whether it is intentional or accidental. Think through the various aspects of your Philosophy of Ministry, write it all down, be able to communicate it, and be intentional about living it out. |  |  | 159 | 159 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-06-01 content updated --pb 2020-12-16 changed Due in # Days from 56& to 61& & Duration from 32& to 47& --pb&
99 | 269 | 268 | Read this "Vision Frame" overview | Understand the Vision Frame and commit to crafting one that is unique for the new church. | You have a way of doing ministry whether you've ever thought about it or not. The process of crafting a Vision Frame will force you to be intentional about how the new church is going to do ministry. And it will help you wordsmith powerful language that will help create the culture of the new church. This milestone is based on Will Mancini's seminal work, <a href="https://a.co/9iJdt6c">Church Unique</a> . You need to buy a copy right now and begin working through it. The tasks in PlanterPlan will work in conjunction with the book to help you produce the various pieces of the Vision Frame. This is a critical processes you can't skip over, photocopy or microwave. Your Vision Frame will: become the filter or decision matrix for everything you do going forward become your protection against any who come with competing or toxic agendas get everybody shooting at the same target provide common language to create culture and stay on mission What are the key parts of the Church Unique process? Discover your Kingdom Concept Define your Vision Frame: Mission Values Strategy Measures Articulate the Vision Proper | Watch the Will Mancini video <a href="https://www.youtube.com/watch?v=MbU7TonadH4">Organizational Alignment</a>. Download and read the <a href="/resources/item/346">Vision Frame Summary</a> provided by Auxano. This action is complete when you have watched the video and read all of the above. |  | 15 | 1 | 2000-01-01 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard Not sure what the 1st Action "training videos" is& supposed to be linked to.& It implies a series of videos.& I'm thinking it should be just a link to the "Philosophy of Ministry" video by Ed Stezter.& -----ds 2017-06-01 updated content and resource link --pb 2017-11-27 content updated to align with & Church Unique --pb 2019-01-11 Due in # Days corrected from 7 to& 31 --pb 2019-11-26 content validated --pb 2020-01-13 replaced broken& gdurl& link to image --pb 2020-12-11 changed Due in # Days from 31& to 15 & Duration from 7 to 1 --pb
100 | 270 | 268 | Call your coach about crafting a Vision Frame | Open a conversation with your coach about crafting your "Vision Frame" (a methodology of preparing philosophy of ministry language based on Will Mancini's <a href="https://a.co/9iJdt6c">Church Unique</a> ). | You have to start thinking early in the planting process about how you're going to approach ministry and what the DNA-setting language of the new church will be. Sample issues to process with your coach: The difference between vision and mission How to communicate your Vision Frame visually Your Vision Frame through the eyes of not-yet-believers Where planting more churches fits into your Vision Frame | This action is complete when you have called coach about the Vision Frame process. |  | 15 | 1 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-30 content updated, audience changed to coach --pb 2017-11-27 content updated to align with Church Unique --pb 2018-02-15 tweaked language based on feedback from Will Heath @ Auxano --pb 2018-04-20 updated content, changed audience to planter --pb 2019-01-11 Due in # Days corrected from 7 to& 31 --pb 2019-11-26 content validated --pb 2020-12-11 changed Due in # Days from 31& to 15 & Duration from 7 to 1 --pb
101 | 271 | 268 | Describe how your church will be unique | Write a clear, 1-sentence explanation of what makes your church unique. | Before God called you to plant this church, He had something in mind. He wanted to create a new congregation as unique as people are one to another. A congregation that would carry out His purposes and expand His Kingdom. Where do you begin discovering God's heart for this new church? Begin with prayer. Lots of prayer. Next, find early clues when you consider the overlap between your wiring and your community's situation. "The place God calls you to is the place where your deep gladness and the world's deep hunger meet." - Frederick Buechner What are the common threads between who God has created you to be and what your target community has become? Where is the intersection between what inspires & animates you and your community's specific flavor of brokenness? | Read Church Unique chapters <a href="https://www.willmancini.com/wp-content/uploads/2013/05/Ch9_Kingdom_Concept.pdf">9</a> & 10. Download and answer the <a href="/resources/item/347">Apostolic Esprit questions</a> provided by Auxano. Download and answer the <a href="/resources/item/348">Local Predicament questions</a> provided by Auxano. Regarding Collective Potential if you already have even a small team, download and answer the <a href="/resources/item/356">Collective Potential questions</a> provided by Auxano if it's just you and your spouse at this point, the "Collective Potential" may be aspirational; set a reminder to revisit this when you have at least 15-20 people on your team in BOTH cases, set a calendar reminder to revisit the Collective Potential exercise just after the first anniversary of your Launch - your team will have grown and changed Craft your unique Kingdom Concept statement. This action is complete after you've written a sentence that clearly describes how God is calling you uniquely to make disciples. " |  | 36 | 14 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-06-01 content and resource links updated --pb 2017-11-27 content updated to align with Church Unique --pb 2018-02-15 added venn& diagram images --pb 2020-01-13 replaced broken& gdurl& link to image --pb 2019-11-26 content validated --pb 2020-12-11 changed Due in # Days from 56 to 36 & Duration from 7 to 14 --pb& 2022-11-21 updated links --sc
102 | 1167 | 268 | Keep vision viral | Determine to do the hard work of word-smithing the various elements of the Vision Frame. | Simple clarity can be really hard work. Our temptation is to use more words so that people get a better idea of what we mean. But if the components of the Vision Frame are too long & complicated, people aren't going to remember them. Or worse, they'll offer up a version that sounds like it was put through <a href="https://www.wikihow.com/Play-the-Telephone-Game">the Telephone Game</a> first. You will be crafting important culture-shaping language in the coming tasks and subtasks. Here are Mancini's 5C's that you will use to test and refine each element: Clear is measured by the Junior High Rule: Is our language clear enough that a 12-year old boy who has not been to church would understand it? Concise is measured by the One Breath Rule: Can any part of the purpose be stated in one breath? Compelling is measured by the Resonance Rule: When the purpose is stated, does this make people want to say it again? Catalytic is measured by the Actionability Rule: Does your language inherently remind the listener to act rather than define success as what the ministerial staff does? Contextual is measured by the Bouquet Rule: Do the words communicate biblical truth for the listener's time and place, thus going to the garden of the Word and arranging the perfect bouquet for our people? For further clarification, refer back to Church Unique p.116 "If these five attributes are fused within the Vision Frame, amazing energy is released. People understand the vision because you have broken it down into meaningful bite-sized chunks. Credibility is enhanced by virtue of the fact that it is comprehensive without being overwhelming. Ownership is increased because it is portable; people can remember it, use it, and share it. It all funnels into an important reality: the vision is contagious. Church Unique, page 116 | This action is complete when you understand the 5C's and commit to use them to evaluate how you articulate each side of the vision frame. |  | 36 | 14 | 2018-04-20 04:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: 2018-08-28 new task --pb 2012-12-02 content updated --pb 2020-12-16 changed Due in # Days from 141& to 135& & Duration from 7 to 1& --pb&
103 | 272 | 268 | Craft your Vision Frame | Compile a Vision Frame document that will get everyone shooting at the same target and using the same language. | The Vision Frame document will simply be a compilation of what you'll produce in the following sub-tasks. Having them all together in one document will be useful in a variety of ways and will help transmit the DNA of the new church to others. The Vision Frame will include the church's: Mission Values Strategies Measures Descriptive Vision (Vision Proper) | Download Passion for Planting's Vision Frame Template (<a href="/resources/item/354">MS Word</a> or <a href="/resources/item/378">Google Doc</a>). Copy and paste the various pieces of your Vision Frame into the template. Send the document to your coach for review. Incorporate the coach's feedback and finalize the Vision Frame. This action is complete after you have a final draft of the Vision Frame ready for distribution. |  | 53 | 28 | 2000-01-01 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-06-01 content and resources links updated --pb 2017-11-27 content updated to align with Church Unique --pb 2018-06-01& gdoc& template added --pb 2019-11-26 content validated --pb 2020-12-11 changed Duration from 21& to 28& --pb &
104 | 274 | 272 | Craft your mission statement | Translate the mission Christ gave His church into a short phrase that is memorable and meaningful to your community. | You don't get to determine the church's mission. Jesus did that while he was still bodily walking the earth 2,000 years ago. What you absolutely must do is restate the mission in a way that makes sense to people in your community. At the heart of most evangelical church mission statements is the intersection of the Great Commandment and the Great Commission. Here are some useful questions to get you going: What does it mean for your church to win? What does it mean for your church to be faithful? What does hitting the bullseye look like? What makes God smile? Why did Jesus establish his Church? Caution: The mission statement is one of the first things you will do that affects what the church will become. If you craft a mission statement filled with "churchy" words, you can expect to create a churchy culture. Also note that the mission statement will be inward-facing language. Another PlanterPlan task will walk you through crafting a tag line that will be the outward-facing communication of your church's brand and mission. | Read Church Unique chapters 11 & <a href="4 Kinds of Church Members and How They Relate to Your Church's Mission by Will Mancini">12</a>. Meditate on passages where Jesus describes why he came and what he sent his church to do. Download and use the <a href="/resources/item/349">Mission Development Exercise</a> (instructions are on page 126 of Church Unique ). Draft several initial versions of your mission statement each using 12 words or less. Run them through the <a href="https://www.visionroom.com/tag/5-cs/">Five C's</a>. Ask for input from friends and peers. Get input from friends and neighbors who are not Christians. Finalize a written mission statement. This action is complete when you have finalized a written mission statement. |  | 39 | 14 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-06-01 content updated, resource link removed --pb 2017-11-27 content updated to align with Church Unique --pb 2019-11-26 content updated --pb& 2020-12-11 changed Due in # Days from 45& to 39 --pb& 2022-11-21 updated link
105 | 276 | 272 | Discover values | Describe what is important to your church by crafting a short list of church values. | The values of the church are the things that define why you do things and what you honor. Your values will play a significant role in shaping the culture of your church. Values are not something you can simply proclaim. You have to live them out, demonstrating them by your actions. Values become a guide for defining normal behavior. They need to become so deeply ingrained in the church's culture that the actual words rarely need to be spoken. Too many churches post a list of values, but then live out a different set of values. Values are caught more than they're taught. Your list should never be longer than 5 values - any more and even your staff won't be able to recite them, let alone live them out intentionally. If your initial list has more than 5, prayerfully consider how to merge or consolidate similar values into broader concepts. NOTE: these are organizational values that become decision-making filters. They're not individual spiritual growth measures - those will be developed in a subsequent PlanterPlan subtask. For each value ask: "Why is this value important?" | Read the brief post <a href="https://www.visionroom.com/the-starting-point-for-discovering-vision-and-values/">The Starting Point for Discovering Vision and Values</a> from Auxano's Vision Room. Read Church Unique chapter 13. Make an initial list of as many possible values that you can think of. Each value should flow from the question, "Why are we on mission?" Many of your listed values will be closely related to each other. Attempt to group similar values together to reduce the list to no more than 4 or 5 values. Download Auxano's <a href="/resources/item/350">Value Statement Worksheet</a> and write out several sentences for each value that starts "As demonstrated by&hellip;" Run your list of values through the <a href="https://www.visionroom.com/tag/5-cs/">Five C's</a>. Get feedback from others. Finalize your values. This action is complete when you've finalized the church values. | <a href="https://ericgeiger.com/2018/10/how-to-uncover-the-values-in-your-culture/">How to Uncover the Values in Your Culture</a> on ericgeiger.com | 46 | 14 | 2000-01-01 05:00 | 2019-11-26 05:00 | 2000-01-01 05:00 | template: standard 2017-06-02 Purpose & Description updated; Actions and resource not --pb 2017-11-27 content updated to align with Church Unique --pb 2018-02-15 tweaked language based on feedback from Will Heath @& Auxano& --pb 2018-10-19 additional resources subsection added --pb 2019-11-26 content validated --pb
106 | 277 | 272 | Define strategies | Write a short list of strategies that define how you will 'do church'. | Strategies answer the question, "How do we carry out the mission?" Using the metaphor of a factory, the strategies are the machines or stations along the assembly line. Your strategies are the pathway by which you makes disciples and carry out the mission. You need to be able to sketch your strategies on the back of a napkin as a diagram or simple mnemonic device. Strategies should be venue language (where to go), not imperative language (what to do). Your guests' fundamental question when they show up is, "Where do I go to [park, drop off kids, etc.]?" Your strategies should sound like the environments or gatherings that you will create to foster values and disciple-making. The few strategies you settle on will become buckets for how you'll communicate different groupings of teams, groups, etc. | Read Church Unique <a href="https://www.willmancini.com/wp-content/uploads/2012/08/Ch14_Strategy.pdf">chapter 14</a>. Scour the Gospels for principles you can learn from Jesus' earthly ministry. Draft several versions of your church strategies. Download Auxano's <a href="/resources/item/351">Our Strategy Picture Worksheet</a> for help creating your back-of-the-napkin version. Consider how your strategies mirror your values and clarify your mission statement. Run your strategies through the <a href="https://www.visionroom.com/tag/5-cs/">Five C's</a>. Get feedback from others. Finalize your strategies. This action is complete when you've finalized the church's strategies. " |  | 46 | 7 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-06-02 content validated --pb 2017-11-27 content swapped (was Measures, now Strategies); content updated to align with Church Unique --pb 2018-02-15 tweaked language based on feedback from Will Heath @& Auxano& --pb 2019-11-26 content validated --pb 2020-12-11 changed Due in # Days from 52& to 46& & Duration from 14 to 7& --pb& 2022-11-21 updated link --sc
107 | 278 | 272 | Recognize marks of a mature disciple | Describe what a mature disciple looks like so that everyone can know what the win is. | You measure what you value. Most American churches primarily measure attendance, offerings and buildings. We train people that those things define success. This is part of why so many American Christians believe that church attendance equals faithfulness and spirituality. Whether intentional or not, these measures define the culture and priorities of the church. A better way is to determine what a disciple of Jesus looks like. Missional measures answer the question, "What are the marks of someone following Jesus?" or, "What fruit does a disciple produce?" Many of these missional measures will come directly from Scripture. For instance, Galatians 5:22-23 tell us the fruit of the Spirit is love, joy, peace, patience, kindness, goodness, faithfulness, gentleness and self-control. Also, the Great Commission teaches us that the job of each Christian is to make disciples. Other measures will come out of your strategy. For instance, in a small-groups-centric church, a missional measure may be involvement in a small group. Once missional measures are defined, you'll have a clear filter for determining if ministries and programs are effective. If the ministry is producing disciples as defined by the measures, it's worth doing. If not, the ministry either needs to be adjusted or ended. | Read the <a href="/resources/item/352">The Difference Between Strategy and Measures</a> provided by Auxano. Read Church Unique chapter 15. Investigate scripture to re/learn how disciples of Jesus live and what fruit they produce. Make a list of the characteristics you desire to see people in the church grow into. See <a href="https://www.willmancini.com/wp-content/uploads/2013/06/Measures-as-the-Portrait-of-Discipleship_CU.pdf">sample</a> list provided by Auxano Boil the list down to no more than 3-5 key marks (or risk recreating a pharisaic checklist). Review your measures to make sure they aren't corporate measures, but individual marks. Now review these marks against your 'Strategies'. Be brutally honest - will the strategies you've proposed really produce the kind of disciple you've just described? Adjust your measures and/or your strategies as necessary. This action is complete when you have defined the missional measures for the new church. |  | 53 | 14 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-11-27 content swapped (was Priorities/Strategy, now Measures); content updated to align with Church Unique --pb 2019-11-26 content validated --pb 2022-11-21 updated links --sc
108 | 279 | 272 | Paint a vision picture | Sketch basic language, metaphors and milestones that capture the picture of the future God is calling your church to co-create. | Vision is different that Mission There are so many different approaches to vision & mission. Every book you read on the subject comes at it a little differently, and even uses the same words differently. For clarity on the difference, re/read 'Mission and Vision: Clarifying the Difference' in Church Unique (page 179). There are two aspects of the vision that you should be able to articulate: Subjective or Qualitative vision (story) Objective or Quantitative vision (numbers) Qualitative Vision Rather than write another concrete statement that competes with your mission statement, begin to build a bullpen of phrases, stories, images and metaphors you will pull from each time you describe the vision of the church. You will cast vision with living language, narrative that is painted within the bounds of the 4 sides of your Vision Frame. God's vision for your church's future is so multi-faceted, you couldn't really put it into a sentence anyway. Quantitative Vision There is also a part of the picture of the preferred future that should be measurable. This is the scorecard of your congregation as a whole. Think beyond attendance & offerings; what are the milestones or measures of success that God is inspiring you to strive for? Purchase God Dreams by Will Mancini The sequel to Church Unique is God Dreams , written to more fully flesh out the Vision Proper. While the sides of the Vision Frame help you define culture, God Dreams will help you paint a more compelling picture of God's preferred future for your church. It's more process, direction and strategic road map. | Download and read <a href="https://www.willmancini.com/wp-content/uploads/2012/05/Articulating-Vision-Proper_CU.pdf">Articulating Vision Proper: the Spider Diagram</a> provided by Auxano. Read Church Unique chapter 17. Draft a qualitative narrative of the preferred future God is calling you to co-create. Draft a few quantitative measures that God is challenging you to accomplish. Review both of these in the light of the 4 sides of your Vision Frame. Ask yourself if they work together and whether the mission & strategies you've articulated are likely to bring about the future you've described. Cast the vision to your coach and get feedback. Adopt vision language that you will use to inspire and lead your church. This task is complete when you have a final draft of your Vision Proper. |  | 53 | 14 | 2015-02-03 05:00 | 2022-02-10 05:00 | 2000-01-01 05:00 | template: standard 2017-06-02 Purpose & Description updated; Actions and resource not --pb 2017-11-27 content overwritten (was Decision-Making, now Paint a Vision); content inserted& to align with Church Unique --pb 2018-02-15 tweaked language based on feedback from Will Heath @& Auxano& --pb 2019-11-26 content validated --pb
109 | 283 | 268 | Coaching Checkpoint: review and affirm Vision Frame | Ensure that the planter has crafted a Vision Frame that can be virally transmitted. | Review the planter's Vision Frame (philosophy of ministry). Either encourage the Planter to rework the insufficient section(s) or affirm that it is a workable and appropriate Vision Frame. used by permission | Have the planter pitch his Vision Frame to you. Provide feedback to the planter - from the various sides of the Vision Frame, you should be able to triangulate common language and themes; the sides should complement each other. This action is complete when you, the coach, have reviewed and affirmed the planter's Vision Frame. |  | 60 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-06-02 content updated, audience changed to coach --pb 2017-11-27 content updated to align with Church Unique --pb 2018-02-15 tweaked language based on feedback from Will Heath @& Auxano& --pb 2019-11-26 content updated --pb 2020-01-13 replaced broken& gdurl& link to image --pb 2020-12-11 changed Due in # Days from 52& to 60 --pb&
110 | 275 | 268 | Develop church beliefs | Craft a written beliefs statement for the new church. | Your Biblical beliefs will play a significant role in shaping the character of your church. Like the guardrails along a road that keep a car from completely veering off the road, beliefs help keep a church focused and on the right track. The guardrails do not guarantee that a car is always staying on the pavement, but they do keep it from dangerously veering off course. You will be asked frequently (especially early in the new church) what your church believes. These questions don't come just from churched people. In studies of unchurched visitors to church, a desire to hear Biblical teaching and learn what the Bible has to say is cited as one of the top reasons people visit. While all Scripture is God-breathed and inspired by God, it is amazing how much disagreement we can have on what the Bible says. In matters essential to salvation, you must be firm in your approach and teaching. You need to be very clear on what you believe and what you will not compromise. You need to give thought to what you consider the essentials (those things where you will not compromise) to be. In other issues, be cautious to maintain unity and to avoid becoming distracted with issues that keep you from your primary purpose. If necessary, agree to disagree and focus your efforts to primary issues of theology. Our beliefs are those primary issues of theology that define what we believe about God, Jesus, the Holy Spirit, man, sin, the Bible, the role of the Church, and salvation. Our beliefs help answer the questions: "Why do we do what we do?" and "What do we do?" We will die for what we believe. Craft the words in a manner that are understandable to people with little or no church background. Use wording that draws people in and causes them to ask more questions. Avoid wording that puts people on the defensive and causes barriers. | For further instruction and multiple examples, read <a href="/resources/item/12">How to Develop a Beliefs Statement</a>. Make a list of key topics such as God, Jesus, the Holy Spirit, man, sin, the Bible, the role of the Church, and salvation. Look to Scripture to speak for you on what you believe in these areas. Write a brief beliefs statement about each. Attempt to tie the topics together into a common theme (like God's plan for redemption of man). Look at how other churches have written their beliefs statements. Search online key words such as church beliefs or Christian Church beliefs . Get feedback and input from others (particularly the unchurched). Finalize the written beliefs statements. This action is complete when you have written out a comprehensive set of belief statements. |  | 46 | 14 | 2000-01-01 05:00 | 2019-12-05 05:00 | 2000-01-01 05:00 | template: standard 2017-06-01 content and resource link updated --pb 2017-11-27 changed parent to "268" (the milestone) and task type to "task" (was a child). 2019-11-26 content updated --pb
111 | 280 | 268 | Learn to listen for attunement | Adopt a framework that will help you understand where each of your team members is at and how to lead them. | In Church Unique, Mancini uses the metaphor of a cruise ship to illustrate your team. There are those that get the vision and those that don't. And among them there are those that contribute and those that don't. When you put those factors together, you get the Attunement Grid: used by permission Crew - these are the lifeblood of your church: they are sold out to the vision and willingly contribute to the church and its mission Passengers - these people buy in to the vision, but either don't know how to contribute or can't; a little leadership will move many of them into your Crew Stowaways - they haven't yet caught the vision and they don't contribute Pirates - these can be the most dangerous because they can be easily mistaken for Crew: they show up, work hard, and even lead teams. But they have their own vision for the church which is not the vision God has entrusted you with. You will discover where your team members are through dialogue. There will be telltale signs and signature phrases they use that will clue you in. This isn't so you can pigeonhole people, but know how to lead them. Especially think through: the kinds of things you'll say to Passengers to get them excited about contributing or perhaps connected to the right serving opportunity how you'll give a 'positive no' to Pirates to keep their agenda from hijacking the vision of the church | Read Church Unique chapter 19. Brainstorm the signature phrases of each group: the kinds of things they'll say that reveal where they're at. Think through your basic approach to leading each of the groups toward greater clarity & contribution. Set a calendar reminder to revisit this every 6 months - this needs to be an ongoing diagnostic and not a one-time exercise. This action is complete when you have a strategy for recognizing and leading each of the four types of team members. | <a href="https://research.lifeway.com/2018/06/18/five-short-timers-who-may-not-stay-long-at-your-church/">Five "Short-Timers" Who May Not Stay Long at Your Church</a> by LifeWay Pastors | 61 | 14 | 2015-02-03 05:00 | 2024-11-25 21:30 | 2000-01-01 05:00 | template: standard 2017-06-02 content and resource links updated; the 'case study' was moved to become its own download (it was too lengthy); the other 3 resource links were updated but NOT the resources themselves --pb 2017-11-27 content overwritten (was Org Structure, now Attunement); changed parent to #268 (the milestone) and task type to "task" (was a child); content inserted to align with Church Unique --pb 2018-02-15 tweaked language based on feedback from Will Heath @& Auxano& --pb 2018-06-26 additional resources subsection added --pb 2019-11-26 content validated --pb 2020-01-13 replaced broken& gdurl& link to image --pb 2020-12-11 changed Due in # Days from 52& to 61 --pb& 2022-11-21 updated link --sc
112 | 287 | 268 | Call your coach about naming the church | Open a conversation with your coach about naming the new church. | While a good name won't guarantee you a healthy church, a poorly selected name could become an obstacle for people. Call your coach and work through your preliminary list of potential names with two filters in mind: Will this name connect with the target audience in the community? Does the church name appropriately reflect the values of the church? Sample issues to process with your coach: What a name communicates to people who are far from God Letting your demographics research inform what the name should be How to test a potential name in the community | This action is complete when your have called your coach about naming the church. |  | 31 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-30 content update, audience changed to coach --pb 2019-11-26 content updated --pb 2020-12-11 changed Due in # Days from 45& to 31 --pb&
113 | 288 | 268 | Select church name | Pick a legal name for the church that is both contextual and communicates the church's identity. | The church name you choose can play a significant role in the people's first impression of the church. Every name communicates something : Fresh or stodgy Formal or informal Alive or dead Churchy or edgy Old-school or hipster Artsy or plain But don't start picking a name until you've done three important things: Exegeted your community enough to create a Target Area Report Drafted your Vision Frame Prayed about it You have to be really know your community before choosing a name. The nuances of local nicknames, geography, attitudes, etc. cannot be appreciated from across the country. If you haven't done the missionary homework of studying your community, chances are really high that you'll pick a name that you'll end up changing to something else. The name of the church should flow directly out of its identity, delineated in the Vision Frame you just completed. The church's name encapsulates all of it. If you haven't finished the Vision Frame , chances are also high you'll pick a name that you'll end up changing. And even when you think you have a winner, don't finalize the name until you've done four important things: Make sure the name is available in your state (google "[name of state] business name search") Make sure there's not a similarly-named church nearby ( Discover Church is pretty close to Discovery Church ) Run it past your coach Conducted a coffee shop straw poll The Tension of Timing Unfortunately, picking a name is sometimes forced on you before all of that is done. The usual culprits are financial systems like bank account, payroll and/or online giving. Without a legal name for the church entity, those things are roadblocked. If you find yourself rushing to pick a name, you have a couple of options: See if a sponsoring church planting network or church congregation will handle your initial financial systems Rush to see how much of the contextualization and visioning process you can get done in a day or two before picking a name Pick a placeholder name, like "The Cheboygan Church Plant"; this is least desirable because it costs you time & expense to change the name later and banks are becoming increasingly inflexible on this | Complete at least a rough draft of your Target Area Report and Vision Frame (covered by preceding PlanterPlan tasks) before beginning. Search online to determine what church names are being used in your target area. Make a list of all other churches and think about what each name communicates about that church. Brainstorm possible names (see Additional Resources below). Ask Jesus what He thinks. Determine name availability/distinguishably through your <a href="https://www.llcuniversity.com/50-secretary-of-state-sos-business-entity-search/">Secretary of State's office or Corporation Commission</a>. Run the name past your coach, and if expected, your oversight or Management Team. Get feedback from people in the target area, especially non-Christians. Finalize the name. This action is complete when you have finalized the church name. | <a href="https://www.igorinternational.com/process/i/Igor%20Naming%20Guide%202022A.pdf">Igor Naming Guide</a> on igorinternational.com <a href="/resources/item/45">Church Name Brainstorming Guide</a> from Passion for Planting | 45 | 14 | 2000-01-01 05:00 | 2022-09-16 04:00 | 2000-01-01 05:00 | template: standard 2017-06-02 content updated --pb 2018-05-04 added link to 50 states'& SOS& --pb 2018-05-15 added Additional Resources subsection & links --pb 2019-11-26 significant content updated --pb 2020-12-11 changed Due in # Days from 52& to 45 --pb& 2022-09-16 removed dead Babylon Bee hyperlink --pb
114 | 289 | 268 | Coaching Checkpoint: review and affirm church name | Affirm that the name the planter wants to us is contextually appropriate and reflects the values of the church. | Use two filters when reviewing the name of the church: Will this name connect with the target audience in the community? Does the church name appropriately reflect the values of the church? If the name fails to meet either of these criteria, provide feedback to the planter and help the planter discover why the name is not a good fit. Some church planting networks will require the use of a denominational name. Have the planter confirm whether this is the case before making a final decision. | The planter communicates the name of the new church to the coach. The coach affirms that the name is contextually appropriate and reflects the values of the church. This action is complete when the coach has affirmed that the name of the church is contextually appropriate and reflects the values of the church. |  | 53 | 7 | 2015-02-03 05:00 | 2020-01-24 05:00 | 2000-01-01 05:00 | template: standard 2017-06-02 content validated --pb 2019-11-26 content updated --pb
115 | 447 | 1310 | Milestone: Develop a Culture of Multiplication | Establish a culture of reproduction within the church to multiply leaders, groups, sites and churches. | In order for the church to grow is size and effectiveness, volunteer and staff leaders need to be in place. Many church plants struggle with developing the leadership needed to grow the church. In some cases, the church growth outpaces the growth in leadership. This can quickly lead to staff burnout and a general collapse of systems. Reproducing leaders is something that is often talked about but seldom put into practice. By setting a reproducing DNA early in the life of the church, leaders will be more effectively identified, trained and released for ministry. |  |  | 137 | 106 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content validated --pb 2020-12-11 changed Due in # Days from 168& to 62 --pb&
116 | 1292 | 447 | Read this leadership multiplication overview | Understand what's at stake in multiplying leaders in the church plant. | Don't complain about not being able to find enough good leaders. If you don't want to find yourself leading alone, you need a farm system to grow more leaders around you. "Everything rises and falls on leadership." - John C. Maxwell The free agent era of church leadership is dying. Not that it probably ever really thrived. Because it usually worked this way: recruit a high-capacity leader from outside of your organization, use them up, spit them out, and then find another. A farm system identifies untapped potential in people within your organization, invites them to grow (and embraces still-learning levels of execution), equips and coaches them, and unleashes them into their calling. Which of those cultures would you rather be a part of? Yeah, a farm system takes longer, but you end up with an ongoing supply of better, more bought-in leaders that are the DNA of the church. Everything that happens in a volunteer-based organization like a church requires leadership. Your church needs disciple-making leaders, small group leaders, serving team leaders, and so many more. And your church needs to grow and reproduce teams, groups, sites and church plants. How will that happen without leaders? | Read the content above. Commit to creating a culture of leadership empowerment and reproduction. This task is complete when you have read the content of this overview. |  | 49 | 1 | 2019-11-01 04:00 | 2021-01-18 05:00 | 2000-01-01 05:00 | template: 2019-12-03 due date fields found empty -pb&
117 | 1293 | 447 | Call your coach about multiplying leaders | Open a conversation with your coach about growing and multiplying leaders. | Leadership development is critical to the sustainability of this new church. Too few organizations, churches or otherwise, have developed a healthy culture of leadership multiplication. Chances are good you haven't experienced what it's like. Or maybe it's been a while since you have. Now you have the awesome responsibility of creating that healthy culture in this new church. Lean on your coach's wisdom and experience and really pick his brain on leadership multiplication. Sample issues to process with your coach: How to get started multiplying leaders Spotting potential leaders How to have an ICNU conversation Embrace imperfect performance as the leader-in-training is learning When to entrust responsibility How to restore trust once broken | This task is complete when you have called your coach about leadership multiplication. |  | 55 | 7 | 2019-11-01 04:00 | 2019-12-05 05:00 | 2000-01-01 05:00 | template: 2019-12-03 due date fields found empty -pb
118 | 1294 | 447 | Craft a Leadership Multiplication Strategy | Create a strategy for multiplying leaders that is simple and reproducible. | The Leadership Multiplication Strategy document is aimed at helping you craft a simple process and simple language to communicate leadership multiplication ideas, principles and processes at the church. Complexity is the enemy of multiplication. Work through the sub-tasks and put your completed answers in the Leadership Development Strategy Template (below). Develop a Leadership Pathway Create a Leadership Development Map | Download Passion for Planting's Leadership Multiplication Strategy Template (<a href="/resources/item/388">MS Word</a> or <a href="/resources/item/389">Google Doc</a>). Work through the subtasks which follow. Compile all of your ideas and answers in the template. Send your completed Leadership Multiplication Strategy to your coach for feedback. This task is complete when you've written down your strategy to develop and multiply leaders in your church. Additional Resources Passion for Planting's <a href="/resources/item/390">Sample Leadership Multiplication Strategy</a> |  | 142 | 80 | 2019-11-01 04:00 | 2019-12-05 05:00 | 2000-01-01 05:00 | template: 2019-12-05 due date fields found empty --pb
119 | 448 | 1294 | Develop your leadership pathway | Create a leadership farm system to identify and grow leaders in your church. | In healthy churches, reproduction happens at every level of the church, from ministry roles to groups to campuses and congregations. Reproduction does not happen by accident, nor does reproduction happen in isolation from other Christians. A culture of reproduction is difficult to produce. So why bother? Many churches are plagued by a chronic shortage of leaders. This problem contributes to burnout for staff and volunteer leaders, and it stagnates growth. It is also a stewardship issue: if every time a new volunteer takes over a ministry position and has to figure things out from scratch, then tons of time is wasted that could have been focused on growing the ministry. If we truly believe that God has gifted each and every Christian, then it is our responsibility to equip those Christians for works of service (Ephesians 4:12). A Simple Pathway You need to outline the levels or progression of leadership. Someone doesn't go from apprentice to lead pastor in one easy step. What are those levels or stages that they can grow through to stretch and grow their leadership? Spell out what expectations are for each level of leadership. More is expected and required of leaders the further down the pathway they grow. A Simple Process Dave Ferguson of <a href="https://www.communitychristian.org">Community Christian Church</a> suggests this simple process for growing new leaders: I do. You watch. We talk. I do. You help. We talk. You do. I help. We talk. You do. I watch. We talk. You do. Someone else watches. By following this simple method at all levels of leadership in the church, you create a leadership pipeline. The next generation of leaders is always being trained up and released for works of service. It is important to set this expectation as value for the church. Expect each person to serve. Teach this on Sunday mornings, communicate it in membership classes, discuss it in small groups. If you have a volunteer leader in a certain role, the first step for them is to recruit an apprentice whom they are relationally investing in. The role could be anything from the lead pastor to a setup team member to a children's ministry volunteer. | Create a simple leadership pathway and include that in your Leadership Multiplication Strategy document. Define expectations for each level of leadership. Determine an apprenticeship policy. Adapt or adopt the process outlined above. This action is complete when you have written down the basics of your leadership pipeline. |  | 62 | 14 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content validated --pb 2019-12-05 content updated --pb 2020-12-11 changed Due in # Days from 168& to 62 --pb&
120 | 449 | 1294 | Create a leadership development map | Set expectations for how your leaders will be trained, discipled and coached. | A leadership development map is a simple tool to get leaders and apprentices on the same page. It shows leaders what they need to instill in their apprentices and sets expectations for what the apprentice needs to be working on. Components The map needs to include the 3-4 things you do to develop leaders. These are the elements of your leadership meetings, training events, and the skills you'll drill your leaders-in-training on. For example, your 3 might be Prepare, Equip, Inspire . Or Head, Hands, Heart . Or Vision, Huddle, Skill . Approaches For each of those components, decide on the things you'll do to help people make progress. In our example, will Prepare training be formal classes? On the job apprenticing? Required reading? Some combination thereof? Some ideas are: Monthly leadership huddles One-on-one coaching Group emails and other forms of written communication Leadership retreats Supervised training or apprenticeships Reading through a book together Self-study materials and curriculum Resources What is the specific content, curriculum and/or events you'll use for each approach? Some ideas are: Books that have been foundational in your own leadership growth Leadership blogs and eNewsletters Church or business leadership podcasts Conferences and seminars For any of these, be sure to name the specific book, podcast, conference, etc. that you'll use. | Name your leadership development map components. Run your list through the 5 C's test. Decide which approaches you'll use for each component. Decide which specific resources you use for each of the approaches. Include all of the above in the leadership development map table in your Leadership Multiplication Strategy document. This action is complete when you have charted out your leadership development map. |  | 62 | 14 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content validated --pb 2020-12-11 changed Due in # Days from 168& to 69 --pb&
121 | 1295 | 447 | Coaching Checkpoint: review and affirm Leadership Multiplication Strategy | Ensure that the planter has crafted a Leadership Multiplication Strategy that is simple and reproducible. | Review the planter's Leadership Multiplication Strategy document. Either encourage the planter to rework the insufficient section(s) or affirm that it is a workable and reproducible strategy. The document should include: a simple 'leadership pathway' that depicts next levels for leaders to grow into a leadership development map that lays out: steps used to develop leaders things done to help move leaders along specific content, curriculum or events to be used | Review the planter's Leadership Multiplication Strategy document and provide feedback where necessary. This task is complete when you, the coach, have reviewed and affirmed the planter's Leadership Multiplication Strategy document. |  | 69 | 7 | 2019-11-01 04:00 | 2019-12-23 05:00 | 2000-01-01 05:00 | template: 2019-12-23 content updated --pb 2020-12-14 changed Due in # Days from 135& to 142& --pb&
122 | 450 | 447 | Get ongoing leadership development meetings on the calendar | Start leadership meetings as soon as you recruit leaders to both equip and support those leaders. | Plan your leadership meetings in a way that enables busy people to participate. Not only will these meetings provide a context for training, prayer, and support, but problems can be dealt with before they develop. Once you've decided on a sustainable rhythm, put a recurring event on the church calendar. | Determine when and where your leadership meetings will be held. Determine the typical agenda for these meetings. Start the meetings and make adjustments as needed. This action is complete when you schedule the first leadership development meeting and have a plan for the frequency of those meetings. |  | 69 | 7 | 2015-02-03 05:00 | 2021-01-18 05:00 | 2000-01-01 05:00 | template: standard 2019-11-20 name updated from "Create a Networking Strategy" --pb 2019-11-26 content validated --pb 2020-12-16 changed Due in # Days from 98& to 52& & Duration from 35& to 21& --pb&
123 | 1253 | 447 | Craft a Church Multiplication Strategy | Create a strategy for how you'll work church multiplication into the very fiber of your church's DNA, and how you'll make it stick. | You, as the leader, may have a clear and tangible picture of what a culture of multiplication could look like. Maybe you've experienced it firsthand, or maybe you've been inspired by various books on the subject. But how do you transition from dream to reality? Working through this strategy document will help you think about multiplication systems and craft some clear next steps. By Age 3 or Not at All Don't put off developing this strategy until later. Research has revealed that churches that don't start a new church by their third birthday rarely ever become multiplying churches. If you wait until your church is "ready" to plant, you probably never will. | Download the Church Multiplication Strategy Template (<a href="/resources/item/323">MS Word</a> or <a href="/resources/item/360">Google Doc</a>). Work the subtasks that follow to assist you in filling out the template. Send your Church Multiplication Strategy to your coach for feedback. This action is complete when you have an actionable church multiplication strategy for the new church. |  | 234 | 220 | 2000-01-01 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: 2019-10-14 new task --pb 2020-12-16 changed Due in # Days from 200& to 143& & Duration from 45& to 112& --pb&
124 | 281 | 1253 | Develop a church planting philosophy | Articulate in writing a short summary of the unique church planting DNA that will undergird the church you are planting. | You are planting this church as a result of 2,000 years of church planting. Don't be the last link of the chain. You can't just hope that planting another church will happen. Now is the time to set church planting in the new church's DNA and put teeth to your decisions. Paint a picture of what your church planting efforts have accomplished by your 5th anniversary. Be specific. Now determine the very practical things you'll need to do to make that vision a reality: How will you embed church multiplication in every level and system in your church? How will you fund church planting? How will you build a church planter pipeline? What will your church planting scorecard be? How will you create a culture of sending? Which church planting network or group will you associate with? | Write out a vision for your church's church planting. Record all of your answers to the questions above in your Church Multiplication Strategy document. Set SMART goals for each element. This action is complete when you have hammered out these elements of your church planting philosophy. |  | 159 | 14 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-06-02 content updated --pb 2018-04-24 outdented& from child to task, set Parent ID to #268 --pb 2018-11-20 indented from task to child, changed parent ID from #268 --pb 2019-12-05 content updated --pb 2020-12-11 changed Due in # Days from 52& to 159 --pb&
125 | 282 | 1253 | Determine global missions involvement | Decide how your church will be involved in carrying out the Great Commission on a global scale. | Churches in North America have a great history of being involved in global missions. Sometimes it's difficult to convince established congregations to get involved in domestic church planting because they're so focused on global missions. Don't let the pendulum swing so far toward domestic church planting that global missions are ignored. Connecting your congregation to another people group or country can be a very healthy thing. | Decide now how you will lead your church to participate in global missions and at what point. Include that commitment in your Church Multiplication Strategy document (download as <a href="/resources/item/323">MS Word</a> or <a href="/resources/item/360">Google Doc</a>). This action is complete when you have included a statement on global missions involvement in the Church Multiplication Strategy document. |  | 159 | 14 | 2000-01-01 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-06-02 new content written (previously blank) --pb 2018-04-24 outdented& from child to task, set Parent ID to #268 --pb 2018-11-20 indented from task to child, changed parent ID from #268 --pb 2019-02-12 changed "include in Philosophy of Ministry document" to "include in Church Multiplication Strategy document" --pb 2019-12-05 content validated --pb 2020-12-11 changed Due in # Days from 52& to 159 --pb&
126 | 664 | 1310 | Milestone: Develop a Groups Strategy | Create systems and plan for environments that will foster relationships and disciple-making. | The church is about people, which means the church is about relationships. It's hard to develop meaning relationships in an hour large-group environment on Sunday morning. There are lots of different approaches to church groups. You get to start a groups system based on what God is calling you to do in your time and place. The tasks in this milestone will walk you through crafting strategies for your small groups structure, systems and leadership. |  |  | 180 | 136 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content update --pb 2018-03-28 changed Exponential channel link to discipleship.org link --pb 2018-11-19 updated content, changed title from "read this discipleship overview" --pb 2019-11-26 content updated --pb 2020-12-11 changed Due in # Days from 133& to 47& & Duration from 7 to 1 --pb&
127 | 665 | 664 | Read this Groups Strategy overview | Brief yourself on what goes into a Groups Strategy and the process you'll follow to create one. | True discipleship doesn't happen in an hour on Sunday mornings. The strategies you developed as part of your Vision Frame will have included some smaller group unit to foster community, relationships and disciple-making. The tasks in this milestone will help you articulate the way that God is calling you to structure your particular flavor of small groups. It's important to have it clearly in mind so that you can train apprentices and leaders. It will also be important for de-programming churched people that come with differing assumptions about what groups should look like. Your Groups Strategy will include: A brief philosophy of groups Type(s) of groups How group will be promoted and people invited to groups How leaders will be identified and trained Benchmarks of health/success | Read the content above. Quantify your own assumptions about groups. Begin praying about what God wants to do in and through the church's groups. This task is complete when you've read the content above. |  | 47 | 1 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated, audience changed to coach --pb 2018-04-20 updated content, changed audience to planter --pb 2019-11-26 content updated --pb 2020-12-11 changed Due in # Days from 133& to 53& --pb&
128 | 666 | 664 | Call your coach about launching groups | Open a conversation with your coach about launching a groups ministry. | Your coach is a practitioner in church planting, which includes starting Groups. They come in all shapes and sizes, but your church will need some kind of groups structure to foster community and disciple-making. Sample issues to process with your coach: Group size and structure Content and format Measuring success Group leader expectations Promoting groups Overcoming objections to joining a group | This action is complete when you have called your coach about launching groups. |  | 53 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content updated --pb 2018-04-20 moved to Launch Team milestone --pb 2018-11-20 moved to DNA milestone, demoted to child, changed Due in days from 114, changed parent ID from #375 --pb 2019-11-25 content updated --pb
129 | 670 | 664 | Craft a Groups Strategy | Draft a comprehensive strategy for groups at your church. | Disciple-making and community don't happen during an hour on Sunday morning. And they don't happen when a believer is a Lone Ranger. Groups create environments where discipleship and community can flourish. There are many different ways to do church groups. As the leader you get to decide how groups will start and function at the church. Using the Church Groups Strategy Template (<a href="/resources/item/357">MS Word</a> or <a href="/resources/item/359">Google Doc</a>), you will work through the following: A brief philosophy of groups Define what kind(s) of groups to start Set a goal for groups at Launch Establish expectations of group leaders Develop group leader training plan Select group curriculum or content Decide when to start groups | Download Passion for Planting's Church Groups Strategy Template (<a href="/resources/item/357">MS Word</a> or <a href="/resources/item/359">Google Doc</a>). Work through the content above and the subsequent PlanterPlan subtasks; record your thoughts & decisions in the template. Interview other churches you respect about their groups structure and systems. Finalize your Church Groups Strategy. Send the completed Groups Strategy to your coach for feedback. This action is complete when you have submitted your written Church Groups Strategy to your coach. |  | 60 | 7 | 2000-01-01 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template: standard 2018-03-28 content overhauled --pb 2019-11-26 content updated --pb 2020-12-11 changed Due in # Days from 147 to 60& & Duration from 14& to 7& --pb&
130 | 671 | 670 | Review church strategies and measures | Review the church's Vision Frame to keep groups structure and systems in alignment with the vision of the church. | When you did the hard work of prayerfully setting the church's DNA through the Vision Frame process, you were led to particular strategies. One of those strategies was invariably some version of church groups. Reorient yourself to the entirety of the Vision Frame and keep the Measures firmly in mind as you strategize your groups systems and structures. Will the groups you envision really produce the kind of disciple described in the church Measures? Will the groups interplay with the other Strategies to accomplish the Mission of the church? | Reread your Vision Frame document. Consider the role of groups in the overall Vision Frame . Keep all of that in mind as you proceed to fully flesh out your groups strategy. This action is complete when you have reviewed your Vision Frame and committed to designing your groups strategy to support it. |  | 60 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2018-03-28 content overhauled --pb 2019-11-26 content validated --pb 2020-12-11 changed Due in # Days from 140& to 60 --pb& 2022-11-21 updated link --sc
131 | 672 | 670 | Define what kind of groups to have | Clearly articulate what groups will look like and how they will function at the new church. | There are tons of options for church groups. Your strategy may even include several types or levels of groups, like micro, small, and large groups. Explore different models and prayerfully determine what will work best in your context. There are lots of ways to approach groups. Here are 11 small group archetypes outlined on <a href="https://www.smallgroupchurches.com/11-small-group-strategies-for-churches/">smallgroupchurches.com</a>: On-going Open Group Semester Sermon Study Semester Elective-Group 40-Day Campaign 9-Month Closed Group Mid-sized Geographic a System that Promotes 2 or More Group Types the Both/And System Cell-Based Church Groups of 12 Missional Communities But also consider: discipleship micro-groups (huddles, triads, etc.) Sunday school classes (gasp!) 12-Step recovery groups &hellip;others not mentioned here Important decisions you'll need to make for each kind or category of groups you'll start include: How big should the groups be (min/max)? What will you call them? What will be their focus and/or expected outcomes? What will their format or curriculum be? What will their duration and annual rhythms look like? | Research different groups models. Determine which model will best fit the new church. Complete the Types of Groups table in the Church Groups Strategy Template . This action is complete you have charted out specific details for each kind/category of group you will start. | <a href="https://a.co/9vY6FzK">The Seven Deadly Sins of a Small Group Ministry</a> by Bill Donahue et al. <a href="https://a.co/7uuz0un">Building a Church of Small Groups</a> by Bill Donahue et al. <a href="https://a.co/807dpWy">Small Groups for the Rest of Us: How to Design Small Groups System to Reach the Fringe</a> by Chris Surratt <a href="https://www.amazon.com/Starting-Small-Ultimate-Group-Blueprint/dp/0615924425">Starting Small: the Ultimate Small Group Blueprint</a> by Ben Reed <a href="https://a.co/blH1Kfz">The Connecting Church 2.0: Beyond Small Groups to Authentic Community</a> by Randy Frazee | 60 | 7 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2018-03-28 content overhauled --pb 2019-11-26 content validated --pb 2020-12-11 changed Due in # Days from 140& to 60 --pb&
132 | 673 | 670 | Set a goal for groups at launch | Prayerfully set goals for what you want your groups system to look like when you launch regular worship gatherings. | Goals help guide our actions and priorities. Setting comfortable goals that we know can be accomplished leaves little room for God's provision. Big goals will force you to pray more and make different kinds of decisions to get there. Set clear goals for the following: Percentage of Launch Team active in groups Number of groups at Launch Number of groups ready to multiply at Launch Percentage of average attendance active in groups after Launch, or maybe groups to attendance ratio | Set goals for each of the above along with any other useful health metric. Strategize how you'll get from where you are today to where you want to be at Launch. Record the goals strategies in your Church Groups Strategy document. This action is complete when you have set goals for your groups and charted a path to attain them. |  | 60 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2018-03-28 content overhauled --pb 2019-11-26 content validated --pb 2020-12-11 changed Due in # Days from 140& to 60 --pb&
133 | 674 | 670 | Establish expectations of group leaders | Clearly define what is expected of group leaders to guide their growth and decision-making. | Every volunteer needs clear expectations. They want to know what is being asked of them and how much time it will take them to do the job. For leadership positions, including group leaders, there are higher expectations. But what exactly are those expectations? Do your group leaders need an MDiv before you'll let them lead? Or will they only to have to pass the 'can fog up a mirror' test? What, if any, moral or behavior boundaries will you set for them? How Pharisaic should that list be? What are their time commitments for training, preparing, shepherding, etc? What are they responsible for? | Write out clear group leader expectations. Consider using a job description or leadership covenant for the group leader to sign. Record the expectations in your Church Groups Strategy document. This action is complete when you have written out clear expectations of group leaders. |  | 60 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2018-03-28 content overhauled --pb 2019-11-26 content validated --pb 2020-12-11 changed Due in # Days from 140& to 60& & Duration from 14& to 7& --pb&
134 | 675 | 670 | Develop a training plan for group leaders | Chart a path for people to grow into group leadership so that groups can grow and multiply. | Leadership training provides one of the best opportunities to communicate with and cast vision to key influencers in the new church. You simply cannot spend enough time with these church leaders. The degree to which they buy in and own the process will affect the DNA and health of the church. In developing a training plan, consider: the type of training (book study, interactive, lecture, etc.) frequency of training (weekly, monthly, etc.) method of training (ex: formal classroom or informal small group environment) length of training (1 hour, all day, etc.) content of training whether to use of outside workshops/seminars (Exponential, Willow Creek, etc.) | Review group leader training plans at other healthy churches. Determine what plans fit the vision and style of your church. Develop or customize a plan to train your group leaders. Include the training plan in your Church Groups Strategy document. This action is complete when you have a written strategy to train group leaders. |  | 60 | 7 | 2015-02-03 05:00 | 2021-01-18 05:00 | 2000-01-01 05:00 | template: standard 2018-03-28 content overhauled --pb 2019-11-26 content validated --pb 2020-12-14 changed Due in # Days from 140& to 74& --pb& 2022-11-16 updated SOAP study link to an existing site. --nz
135 | 678 | 664 | Coaching Checkpoint: review and affirm Groups Strategy | Make sure that the planter has thought through and developed a Groups Strategy. | After you get the planter's Groups Strategy document, either encourage the planter to fix its weaknesses or affirm that is a sufficient plan. A solid Groups Strategy will cover: description of kind(s) of groups group curriculum or content expectations of group leaders training plan for group leaders a target date for launching the first group(s) a goal for number of groups at launch | Review the planter's Groups Strategy. Offer the planter feedback. This action is complete when you, the coach, have reviewed and affirmed the planter's Groups Strategy. |  | 67 | 7 | 2015-02-03 05:00 | 2020-12-11 05:00 | 2000-01-01 05:00 | template: standard 2018-03-29 content update --pb 2018-11-19 title changed from "implement discipleship strategy" --pb 2019-12-03 content updated --pb 2020-12-16 changed Due in # Days from 175& to 105& & Duration from 42& to 45& --pb &
136 | 1312 | 0 | PHASE III - STRUCTURE | [6 empty] | 2020-11-25 05:00 | 2021-01-15 05:00 | 2000-01-01 05:00 | template:
137 | 245 | 1312 | Milestone: Set Up Office | Provide an environment where you (and additional staff as appropriate) can work productively. | Whether you set up an office inside or outside the home, you will need to set a few things up. Typical office location choices include: rented office space donated space from a local church or business working from a coffee shop or other public space Your workspace can maximize or choke your ministry opportunities. Be intentional as you decide what your office will be and where it will be located. Your ministry will be impacted by where you set up your office based on: whether you can host meetings at convenient times people's perceptions of your space your ability to interact with not-yet-believers each day Carefully consider the tensions of productivity, accessibility, and evangelistic opportunities as you decide. |  |  | 45 | 45 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-08-10 content updated --pb 2019-12-10 content updated --pb 2020-12-16 changed Due in # Days from 98& to 45& & Duration from 30& to 45& --pb&
138 | 246 | 245 | Rent a PO Box or other mailing address | Establish a permanent mailing address for the church that can be used on legal forms and won't change when you move your family or the church meeting place. | You don't usually start off with a physical building or mailing address, but various government forms, purchase invoices, etc. require an address. You have a couple of options: Use your home address - the problem is that your address becomes a matter of public record for people to stalk you & market to you. And it's common to move your family at least once in the early years, which creates a lot of address change paperwork for the church. Use a supporting church address - the problem is that you won't get your mail in a timely manner, and they'll want this to be a short-term solution, which creates a lot of address change paperwork when you switch Use your rented office address - office space can be very expensive, but if you've already decided to go this route, having your mail sent there is a no-brainer Rent a PO Box Passion for Planting recommends renting a PO Box to use as the church address. Get it very early in the process so that you can use the address on forms, purchases and business filings. The PO Box used to be problematic because UPS & FedEx wouldn't deliver there, but the US Post Office fixed that in 2012 by allowing you to use the office's street address along with your box number. <a href="https://www.mymoneyblog.com/po-boxes-real-street-address.html">Read more</a>. PO Boxes are also a lot cheaper that postal service mailboxes (ex: UPS Store): you can usually rent a small PO Box for $50-$75 a year but will often pay $12-$25 a month at a retail location. Don't use your home address if it is at all avoidable. | <a href="https://tools.usps.com/find-location.htm">Locate a USPS location</a> near where the worship gathering facility is likely to be. Rent a PO Box. This action is complete when a PO Box or other physical address has been set up for the church. |  | 7 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-08-10 content updated including removal of reference to UPS Stores --pb 2019-12-10 content validated --pb 2020-12-14 changed Duration from 63& to 7 --pb&
139 | 251 | 245 | Set up home office | Save the church plant thousands of dollars by not renting office space while still meeting the needs of your staff. | When deciding whether to set up office in your home or to go rent space, there are several things to consider. Passion for Planting recommends most planters set up a home office. Here are the advantages to a home office: It's cost effective . In most suburban and city areas you will pay a minimum of $1,000 a month and upwards to $3,000 a month for rented office space. Add utilities to that cost and you can quickly be in the tens of thousands of dollars for rented office space. Cash flow is important. Spending it on rented office space can severely limit your ability to do ministry. It forces you out into the community . A home office only works for a handful of hours during the week, but that's good. Unavoidable distractions at home will drive you out into the community where the people that you're trying to reach are. It gives you more time for both work and family . Why? There is no commute involved. Not commuting would save the average American an hour a day. That's an hour you could spend relaxing, spending time with God, exercising, hanging with the family; the possibilities are endless. One extra hour a day is nearly 11 extra days of the course of year - having a home office is like getting an extra two weeks of vacation a year! If you have young children, working out of the home can be difficult. Be sure to set clear boundaries such as, "If the door is closed, please do not disturb me. But if it is open, I'd love to have you come say hi" or something similar. Or consider using someone else's home. In many families, both the husband and wife work. You could use a desk or garage workstation in their empty home as your office during the day. | Determine the location for your home office. Set up your office and get to work. This action is complete when you have set up a home office. |  | 30 | 30 | 2015-02-03 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: standard 2017-08-10 content updated --pb 2019-12-10 content validated --pb 2020-12-14 changed Due in # Days from 77& to 30& & Duration from 14& to 30& --pb&
140 | 253 | 245 | Get a dedicated church phone number | Get a phone number for the church so you don't have to publish your personal number to the public. | Communications are vital to the new church, but life-work boundaries are too easy to cross. Set up a phone number for the church very early in the process, but pick an option that is flexible and will eventually accommodate other staff and/or locations. There are 3 main options for setting up a church phone number: Dedicated Land Line This old-school approach is the most expensive and least portable. This may be a good option if you're building out a 24/7 leased facility, but Passion for Planting discourages this option for all other planters. Cell Phone This is an OK option, but is equally as expensive. And you have to pick the lesser of 3 evils: use your personal cell (or let the church cell double as your personal cell) carry 2 phones everywhere (or leave your personal cell phone at home) buy a higher-end mobile phone that accepts to SIM cards (has 2 phone numbers) Voice Over IP (VoIP) Passion for Planting recommends picking one of the various internet phone options. Here's why: they are inexpensive or free (see below) they are portable - it isn't tied to a location or even a specific user you may be able to answer calls through your computer/browser they may offer sharing or multiple inboxes - press 1 for Joe, press 2 for Erica Current best options (Winter 2019): <a href="https://voice.google.com/about">Google Voice</a> PRO: free (personal) or $10/mo (if you used GSuite), one number rings any/all of your devices, unlimited calling, send & receive SMS/MMS texts; CON: no support, sometimes poor call quality, one inbox (no extensions); not available in some markets <a href="https://www.magicjack.com">MagicJack</a> PRO: $39/year, rings mobile app and/or phone connected to device, unlimited calling, send & receive SMS texts; CON: no MMS texts, one inbox (no extensions) <a href="https://www.skype.com/">Skype</a> PRO: $3.59/mo, send & receive SMS texts, unlimited calling; CON: one inbox (no extensions), only rings app (computer and/or mobile app) <a href="https://www.godaddy.com/smartline">GoDaddy SmartLine</a> PRO: $10/mo, rings any/all of your devices, set business hours, caller ID, send & receive SMS texts; CON: one inbox (no extensions) <a href="https://www.phone.com">Phone.com</a> PRO: $10/mo, unlimited users, rings any/all of your devices, send & receive SMS texts; CON: 300 minute monthly limit <a href="https://www.sideline.com">Sideline</a> PRO: $10/mo, one number rings any/all of your devices, unlimited calling, send & receive SMS/MMS texts; CON: one inbox (no extensions) | Research costs associated with each option for phones Determine which option is most cost effective and will serve the needs of the church the best Obtain a phone number for the new church This action is complete when you have a phone number for the church. |  | 45 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard Q:& Should we remove this task altogether?& ----ds& No it still applies... some guys will still do this. It talks cellular and voip& as options. 2017-08-11 content updated --pb 2019-12-10 content updated & links verified--pb 2020-08-02 GoDaddy SmartLine& added --pb 2020-12-14 changed Duration from 7 to 14 --pb&
141 | 256 | 245 | Beg, borrow or buy office equipment | Equip the church office with the tools and resources you need to create a productive environment. | There are several pieces of equipment that you'll want to purchase or have donated to make your office efficient and effective: Laptop computer Wireless router All-in-One printer Smart phone Productivity software Other hardware you might consider includes: Folding machine Tablet (iOS or Android) Laptop System Requirements Figure out what the highest demands on your machine will be and get one that has at least that much power. Typically, those will be: projection - does it have enough muscle to run the projection software? Does it have the right output jacks (tablets probably don't)? video editing - does it have enough RAM and drive space to edit & render video files with your preferred editing software? | Figure out which office equipment you'll need to be productive. Buy it or get it donated. This action is complete when you have obtained the office equipment you need. |  | 30 | 30 | 2015-02-03 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: standard 2017-08-25 content updated --pb 2019-12-10 content validated --pb 2020-12-14 changed Due in # Days from 77& to 30& & Duration from 7 to 30& --pb& 2021-01-28 merged in content from task "Get a laptop computer" --pb
142 | 259 | 245 | Get these productivity apps | Get these church planting power apps to maximize your productivity. | Don't break the bank, but don't be penny-wise and pound-foolish either. Get the apps you need to be productive. Office Suites Microsoft Office (Word, Excel,Powerpoint, etc.) the overall dominant choice but not free $8/user/month until you get your 501c3 back from the IRS; then can be free thru TechSoup.org PC and Mac AppleiWork (Pages, Numbers, Keynote, etc.) free with apple computers since late 2013 Mac only Google apps (<a href="https://www.google.com/gmail/about/">Gmail</a>, <a href="https://docs.google.com">Docs</a>, <a href="https://sheets.google.com">Sheets</a>, <a href="https://slides.google.com">Slides</a>, etc.) free all platforms <a href="https://workspace.google.com/">Google G-Suite</a> (Docs, Sheets, Slides, etc.) same as google apps, but branded with your church's domain name $6/user/month until you get your 501c3 back from the IRS; then can be free thru the Google Grant program all platforms Cloud File Storage These allow you to share files across devices and keep them safely backed up on a server in case your device(s) go down. Choose: <a href="https://www.icloud.com/">iCloud</a> (Mac) <a href="https://www.dropbox.com/">Dropbox</a> (PC and Mac) <a href="https://drive.google.com">Google Drive</a> (PC and Mac) another you prefer Password Manager Don't just keep using the same password on all the different sites you use. Get a password manager that will create different passwords for each site and then auto-fill them for you. Your best options will allow you to sync your passwords across your devices so that they're instantly accessible. Choose: <a href="https://1password.com/">1Password</a> <a href="https://www.lastpass.com/">LastPass</a> <a href="https://www.dashlane.com">Dashlane</a> another you prefer Collaborative To-Do List These apps help you keep track of what needs to get done. They also allow you to invite team members to share the same task list so you can delegate stuff out and see how it's going. Choose: <a href="https://todoist.com">ToDoist</a> <a href="https://asana.com">Asana</a> <a href="https://todo.microsoft.com/tasks/en-us">Microsoft To Do</a> another you prefer | Figure out which software you'll need and maybe try out a new category you've never used before. Buy it and install it on your various devices. This action is complete when you have obtained office software. |  | 30 | 30 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard So many options here.& Thinking this is& intuitive for guys today.& & Definitely need& guidance on video editing software (another task) but not on office software.& Delete task? -----ds Agreed. Will delete when the interface supports it. --pcf 2017-08-25 content updated --pb 2019-12-10 content validated and links verified --pb 2020-01-02 Wunderlist removed on announcement of its discontinuation, replaced with MS To Do --pb 2020-12-14 changed name from "Buy software" & Due in # Days from 45& to 30& & Duration from 7 to 30; content updated --pb&
143 | 183 | 1312 | Milestone: Implement Fundraising Strategy | Put into practice the strategies laid out in the previous Milestone to provide for all of the church's financial needs. | Now that a fundraising strategy has been developed, it is time to put the strategies into action. Take each action item resulting from the fundraising strategy and add them to this milestone. This can be done through the PlanterPlan tool. Fundraising will be an ongoing effort during the pre-launch phase of the church. Be sure to set realistic goals for completion. If you're planting through a managing partner, denomination, network or mother church, consult with them about where your financial supporters can send money or how they can give to your project online. |  |  | 109 | 109 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated --pb 2019-12-11 content validated --pb 2020-12-16 changed Due in # Days from 60 to 74& & Duration from 39& to 59& --pb&
144 | 178 | 183 | Create Launch Vision prospectus | Create a Launch Vision Prospectus (aka Vision Book) to clarify your vision and provide a resource for your fundraising and Launch Team recruiting. | You have been called to plant a church. You have been praying and God has given you a vision that is growing more exciting each day. You are eager to turn this vision into action. 3 Levels of Detail There are 3 different launch documents you'll create that increase in their level of detail: Launch Vision Prospectus This is a shorter, big-picture document. It's intended to be a colorful and compelling quick read that gives prospective donors and Launch Team members a glimpse at the vision of the church plant. Launch Strategy Document This is a lengthy document that lays out in detail how you'll go about launching the new church. It is content-driven with few images, focusing on philosophy, strategies and goals. It's the business plan to pitch to venture capitalists. Think Shark Tank . Launch Plan The Launch Plan goes further by spelling out specific actions that need to be accomplished to execute the strategies. It also assigns dates and doers for each action. PlanterPlan is your Launch Plan! The Launch Vision Prospectus Creating the prospectus will help you focus and refine your vision. It will help you think in stories and pictures, and challenge you to attach some dates and numbers to the project. The printed Launch Vision will become an important tool in your fundraising efforts. It can also be a great piece to hand out at your info nights or at Chamber of Commerce mixers, for example. Here are the things to include in your Launch Vision content: Summary information about your target community; consider telling the story of a typical individual or family that lives there Reasons to plant a church there now Bio of the planter and picture of the planter's family Brief overview of your mission, vision and values (it's OK if you don't have the language formalized at this point; get it roughly right) An overview time line, especially as a graphic A high-level budget; demonstrate as you're able that there are already funds committed - people hesitate to be the first one in the water Endorsements from respected pastors and/or organizations Clear next steps that the reader can take to get involved Use the template linked below to assemble your content for delivery to a graphic designer. A professionally designed and printed prospectus may cost a few bucks, but can bring significant returns on the investment. | Download Passion for Planting's Launch Vision Contents Template (<a href="/resources/item/328">MS Word</a> or <a href="/resources/item/369">Google Doc</a>). Fill in the blanks to craft the content that a designer will use to draft your Launch Vision. Work with a graphic designer to create a colorful, compelling Launch Vision document. Ask your coach and several other experienced church planting leaders to review your Launch Vision and give you feedback. Incorporate their suggestions. Print/produce the final Launch Vision document. This action is complete when the final Launch Vision document is printed and in hand. |  | 46 | 14 | 2000-01-01 05:00 | 2020-06-24 04:00 | 2000-01-01 05:00 | template: standard 2017-05-31 completely overhauled content from "Launch Plan, including Launch Strategy" to simply the Launch Vision document --pb 2018-07-26 changed title from "vision document" to "vision prospectus" --pb 2018-11-02 content updated --pb 2020-06-24 added 'send to coach' language --pb 2019-11-19 content updated --pb
145 | 179 | 178 | Clarify church planting approach and model | Clarify which church planting approach and model God is calling you to use so you can communicate it clearly and partner with the right organizations. | There is no universally agreed upon list of church planting models - ask ten different organizations for a list of the different models and you will get ten different lists. Instead of providing a comprehensive list of all possible models, we will attempt to highlight the high-level considerations that distinguish different models. Note: Often people confuse "models," "strategies" and "approaches." For example, the decision to host a worship gathering in a small coffee shop venue with candles to reach Gen-X'ers is a strategy and not a model. However, starting churches that meet exclusively in coffee shops would be a model. An approach would be the way in which the leader(s) goes about starting these new environments or churches. ### Approach Church planting approaches typically fall into three major categories: Parachute A planter and their family move into a new location to start a church from scratch. The planter begins with little support and few connections within this new area. The planter and their family are "pioneering" new territory. Where there is great risk, there is great reward, but this approach is not for the faint of heart. Sponsoring Church An existing church provides the initial leadership and resources (dollars and/or people) to get a new church started including the selection of the church planter. Often the church planter is selected from within the church and has already bought into its vision, values and beliefs. The existing relationship allows for a close working relationship between the "mother" and "daughter" churches. Although the new church is autonomous, the sponsoring church often has significant influence in the new church (including decision making during the pre-launch phase). Advantages often include increased financial resources and the ability to draw core team/launch team members from the mother church. Collaborative Network/Partnership This is a rapidly growing trend where churches work together to plant churches. These alliances are referred to as collaborative, partnership or planting networks. The participating organizations often share common beliefs and a passion for starting new churches. Planters often get many of the benefits of the "sponsoring church" model but with increased autonomy in decision making. The approach doesn't dictate the model. All of these approaches can and do employ various models in order to accomplish their mission of planting healthy churches. Therefore, the question becomes which approach works best for you based on your situation and calling? ### Model Along with determining your approach , you have to determine which model best positions you to accomplish the vision God has placed in your heart and mind. Work through these questions to gain some clarity on models: What is your strategy for disciple-making? Will you build a core team one person at a time through relationships with the lead planter? Will you draw a crowd through marketing and outreach? Will you develop fully devoted followers through one-on-one discipleship in small groups? Will you focus on reaching seekers and establishing easy "next steps" for them to get connected at their own pace through a range of felt-needs-based ministries and programs? Will you use a formalized class/curriculum based approach (like 101, 201, 301, 401)? Will you hold regular Sunday worship gatherings? What will the role of your small groups be? Will teaching be primarily done through Sunday sermons, through classes, or through small groups? Do you anticipate having a public launch or functioning on a more informal, relational basis? What will your staffing philosophy be? Will the new church be able to financially support a full-time paid minister? Will you be the only staff initially or will the plant have the funding for a staff team? If bi-vocational or co-vocational, how much time will you have to dedicate to the church? Is the plan to eventually become paid by the new church or to continue in a co-vocational capacity? What size Launch/Core Team will you build? How large do you expect the launch team/core team to be when public worship gatherings are started? How do you intend to build and add to the launch team? Will the team primarily come from a single existing church, multiple existing churches, or from non-believers? How will you build community awareness about the church? Will you grow exclusively through friends inviting friends - relationships? Will you use outreach activities to build awareness and start conversations in the community? Will you use marketing activities to build awareness and start conversations in the community? Will you attempt to establish a broad "brand" awareness and reputation in the community? If so, how? What is the purpose for starting the new church? Is the new church being founded to reach more lost people in a new geographic area/location? Is the new church being formed as a result of a church split? Is the church being started to revitalize a dying church? Is the church being started to allow a new campus or site of an existing church to be started? If so, for what purpose (e.g. alleviate overcrowding at the main campus, for the convenience of existing members, to reach new people, etc.)? Are there models to which you already have an affinity or bias? Most of us have a hard time breaking past paradigms. Are you coming out of an experience that will bias you to a particular model? Have you seen a specific model in practice that you feel God may be calling you to? What model best fits your experience and gifting? Are there specific models that will best fit the geographic area to which you are called or to the people group you will be reaching? Take some time to answer these questions as you consider which model fits your vision. Most models fit into one or more of the following categories: House/Micro Church Network Small (5-20 people) groups/cells form and multiply via a network of people meeting in homes. In some cases, the individual cells are connected in a larger network that meets together periodically in a large group setting. This relational model focuses on personal obedience, care and teaching through one-on-one and small group disciple-making. Groups are birthed through multiplication. This model requires very little funding. Launch Large This model is focused on gathering a large group of people for a worship gathering. It starts with a vocational lead planter, and possibly a staff team, gathering a launch team of 40-60 people. This launch team will commit to spreading the word about the church, serve on ministry teams to create worship environments, and support the church financially. These launch team members can come from sending/sponsor churches or through personal contact by the planter or staff team. In order to accomplish the goal of launching large, the new church will invest a significant amount of money and energy into staffing, marketing, equipment, facilities, etc, so it must be well-funded. This model is typical for suburban settings. Missional/Incarnational If church plants could be compared to kitchen appliances, the launch large model would be a microwave and this model would be the slow cooker. They both gather for public gatherings (although sometimes not every week), but instead of trying to launch large, this model launches slow. It focuses on building relationships and getting people into smaller groups where they can study God's word together and serve each other and their community. It's not focused on calling the community to their worship gathering, but infiltrating their community through service. Since this model takes a longer time to gather enough people to support any full-time staff members, the leaders need to start bi-vocationally. Satellite Campus (Multisite) An existing church opens new locations. The idea is for one church to have many meeting locations. Motives range from reaching more lost people to making more room at an existing location. The evolving multisite model is proving important in creating an entrepreneurial spirit of multiplication/replication within existing churches. Restart/Re-launch An existing struggling church decides to bury the old and plant a fresh new church. The restart may or may not be at a new location and may or may not be with the same leadership. The resources of many older, stagnant churches are a good way to bring new life to the community being served. Church Split Unfortunately, this model of "church planting" most often results from disunity. As a result, it is the most dangerous form of planting. A split typically occurs when competing groups conclude there is less energy required to split or "divorce" than to resolve differences and reconcile. The underlying factors causing the split often develop over years, only to explode in what seems like a spontaneous act. In many cases, the dysfunctional character traits of the old church carry forward to the new churches. Each of these models is unique, but they all have something to offer to the next model (perhaps with the exception of the church split). The decision of which model to employ should take into consideration the community context of the new church, the people it seeks to reach, and the wiring of the planter. It must also be bathed in prayer. | Clarify which church planting approach you will use. Clarify which church planting model you will use. This action is complete when the planter is able to clearly articulate his church planting approach and model. | <a href="https://www.rca.org/wp-content/uploads/2020/09/Sixteen-Ways-to-Plant-a-Church.pdf">Sixteen Ways to Plant a Church</a> by rca.org | 46 | 14 | 2015-02-03 05:00 | 2021-03-08 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content reformatted and validated --pb 2019-11-19 content updated --pb 2019-12-03 additional resources subsection added --pb 2021-03-08 hyperlink updated --pb
146 | 180 | 178 | Develop a preliminary budget for fundraising purposes | Identify fundraising requirements for recruiting prospective financial supporters. | You'll work up a formal budget in a subsequent PlanterPlan task. For now, you need to identify a very basic budget to determine a fundraising goal that you'll use with potential supporters. The budget should be simple, including only the major expense categories. In the launch large model, each of the following categories represent roughly 25% of the total expenses through launch: staffing marketing/outreach equipment administration/operations Percentage vary widely in other models. Expenses Where does all the money go? This is the question you have to ask. And soon have an answer for curious prospective donors. Money follows vision, so the type of church you plan to start significantly influences the money required to start. In a previous task, we discussed church planting models. As you might expect, micro churches require far less funding than launch large. In general, expenses through launch (pre-launch phase) can be grouped into the following categories: Staffing How much will you spend on staffing? It depends on how many staff will be hired, how much they will be paid, when they will be hired, and whether they are expected to raise any outside support. In a micro church, staffing expenses may be zero. In a multi-staff, launch large plant, staffing expenses could be well over $100,000 annually. Equipment Most new churches have a number of one-time expenses for equipment purchases. These include but are not limited to: a sound system, lighting, projectors, storage cabinets, children's supplies, Bibles, a trailer, etc. Depending on the quality and size, total equipment costs can range from zero to $80,000 or more. Unlike staffing expenses which are ongoing, most equipment purchases are one-time expenses up front. Marketing and Outreach Marketing and outreach are all about starting conversations with people in the community.You can no longer rely on one big marketing campaign just prior to launch to establish name recognition. You have to take a more balanced approach between outreach and marketing activities. A new church is ready for a big direct mail campaign only AFTER establishing broad name recognition in the community. Facilities Most new churches cannot afford to purchase a building (nor should they). Instead, they rent schools, movie theatres, or community centers. Sunday rent typically ranges from $12,000 to $60,000 per year for Sunday mornings. Additional facility costs could include rented office space. During the pre-launch phase, when the new church has not yet started weekly gatherings, facility costs will be much lower. Costs will be driven by the timing of when you start weekly worship gatherings. Operations Ongoing operations including ministry expenses, printing, copying, website, email, software, office supplies, insurance, phones, etc. | Develop an initial preliminary budget for fundraising purposes using the guidelines above. Use the total budget number as your goal for fundraising. This action is complete when you haves developed an initial budget to support your fundraising. |  | 46 | 14 | 2015-02-03 05:00 | 2019-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content reformatted --pb 2019-11-19 content updated --pb
147 | 228 | 183 | Set up supporter web page | Set up a simple initial/preliminary web page to communicate with outside supporters and to accept online donations. | By the time you get to the launch of your regular worship gatherings, your church plant website will have gone through several stages. This task walks you through the first stage. Note the other stages so you can transition intentionally instead of accidentally when the time comes. Your major website stages will take their cues from your changing audience. Whenever you're writing website content, always ask and remind yourself, "Who's my audience?" And you'll have to rewrite your content at least twice. Stage 1: Your Supporters Very early in your church planting process, you're going to need a web page to direct your supporters to. You probably only need a single page, so keep it simple. But a website will be really handy for accepting online donations as you raise funds. You may not have even named your church yet, so here are some options at this stage: Get a dedicated page on a supporting church or planting organization's site Use drag and drop website builder like <a href="https://www.squarespace.com/">SquareSpace</a>, <a href="https://www.weebly.com">Weebly</a>, <a href="https://mailchimp.com/features/website-builder/">MailChimp</a> or <a href="https://www.wix.com">Wix</a> that assigns you a subdomain (it'll usually look like mychurchplant.[nameofservice].com) Buy a temporary domain name to use for a year (like "thecheboyganproject.com") and host your own page Nobody is going to be stumbling onto your site through internet searches at this stage, so you don't have to worry too much about SEO (getting found). You'll send your supporters a direct, clickable link through email or text. Stage 2: Your Team As you network in the community and begin gathering a team, you're going to want a site to establish your credibility. At that point you will need to de-emphasize the 'money talk' and emphasize vision, community involvement, and recruitment. You'll write new content addressed not to the community at large, but to people that you're meeting personally. The subsequent PlanterPlan task <a href="/projects/project-tasks/[[project_id]]/all-tasks/1390">Publish simple 1-page website</a> will walk you through this. Stage 3: Your Community Several months before your grand opening of regular worship gatherings, you'll need to transition the website to its permanent audience: your community. That is covered in more detail in the subsequent PlanterPlan task <a href="/projects/project-tasks/[[project_id]]/all-tasks/584">Publish your website</a> . | Choose a publication path as described above. Determine initial content for web page. Design initial web page. If necessary, find someone to help. Publish initial page to the internet. This action is complete when the basic one-page website is up and functioning. |  | 43 | 28 | 2015-02-03 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template: standard Need Pat's review to determine which of these tools/sites to ditch (too old) and which new ones to add based on current technology.& -----ds 2017-09-15 content updated --pb 2017-09-26 content overhauled; Due in # of Days changed from 49 to 42 to coincide& with other fundraising activities --pb 2019-11-19 content updated --pb 2020-12-14 changed& title from "set up supporter website" --pb 2020-01-26 content updated --pb
148 | 696 | 699 | Purchase church management software | Select and purchase church management software to collaborate with your team, track important metrics, and communicate with people. | Whether it's done intentionally or accidentally, keeping ministry information to yourself creates a silo that prevents other staff and key volunteer leaders from being included in ministry. Instead of each leader having their own information silo, wouldn't it be great if there was a 'shared brain' where important information could be securely stored & shared? Enter Church Management Software (ChMS) A good ChMS platform is built to do that and much more: Compile a fuller picture of each person's life story and discipleship journey through: marking major life events recording prayer requests and private pastoral notes displaying a history of their involvement in various teams and groups Keep track of everyone's contact information Track giving history for year-end giving statements (and even facilitate online giving) Organizing and tracking small groups Create and manage volunteer serving schedules Standardize and reinforce repeatable people processes (like guest followup) Produce reports that reveal the church's effectiveness at accomplishing its mission A Collision Course As of 2020, ChMS platforms are well into a collision course with 2 other church software tools: online giving and mobile apps. It makes sense to consider even briefly where you might want to end up with these other two so that you can pick a ChMS that will be compatible. Power vs. Ease of Use The other big determining factor is choosing between power and simplicity. A more powerful ChMS comes with more features and, often, a level of complexity that requires more training and patience of your staff & volunteers. A simpler, easier-to-use system can be easier for your team to adopt, but may come with limitations that prevent it from doing some of the advanced things you really need it to. So choose between a complex system that risks not getting used and a simple system that risks frustrating you with its limitations. Top Picks Passion for Planting recommends the the following ChMS solutions: <a href="https://www.planningcenter.com/">Planning Center</a> - <a href="https://www.planningcenter.com/use-cases/church-planters">Click here to apply for Church Planter discount</a> <a href="https://pushpay.com/">Push Pay (formerly Church Community Builder)</a> <a href="https://get.tithe.ly/product/church-management">Tithe.ly ChMS (formerly Elvanto)</a> - an early 3-in-1 "collision-course" solution <a href="https://faithteams.com/">FaithTeams</a> <a href="https://go.churchteams.com">Church Teams</a> Others to consider include: <a href="https://www.acstechnologies.com">Realm</a> by ACS Technologies <a href="https://www.rockrms.com">Rock RMS</a> (open source, self-hosted) <a href="https://www.breezechms.com/">Breeze ChMS</a> Supplemental Software Here are a few other software solutions to consider that aren't a ChMS, but have specific functionality that may supplement your ChMS: <a href="https://textinchurch.com">Text in Church</a> (guest followup) <a href="https://churchmetrics.com">Church Metrics</a> | Determine your feature requirements. Research various ChMS solutions; consider sitting through sales demos and/or test-driving software. Get recommendations from other church plants and friends in ministry. Sign up for your top ChMS choice. This action is complete when you've purchased a church management software solution. |  | 74 | 30 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-12-26 content updated --pb 2018-11-16 content updated to match Greg Curtis' content in our strategy template --pb 2012-12-02 content updated --pb 2020-12-16 changed Due in # Days from 137& to 155& & Duration from 7 to 14& --pb&
149 | 957 | 183 | Set up online giving | Sign up for an online giving solution so that outside supporters and local team members can give electronically. | Paper checks may not completely go away any time soon, but having an electronic giving option for your church is no longer negotiable. Online giving solutions come in many different shapes and sizes designed to meet the needs of all types of churches. Each solution has pros and cons for a church plant. Pricing Each provider will charge you with some combination of the following: Transaction rate - every vendor will charge some percentage of the donation; rates may differ between credit, debit & ACH (bank account) options Transaction fee - many providers charge a percentage plus 25&cent; or 40&cent; per transaction; again, these may differ between credit, debit & ACH Set up fee - only a few vendors charge one Monthly fee - some vendors offer you lower transaction rates & fees offset by a monthly fee Annual or Compliance fees - some vendors also charge fees annually A Collision Course As of 2020, church management software (ChMS) platforms have begun the collision with both online giving and mobile apps. Soon you'll picking just one provider that does all 3 in an integrated fashion. But there are still some options, so it makes sense to consider even briefly how these will all line up so you can pick solutions that play nice together. Mobile App Provider In-House Options Think long game. Many church plants don't need a church app prior to launch, but knowing your options could line you up to make that easy/er someday. Top picks include: <a href="https://www.planningcenter.com/church-center">Planning Center Church App</a> <a href="https://www.subsplash.com/giving">Subsplash</a> <a href="https://aware3.com/pricing/">Aware3</a> <a href="https://get.tithe.ly/product/church-giving">Tithe.ly</a> ChMS Compatible Options These are the respective providers that integrate with the top ChMS platforms: Church Community Builder (now owned by PushPay) full integration option: <a href="https://pushpay.com/">PushPay</a> options that sync: <a href="https://get.tithe.ly">Tithe.ly</a>, <a href="https://aware3.com/ccb/?utm_source=ccb&utm_medium=uri&utm_campaign=ccbcom">Aware3</a>, <a href="https://www.thechurchapp.org/ccb">Subsplash</a>, <a href="https://gyve.com/">Gyve</a>, <a href="https://www.securegive.com">SecureGive</a> Planning Center Online full integration option: <a href="https://www.planningcenter.com/giving">Stripe</a> options that sync: <a href="https://get.tithe.ly">Tithe.ly</a>, <a href="https://aware3.com/pricing/">Aware3</a>, <a href="https://www.kindrid.com/">Kindrid*</a>, <a href="https://pushpay.com/">PushPay</a> Tithely CMS (formerly Elvanto ) full integration option: <a href="https://get.tithe.ly">Tithe.ly Giving</a> options that sync: <a href="https://www.continuetogive.com">Continue to Give</a>, <a href="https://www.mogiv.com">MoGiv*</a>, <a href="https://pushpay.com">PushPay</a> Stand Alone Options There are truly too many to list. The following options may or may not play nice with your other software platforms: <a href="https://www.onlinegiving.org/">OnlineGiving.org</a> <a href="https://www.paypal.com/us/non-profit/fundraising/fundraising-online">PayPal Donations</a> <a href="https://www.authorize.net/">Authorize.net</a> *These providers have been purchased by the conglomerate <a href="https://www.ministrybrands.com/our-brands/">Ministry Brands</a>: Kindrid EasyTithe eGiving SimpleGive Giving Kiosk MoGiv EFT Plus HaloPays | Ask around of other church plants and friends in ministry what they think of their online giving. Consider which platforms will line up best with your church management software. Consider which platforms will line up best with your long-range mobile app development plans. Purchase and set up the giving solution that is the best match. Share online giving options with your launch team and financial supporters. This task is complete when the first gift has been given through the new online giving platform. |  | 74 | 14 | 2016-09-19 04:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: New Milestone 2018-08-21 name tweaked --pb 2019-10-14 content rewritten --pb
150 | 189 | 183 | Develop promotional materials for recruiting partners | Develop high-quality, first-touch promotional materials that you will use to recruit financial supporters and partners. | Create a fundraising packet or kit that you will send to potential partners. Your packet should include basic information about the church plant as well as information about you, the planter. Be strategic about what you stuff in the envelope. Will you use?: a letter a homemade brochure a professionally printed brochure a commitment card (this is discouraged; read more in the task Develop a Donor Commitment Card ) something tactile (see below) Especially for churches, organizations and other high-capacity givers, consider mailing something 3-dimensional (more than just printed paper). It will significantly increase the 'open rate' and may lead to more conversations than otherwise. For example, use a padded envelope or small box and include something your target community is famous for. Or include something that demonstrates the need for more churches in your region. Record a video and load it onto an inexpensive thumb drive. Even a simple ink pen in an envelope will get the recipient's attention. Get creative! Remember though that the point of a mailing is to set up a meeting or call with the prospect, not get them to make a decision on the spot with no conversation. They need to hear your heart. These packets just buy that opportunity. If you have children at home, having them help assemble the packets for mailing can be a great way to involve them in the early stages of the church plant! | Decide what you'll put into each fundraising packet. Write the content for any print pieces and get them printed. Design and otherwise order creative elements you'll include. Assemble the fundraising packets. This action is complete when several packets are assembled and ready to send out. |  | 46 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated --pb 2018-11-02 content updated --pb 2019-12-11 content validated --pb 2020-12-14 changed Due in # Days from 42& to 43 --pb&
151 | 190 | 183 | Develop a donor Commitment Card for your maybes | Design and print a commitment card to leave with potential donors after you've met with them in person or in large groups. | A commitment card is a simple tool that is widely used by nonprofits as they solicit donations. You've probably seen them in nonprofit solicitations in the mail. They can be printed professionally or on a home computer. Don't Lead with It Don't mail out a commitment card. Fundraising is about relationships first, not transactions. Whenever possible, make the ask in person. If you start with the commitment card, it potentially sends all kinds of negative messages: I'm too afraid to ask you myself I don't believe in the vision enough to be bothered I'm more interested in your money There's just too many of you to ask (you're just a number) etc. This also means don't go into a meeting and hand out a commitment card first thing. They'll be reading the card instead of listening to you. And again, it could send the wrong message. Leave your prospects with a commitment card only if they are unable or unwilling to commit to your while you're still together. Then set an expectation for when you'll follow up with them to get their commitment. Do's Include the following to increase your commitment card's effectiveness: Commitment language stated in the first person; something like, "As God provides, I commit to:" or "For the next 2 years I will:" White space - leave at least 33% or your card as 'white space' and it will be much easier to read Spaces to fill in their contact info Your phone number and email address so that they can contact you A short website address (vanity URL) where they can go to give online Don'ts Here are some common mistakes and poor design that decrease effectiveness: Include a prayer commitment option (don't give them the easy out; make them tell you 'no') Use the phrase "One-Time Gift" instead of "Up Front Gift" Give them a crazy short fill-in line for their email address - it won't fit Give them a crazy long website address for online giving (like www.mychurch.onlinegivingprovider.com/246810/church/secure-portal.htm) Fill up every square inch with text Make it hard or confusing to get the commitment back to you | Have a graphic designer draft your cards, or do it yourself if you have to. Have the cards professionally printed or print them yourself and cut them apart. This action is complete when the cards are ready to be handed out or shared online in digital form to potential donors. | <a href="/resources/item/387">Donor Commitment Card Template</a> (half page, Apple Pages format) <a href="/resources/item/386">Donor Commitment Card Template</a> (third page, Apple Pages format) | 46 | 14 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated --pb 2018-11-02 content updated --pb 2019-08-09 additional resources subsection created --pb 2019-11-19 content updated --pb 2020-12-14 changed Due in # Days from 42& to 46 --pb&
152 | 192 | 183 | Initiate contact with potential partners | Open the lines of communication with potential support partners. | You need to get past any psychological or emotional barriers and make initial contact with everyone on your potential partners list. Don't Spray and Pray Send letters to everyone on the list in smaller batches so you can follow up in a reasonable amount of time. If you mail 200 letters at once but can only call 40 people a week, it will be as much as 5 weeks (more than a month) before the last donors hear from you! Better to create a rhythm of mailing 40 letters each week and calling on the 40 from the previous week's mailing. Decide who on the list is a high-capacity donor to meet with in person. Follow up the letter to those donors with a request for a meeting to share the vision God is calling him to. Remember that money follows vision and relationship, not need. | Practice pitching your vision at least 25 times before getting in any situation where you'll need to pitch it to a potential support partner. Send out the first communication piece to the first batch of prospects following the instructions in the subsequent child task. Schedule in-person meetings following the instructions in the subsequent child task. This action is complete when you have sent a support letter to at least the first 40 prospects on your potential partner list. |  | 71 | 21 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated --pb 2019-11-19 content updated --pb 2020-12-14 changed Due in # Days from 49& to 71& & Duration from 14& to 21& --pb&
153 | 193 | 192 | Send initial letter to potential partners | Let the people in your life know what God has been up to, what He is calling you to, and ask them to partner with you in this new endeavor. | No one wants to be called out of the blue and be asked for money. Open the lines of communication with each of your potential supporters by sending out an engaging letter that tells the story of the plant, casts the vision, and invites them to participate. The "letter" in this case could be an actual printed letter (old school still works), a direct message on social media, etc. The goal of the letter should be to set up a phone call, whose goal should be to set up an in-person meeting. "The biggest checks come from the smallest rooms." - Phil Ling of <a href="https://thegivingchurch.com">thegivingchurch.com</a> Print Letter Considerations Things to be sure to include in or with a printed letter: A picture of your family and the church logo (if it has already been designed) The church's tag line (if it has been developed) Your phone number, mailing address, and email address so that they can contact you The expectation that you'll be following up with them Passion for Planting has collected <a href="https://church-planting.net/pp_addendums/Fundraising%20Letters.htm">Sample Letters</a> for you to review. Here are some production & design ideas to consider: Save the commitment card for after you've spoken with them over the phone or in person. You'll get a much higher commitment rate than the old 'spray and pray' method. Keep it to the front of one page. If you absolutely have too much to say, use legal size paper, but constrain yourself to one side. Use a design template in whatever publishing software you are using. Don't try to reinvent the wheel; just pick a style that reflects you and/or your plant. Print in color. It really does make a difference. Use the mail merge feature of the publishing software you are using to personalize the greeting line of each letter with the recipient's name. You can also use mail merge to print right onto the envelopes (preferable), or onto address labels that you can affix to the envelopes (acceptable). If you don't want to fold the letters by hand, use a folding machine at a local church or business services store. | Draft the support letter or direct message. Have at least two other people read it for errors and feedback. Print the letter or send the direct message. Further for snail mail: Address the envelopes. Fold the letters and insert into each outgoing envelope. Affix proper postage and drop them to the postal service. This action is complete when you have sent out the first several letters. |  | 64 | 14 | 2015-02-03 05:00 | 2019-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated --pb 2019-12-11 content updated --pb
154 | 194 | 192 | Schedule meetings with potential partners | Honor high-capacity donors by meeting with them in person and building your relationship. | Financial supporters give when they are excited about a vision and the chance to participate in what God is doing. For many, it is part of their Kingdom ministry and a great joy to provide financially for God's work. Meet with people from your potential support partner list that you know have the means to participate financially. Don't go to them asking for money, but casting your vision and inviting them to join you in this Kingdom effort. Get Someone Else to Make Your Calls Seriously. The point of the call is to book a face-to-face meeting. If you make the call yourself, they may tell you, "Just tell me what this is all about." If your spouse, friend or family member calls to book the appointment, you won't step on this landmine. If at all possible, have someone else make the calls and schedule your meetings. Don't forget that your helper will need to have access to your calendar. | Call each high-capacity individual or group very shortly after you know they will have received your initial contact. Schedule an in-person meeting to tell your story and cast the vision God is calling you to. Put each meeting on the calendar immediately to avoid schedule conflicts and the embarrassment of having to reschedule. Make travel arrangements well in advance of the trip to get the best airfares, etc... Show up for the meeting and cast your vision. Remember that money follows vision and relationship, not need. This action is complete when you have scheduled face-to-face meetings with the high-capacity supporters on your contact list. |  | 71 | 14 | 2015-02-03 05:00 | 2019-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated --pb 2019-11-19 content updated --pb
155 | 195 | 183 | Formalize partner commitments | Solidify your relationship and everyone's expectations by formalizing financial commitments. | Especially with support organizations such as church planting groups, denominations or other churches, it may take months of cultivation before a financial commitment is made. There will be lots of communication and intentions in the mean time, but at some point you will want (and should expect) a firm decision. You cannot take good intentions to the bank. And the timing of the gift is important for you to know, too. If they commit $10,000, there is a huge difference between $1,000 per quarter and $10,000 up front. It's reasonable for you to ask for specifics once they've made a commitment. | Continue to follow up with each support organization lead. Do not give up until you get a firm answer one way or the other. During each interaction, be sure to ask when you can expect a decision and when you should follow up. Be sure to ask for referrals and leads to other organizations that you should approach for support. This action is complete when you have received a firm 'yes' or 'no' from each support organization you have been pursuing. |  | 74 | 42 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated --pb 2019-11-19 content updated --pb 2020-12-14 changed Due in # Days from 60& to 74& & Duration from 30& to 42& --pb
156 | 196 | 183 | Create a schedule for sending ongoing communication to potential partners | Keep lines of communication open with every one of your potential supporters whether they have committed to some kind of support or not. | Perhaps the worst things you can do in the support raising process is to send one support letter and then never follow up or send any other communication. You never know when the supporter's circumstances or heart may change. There will be several recipients who are waiting to see if you are serious and willing to follow through. And we could share countless stories of supporters who started sending in support only after having received letters for 4, 5, and 6 months. You have to be disciplined about sending out communication. It will be easy to put this on the back burner when crunched for time. Relationships with financial supporters are no less important than relationships you develop with the locals. Plan on spending about one full work day each month managing your fundraising process. Consider this: in terms of return on time invested, spending one day a month on support raising can net several thousand dollars for the ministry each month. That support enables all of the rest of the ministry that happens on the other days of the month. Time well spent. | Review your fundraising strategy. Look at the how frequently you have planned to use each communication method. For each communication method, schedule time on your calendar for accomplishing each. For example, if you have committed to send weekly emails to supporters, schedule a recurring appointment each week on your calendar to accomplish this. This action is complete when you have scheduled time to create and distribute each method of communication from the fundraising strategy. | <a href="https://www.thegospelcoalition.org/article/changed-mind-fundraising-church-plant/">Why I Changed My Mind About Fundraising for Our Church Plant</a> on GospelCoalition.org | 46 | 7 | 2015-02-03 05:00 | 2019-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content validated --pb 2019-04-23 additional resources subsection added --pb 2019-11-19 content updated --pb
157 | 197 | 183 | Add financial partners to your group distribution list | Keep financial partners informed about your church and inspired with stories of life change. | Good communication is key to keeping financial supporters included and connected. They are your co-laborers in the work of the new church. Keeping them out of the loop or just plain ignoring them doesn't honor their sacrifice and willingness to buy in to the vision. Earlier, you chose a communication channel for your intercessory prayer team. Decide whether to use that same tool or something else to keep your supporters in the loop. Options abound: group email group SMS social media (private groups) group messaging apps printed letters etc. | Compile the list of all your financial supporters and make sure you have current contact information for each. Import them into your distribution list (Mailchimp, ConstantContact, group SMS, etc.). Optional: segment the list by flagging the financial supporters. That way they will be part of the overall list, but you will also be able to send custom emails to just your supporters should the need arise. This action is complete when each financial supporter is uploaded or input into your group communication channel. |  | 61 | 7 | 2015-02-03 05:00 | 2019-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated --pb 2019-11-19 content updated --pb
158 | 198 | 183 | Establish an initial donor management system for fundraising | Set up a clear, secure, and reliable donations receipt process to honor your donors and comply with IRS requirements. | For legal reasons and for accountability, you absolutely must have a clear, secure, and reliable donations receipt process. This includes keeping documentation of who donated what money or goods to the church and what, if anything, they received in return. To keep the donations coming in, you have to accurately track donations, keep donors informed of church status, and to report the donations (as appropriate) to the IRS. Determine how donations will be tracked and followed up. Two Main Options Sponsor: The fast and easy way is to piggyback on another organization's systems. Often church planting groups or mother churches will handle this process until the church has been launched. In-House: If that's not an option, you'll have to process and track everything in-house. That requires the church to have its own bank account, which in turns requires the church to be legally established in its state. Reference the Milestone that covers legal issues for further help on these steps. More Than Just Receipts Once again, fundraising is about relationships. It's important to keep track of giving so you can provide giving statements, but donor management should be about way more than that. A good donor management system will help you keep track of when you contacted each donor last, what they've committed, and space for important notes like birthdays, spouse's and children's names, etc. The long game for your donor tracking will certainly be some kind of church management software (ChMS). Today's ChMS apps do all of the above, so Passion for Planting recommends getting that started sooner rather than later (see subsequent PlanterPlan task for recommendations). At the very least, keep everything together in one place, like a doc or spreadsheet. | Decide whether to piggyback or process in-house. If doing it in-house, choose which software to use. Determine what additional records/copies should be maintained. This action is complete when you have implemented the donor relationship management system. |  | 61 | 14 | 2000-01-01 05:00 | 2019-12-11 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated --pb 2018-05-07 added& google& doc template version --pb 2019-11-19 content updated --pb
159 | 200 | 1312 | Milestone: Establish Budget and Financial Systems | Establish key processes that make up a solid financial system. | We have to be above reproach in how we handle our finances - everything from bookkeeping to what we spend our money on. There should not be even the slightest hint of impropriety. As clearly demonstrated in the Bible, Satan does some of his best work through sex and money. Even the smallest honest slip with our finances has the potential for scandal. For legal and for accountability reasons, the church must have clear, secure, and reliable financial processes. This Milestone covers the following: Bookkeeping plans IRS tax regulations Staff payroll Financial software Accounting processes Donor management system Budgeting |  |  | 109 | 94 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content udpated& --pb 2019-12-12 content updated --pb 2020-12-16 changed Duration from 40& to 45& --pb&
160 | 201 | 200 | Read this budget and financial systems overview | Understand the key processes that make up a solid financial system. | Financial controls in the church are aimed at preventing two types of problems: Actual loss of proper control of finances Losing money, improper disclosure of personal information, theft, violation of IRS or other legal requirements, writing checks with insufficient funds Perception of loss of adequate control of finances Individuals carrying weekly offering through the lobby in a see-through plastic bag, offering left in an unlocked car, church staff renting luxury sports car rather than economy car Avoiding both of these types of problems is very important. The easiest way to get audited/investigated by the IRS is a public scandal involving money. Worst case scenario, a church can lose its 501c3 status, be fined, and prosecuted. A lack of confidence by members in the church's ability to manage finances will impact financial giving. At a minimum, the new church's financial system should include: A checking account Ongoing reconciliation of monthly account statements Financial accounting including processing and tracking accounts payable (expenses) and accounts receivable (income) (i.e. writing checks and making deposits) An accountable reimbursement process Generating ongoing financial reports including cash flow and budget variance Payroll process for staff (including filing required reports and paying all required taxes) Maintaining financial records and files Keeping track of all donations and providing tax receipts Receiving, counting, tracking and reporting weekly Tithes and Offerings Each of these processes is covered by a separate PlanterPlan action. | Read and understand this action. The development of the processes listed above is covered in subsequent PlanterPlan actions. This action is complete once you have read the entirety of this task. | Benevolence Policy and Request Form Template (<a href="../../../resources/item/396">ms word</a>) | 37 | 1 | 2015-02-03 05:00 | 2024-08-21 15:29 | 2000-01-01 05:00 | template: standard 2017-05-26 content updated --pb 2019-12-12 content updated --pb 2020-12-14 changed Due in # Days from 42& to 37& & Duration from 7 to 1& --pb&
161 | 202 | 200 | Call your coach about setting up financial systems | Open a conversation with your coach about what needs to be in place for properly handling church finances. | If you have already been provided bookkeeping by a sponsoring church or church planting network, you don't need to call your coach about this. If you haven't, initiate a call to your coach about your own arrangements for a bookkeeper. Sample issues to process with your coach: Lessons the coach learned the hard way How to insure the integrity of church finances Typical financial system weak spots How to work with a virtual bookkeeper How to recruit a finance team | This action is complete when you have called your coach about setting up financial systems. |  | 46 | 7 | 2015-02-03 05:00 | 2019-12-12 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content validated --pb 2017-05-30 audience changed to coach --pb 2019-12-12 content updated --pb &
162 | 203 | 200 | Read IRS Tax Publication for Churches | Gain a better understanding of the benefits and responsibilities of churches under federal tax law. | This IRS publication covers: Tax-Exempt Status and what may jeopardize it Employment tax Special rules for compensation of ministers Record keeping requirements Tax return filing requirements Charitable contributions - substantiating and disclosing IRS's authority to audit a church | Download the free <a href="https://www.irs.gov/pub/irs-pdf/p1828.pdf">IRS Publication 1828</a>: Tax Guide for Churches and Religious Organizations Read the publication Make any necessary changes to your financial processes based on what you learned This action is complete once the planter read IRS Publication 1828: Tax Guide for Church and Religious Organizations . |  | 43 | 7 | 2015-02-03 05:00 | 2019-12-12 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content and link validated --pb 2019-12-12 content and link validated --pb
163 | 204 | 200 | Buy the Church and Clergy Tax Guide by Richard Hammar | Have an easy-to-understand reference book on hand that covers church and clergy tax concerns. | This guide will help you: Determine and properly record pastoral housing allowances Understand self-employment and social security taxes ...and much more. | Purchase this book online or from a local bookstore. Read the Table of Contents to get an overview of the Guide. Keep the Guide for reference in the church office. This action is complete once you have obtained a reference copy of <a href="https://store.churchlawandtax.com/2023-church-clergy-tax-guide-book/">The Church and Clergy Tax Guide</a> by Richard Hammar. |  | 43 | 7 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2019-12-12 content and link validated --pb 2022-11-21 update link --sc
164 | 223 | 200 | Develop a church plant budget | Develop an income and spending plan (budget) to focus and prioritize expenses, and to support your fundraising efforts. | A budget is a plan for spending money to accomplish God's will. The process forces you to choose priorities and "put your money where your mouth is". You'll quickly discover that a budget is really a vision document. Consider Theology Before you sit down to hammer out the budget, take a moment to be honest about your attitude(s) toward money. How you handle money and attitudes you've developed are rooted in your theology. Or at least, good theology and an honest conversation with Jesus can correct a broken relationship with money. One of the most dangerous attitudes in the church budgeting process is a scarcity mindset. You may not initially know where the money is coming from, but you can't take a posture of protection and still plant a healthy church. Of course, you still want to make wise decisions and not waste money on frivolous spending. But creating a budget based on the vision God is giving you will stretch your faith. And it will often result in your getting a front row seat to God's miraculous provision. Common Mistakes Here are some mistakes that happen a lot in the church plant budgeting process: vague time frames not including income projections not considering cash flow confusing recurring expenses and one-time startup costs Fiscal Year When does your "first year" start? When you move on site? When you come on payroll? January 1 of any given year? Maybe when you launch worship gatherings? Whether you call it a fiscal year or not, you'll have one. Being clear on when it starts each year removes any vagueness. Your budget spreadsheet will have 12 columns for each fiscal year. For simplicity, Passion for Planting recommends using the calendar year as your fiscal year. So your 12 columns run from January to December. But maybe you want your fiscal year to line up with the anniversary of the launch of your worship gatherings. For instance, if you launch your worship gatherings in September, then your 12 columns will run from September to August for each budget year. Income A budget without projected income is just a spending plan. Where is the money coming from? As you hammer out the budget, even if you don't know precisely who will be giving how much, you can make some prayerful estimates. First, break your income into categories or streams of income. Commonly those will be outside support and local giving. You may want to split outside support into two categories: organizations and individuals. Then you can include commitments you have received. And you can enter some local giving estimates based on per capita giving and projected attendance figures. Solvency After your first pass at the budget, verify that your total expenses each year are less than or equal to your total income each year. For example, if your expenses for next calendar year are $250k but your projected income is only $200k, you're headed for a train wreck. Cash Flow Having one column for each year of your budget is very handy for summaries and reports. But if you never consider the timing of the income compared to when you need to spend it, you'll be sorry. You can't spend the money until it comes in. An annual budget figure presumes that your income and expenses will each be divided by 12 and spread evenly across the year. That's not usually how it happens. If you have a donor that's going to write you a check for $50k to cover your equipment but not until September , you probably can't buy the equipment in May. | Download Passion for Planting's Church Plant Budget Worksheet Template (<a href="/resources/item/25">MS Excel</a> or <a href="/resources/item/366">Google Sheet</a>) or develop your own format. Follow the instructions in the file: fill in assumed dates & dollar amounts tweak income & expense figures use fundraising commitments (not goals) Double-check the cash flow on the bottom line; make sure there are no negative bank balance projections Submit the finalized budget to your Management Team or oversight. This action is complete when the budget has been approved by the Management Team or appropriate oversight. | <a href="/resources/item/22">Sample Church Plant Budget</a> by Passion for Planting <a href="https://www.churchplantingtactics.com/create-a-church-plant-budget/">How to Create a Church Plant Budget</a> on churchplantingtactics.com <a href="https://www.churchplantingtactics.com/how-to-review-a-church-plant-budget/">How to Review a Church Plant Budget</a> on churchplantingtactics.com | 50 | 21 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-30 contents & resource links updated --pb 2019-12-12 content updated --pb 2020-12-14 changed Due in # Days from 75& to 50 --pb&
165 | 349 | 200 | Open a church checking account | Open a church checking account to transact all of the church's income and expenses. | Find a bank that has convenient locations in your community. You may have to stop in from time to time and your team will be dropping deposit bags after worship gatherings. Some banks still offer free nonprofit accounts, but some banks have seen the high maintenance and low balances associated with nonprofits and don't offer them any more. Most banks still offer accounts where the fees can be waived by maintaining minimum balances. Shop around for a bank that offers accounts that meet your needs. If you're hiring a virtual church bookkeeper outside of your area, consider shopping for a bank that also has a branch near them. They may need to stop in for customer service support as well. Opening a church bank account is a little different than opening a personal account. With the ever-increasing anti-fraud and anti-terrorism regulations, the bank will be concerned about: Whether your corporation is a real entity or a fraudulent front company The physical location of the corporation Whether your corporation is truly a tax-exempt nonprofit Who the legitimate authorized signers are for the account Whether those authorized signers have legitimate identification or are impostors Why your bookkeeper is in another state To satisfy their concerns, take with you all of the following when you go to open the account: Your approved Articles of Incorporation and Certificate of Incorporation The printed EIN issuance letter from the Feds The physical and mailing addresses of your church Corporate meeting minutes that include a resolution to open an account with that bank specifically, and with the authorized signers named The authorized signers themselves - make sure they each have 2 forms of ID A list of the names & addresses of each Board Member A list of the names & addresses of the chief corporate officers: president, secretary & treasurer An opening deposit IMPORTANT : whenever possible, the church planter and his relatives should not be signers on the church accounts. This also means that they cannot have a debit card that accesses the church account, either. It's not illegal or immoral for the planter to be a signer, but it protects the planter from accusation and suspicion, as well as unnecessary administrative duties. Lastly, don't underestimate the value of establishing a working relationship with the banker and/or branch manager, both for the church's sake and as an evangelistic opportunity. | Determine which bank provides the best locations and features. Find out what documentation they require to open nonprofit corporation account. Open a checking account in the church name. This action is complete when the church checking account has been opened. |  | 67 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-25 content updated --pb 2018-07-13 content updated --pb 2019-12-12 content updated --pb 2020-12-14 changed Due in # Days from 140& to 58& & Duration from 14& to 7& --pb&
166 | 1299 | 200 | Set up payroll for staff | Take care of all the legal responsibilities associated with paying staff. | As a brand new, independent legal entity, you get the dubious privilege of creating entire Human Resource (HR) systems from scratch, including everything that has to be done to hire staff. The subsequent child tasks will walk you step-by-step through these major requirements: Completing hiring paperwork Signing up for payroll processing Getting tax withholding accounts opened Getting workers' comp insurance (if applicable) The church's employees depend on the church getting all of this right. And the church depends on getting it right to avoid very real fines and penalties. This is too important to get wrong. | Work through each of the subtasks that follow. Process the first payroll. This action is complete when employees have received their first payroll. |  | 234 | 212 | 2019-11-01 04:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: 2020-01-24 content updated --pb
167 | 438 | 1299 | Complete hiring paperwork for staff | Comply with government requirements by completing paperwork for each employee hired. | The IRS and other government departments require certain forms to be completed for each employee on staff. These need to be completed within 48 hours of the employee's first day of work . At a minimum, complete and file the following: IRS Form I-9 IRS Form W4 withholding election State withholding election form (as applicable) You may also want to get from each pastoral employee: Housing Allowance designation request (be sure to get copies of ordination paperwork) Medical Allowance designation request A copy of their Exemption from Social Security approval letter if they've opted out | Go online to get most recent versions of the 3 government forms identified above. Complete each with the new employee within 48 hours of their first day of work. File the withholding forms in the employee's personnel file. File the I-9 in the common folder where all employees' I-9s are filed. This action is complete when you have completed and filed important government forms for each new employee. | <a href="https://accupay.com/new-hire-payroll-forms/">New Hire Payroll Forms</a> on Accupay.com <a href="https://www.churchplantingtactics.com/free-church-employee-onboarding-checklist/">Free Church Employee Onboarding Checklist</a> by churchplantingtactics.com | 58 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-11-10 content scrubbed of HTML& formatting baggage and validated --pb 2018-08-23 additional resources subsection added --pb& 2019-12-23 content updated and links verified --pb 2020-12-14 changed Due in # Days from 84& to 135& --pb
168 | 206 | 1299 | Sign up for payroll processing | Make sure staff get paid and all the taxes are properly withheld and filed. | Churches have to be very careful in setting up payroll for their employees since there are four different types of workers. Each type is processed differently. Many churches incorrectly process payroll. Kinds of Workers Churches can have four types of workers: Category 1 Regular non-minister employees subject to all taxes includes FICA (social security and Medicare). Examples include church secretaries and custodians. Employees can be either hourly or salaried. Category 2 Ministers subject to SEPA ("opted in" to self-employment taxes, the equivalent of social security and Medicare). Ministers are also eligible for a housing allowance. See definition of ministers below. Employees are typically salaried. Category 3 Ministers exempt from SEPA ("opted out", having filed form 4361 with the IRS and received approval letter to be exempt from these taxes). Also eligible for a housing allowance. See definition of ministers below. Employees are typically salaried. Category 4 Independent contractor receiving a 1099 tax statement (these self-employed contractors have no taxes withheld as they are responsible for filing their own taxes). Examples include graphic designers, painters, roofers, etc. In general, independent contractors are paid for a finished product. They do not actually work under the management control of the church. Rarely are ministers considered category 4 self-employed employees (not to be confused by the fact that category 2 and 3 ministers are considered by the IRS to be self-employed only for social security purposes). Payroll Processing Options You have several options for setting up a payroll system: Provided by Sponsoring or Supporting Organization One of your sponsoring or supporting organizations may be willing to process your payroll in their system. Ask around to find out. Outsourced using an full-service payroll processor. The advantage is that they take care of all administrative requirements including filing taxes, reporting new employees, etc. Be sure to choose a payroll processor that specializes in church payroll, such as <a href="https://www.ministryworks.com/">MinistryWorks</a>, <a href="https://simplifychurch.com/church-payroll/">Simplify Church</a>, <a href="https://www.ministryadvantage.net/payroll/">Ministry Advantage</a> or similar. In-house using a manual process. Your team manages payroll on the church's computer and administers pay locally. Passion for Planting can help set up the necessary files and show you how to administer pay. Under this option, you'll have to: write monthly checks make monthly federal payroll tax deposits send monthly state payroll taxes (as applicable) file quarterly 941 forms issue year end W2 and W3 forms and file year end state tax forms. Although payroll is straightforward once it is understood, it can be a bit intimidating to learn (especially with housing allowance, social security exemptions, etc.). This option saves money but puts all the responsibility on the church. In-house processing with outsourced administration. There are some services (e.g. Quicken, Costco Member Services, Gusto, etc), that offer semi-automated payroll processing. You still processes the payroll locally but most of the administration of filing required taxes, etc. is automated. It is Passion for Planting's strong recommendation that church plants outsource payroll processing using one of the first two options. At the very least, a pastor should NEVER process his own payroll. | Determine which payroll method you're going to use. Set up your payroll processes. This action is complete when you have processed the first payroll. | <a href="/resources/item/205">Payroll Explanation</a> <a href="https://www.workcompone.com/employee-or-independent-contractor">Employee or Independent Contractor? 10 Ways to Tell</a> on workcompone.com | 58 | 14 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content updated & resource link pointed to library, though& resource itself has not yet been updated --pb 2018-08-21 tweaked title --pb 2019-01-14 updated payroll vendors --pb 2019-11-20 content updated --pb 2020-12-14 changed Duration from 21& to 14& --pb&
169 | 339 | 1299 | Get a state employer's withholding number | Establish an employer withholding account with your state. | A state tax withholding number is similar to a Federal Employer Identification Number (EIN). Each organization receives a unique number when they register with the state. Most states require that you register for a number. Churches are exempt in some states. A state tax withholding number is required in many states for any legal entity whether or not they end up paying any taxes. It will be required in any state where clergy are not exempted from state income tax, or if the church hires non-pastoral staff, like an administrative assistant. Contact your state for specific instructions on registering for a tax withholding number. Try a searching on [name of state] employer withholding number . In most states, you can register and file online. If you are working with a Passion for Planting Project Manager, you will be getting significant custom support on this task. If not, follow the instructions below. | Obtain a state tax withholding application or go to your state's online application page. Complete the form with all required information. Submit the form. Record the Tax ID number in your corporate records book (see subsequent PlanterPlan action). This action is complete when you have filed the state tax withholding number in its corporate records. |  | 58 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-24 content updated --pb 2019-12-11 content updated --pb 2020-12-14 changed Due in # Days from 90& to 167 --pb&
170 | 350 | 1299 | Obtain Workers Compensation insurance | Bind a workers' comp insurance policy that covers each employee of the church in case they get hurt on the job. | Every employer must maintain workers' compensation insurance. Requirements vary slightly from state to state: most states require it for every employee, some only when you have, for instance, 3 or more employees. Investigate your state's requirements. The workers' compensation system has been around since the 1920s and is basically a trade-off between employers and employees. Employees are entitled to medical treatment for on-the-job injuries or illnesses and, in return, can't sue employers over those injuries. You get workers' comp insurance in one of 2 ways depending on your state: The state itself is the insurer (OH, ND, WA & WY) Buy your own insurance (all other states) For those other 46 states, we recommend shopping your own church insurance provider first. They've already written, or will soon write, your liability insurance policy (see PlanterPlan task Obtain church insurance policy ). It keeps things simple if it's all in one place. You can also get workers' comp insurance from independent agencies and carriers in your state. Try searching on [name of state] workers comp . | Determine if your church is required to carry workers' comp insurance. Determine where to purchase the insurance in your state. Shop two different providers, if available, to compare pricing. Purchase the insurance. File the policy in the Corporate Records Binder. This action is complete when a workers' compensation insurance policy has been bound and filed in the official corporate records. |  | 58 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-25 content updated --pb 2019-12-11 content updated --pb 2020-12-14 changed Due in # Days from 189& to 167& & Duration from 45& to 14& --pb& 2022-11-21 updated links --sc
171 | 209 | 200 | Identify or hire a bookkeeper/accountant | Formally engage a bookkeeper to process and track all of the church's financial transactions. | You have to have a bookkeeper to keep track of the church finances. Period. Common options include: Your church planting network provides one for you A sponsoring church is willing to keep your books for you (usually only for a season) A qualified volunteer from your church Hiring a local bookkeeping firm Hiring a virtual bookkeeper that specializes in church accounting To remain above reproach, this person really should not be the planter or anyone related to the planter by blood or marriage. A bookkeeper will perform the following functions for the church: Reconciling monthly bank account statements Processing and tracking accounts payable (expenses/writing checks) Processing and tracking accounts receivable (income/making deposits) Maintaining an accountable reimbursement process Generating ongoing financial reports including cash flow and budget variance Maintaining financial records and files Tracking Weekly Tithes and Offerings with donor management software Processing payroll for staff (including filing required reports and paying all required taxes) Consider these virtual church bookkeeping vendors: <a href="https://www.luke923ministries.org/bookkeeping-payroll">Luke 9:23 Ministries</a> <a href="https://belaysolutions.com">Belay</a> <a href="https://www.startchurch.com/services/bookkeeping">StartChurch</a> <a href="https://simplifychurch.com">Simplify Church</a> <a href="https://tenfoldbpo.org/">Ten Fold</a> <a href="https://churchaccountingservices.com/">Church Accounting Services</a> | Identify a bookkeeper through referral or research. Negotiate a reasonable fee for services. Contract with the bookkeeper to perform functions listed above. Maintain regular, open communication with the bookkeeper. This action is complete once you have contracted with a bookkeeper. |  | 64 | 14 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content & vendor links updated --pb 2019-12-12 content updated and links verified --pb 2022-09-16 removed recommendation hyperlink for Belay, added Luke 9:23 --pb
172 | 210 | 200 | Coaching Checkpoint: review and affirm bookkeeping plans | Make sure that the planter has engaged a competent and reliable bookkeeper to keep the church financial records in order and above reproach. | Once the planter has identified a bookkeeper, he will initiate a call to you, the coach, to review and affirm bookkeeping plans. | Reviews the planter's bookkeeping plans. Affirm that the plan is workable and accountable. This action is complete when you, the coach, have reviewed and affirmed the planter's bookkeeping plan. |  | 74 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content validated --pb 2019-12-12 content updated --pb 2020-12-14 changed Due in # Days from 63& to 74 --pb&
173 | 211 | 200 | Purchase and set up financial software | Keep an orderly account of church finances by purchasing and implementing a financial software solution. | Purchasing a financial software solution should be delayed until after you have identified your bookkeeper. Financial software solutions, being about the same, can be selected based on what the bookkeeper prefers. They will have expertise in one brand of software and you can often purchase a software license through them. When considering accounting software (such as <a href="https://quickbooks.intuit.com/">QuickBooks</a> and <a href="https://www.xero.com/us/">Xero</a>) in conjunction with the bookkeeper, consider the following factors: Initial or recurring costs of software Whether it is online - if you are using a virtual bookkeeper, insist on online software Whether the software will accommodate donation tracking and charitable giving statements Accounting Software vs. Church Management Software One wrinkle is that accounting software is typically a clumsy tool for donor management. Today's church management software (ChMS) solutions are specifically designed to track your donors' gifts along with their prayer requests, group participation, and a host of other important ministry information. See subsequent PlanterPlan task Implement church management software . Keep your someday ChMS in mind as you consider accounting software. Investigate whether the system integrates with your ChMS and which ChMS your bookkeeper has experience using for donor tracking. | Ask which software solution your bookkeeping uses. Determine if that solution will meet your requirements. If not, ask for and seek recommendations from other churches. Select and purchase an financial software solution. Do the initial set up of things like the chart of accounts . Train additional staff and/or necessary volunteers in the use of the system. This action is complete when the financial software is purchased and set up. | <a href="https://www.clergyfinancial.com/quickbooks-for-churches/">Quickbooks for Churches</a> from clergytaxnet.com | 64 | 14 | 2015-02-03 05:00 | 2019-12-12 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content & links updated --pb 2018-02-22 additional resources section added --pb 2019-12-12 content updated --pb
174 | 212 | 200 | Implement financial accounting processes | Set up solid, reliable accounting processes for the new church. | Accounting processes will keep all the money straight and reduce chances for people to steal or embezzle. The following specific processes are covered in detail in subtasks: Process for receiving, tracking and reporting donations Financial checks & balances, and cash counting Reimbursing expenses Keeping good records In addition to those, consider the following: Selling T-Shirts If you sell any goods or services, you are required to report that income to the IRS and your state tax agency. Check your state requirements for specifics. You may be subject to sales and use tax on these transactions. Church Credit Cards Some churches use church credit cards. If you do, pay them off every month. DO NOT USE A CREDIT CARD IF IT CAN'T BE PAID OFF EACH MONTH! Also, avoid cards that charge yearly fees. Credit cards do have several benefits if used properly: You write one check to pay your bills rather than many checks. You have a summary/record of all transactions via your monthly statement. Some charge companies give 'cash back' (like 2% of total purchases back) based on your total charges. It makes credits for returns and refunds easier to administer (if you write a check and then return a product, you have to deal with handling cash back). Where a charge card is used, users should be required to keep and submit receipts. You will need to implement a process for reconciling the charge bill each month. For example, you could have each staff member fill out a form documenting what each expenditure was for, its budget category and attaching the receipts. | Work through each of the subtasks. Coordinate setting up bullet-proof processes for each with your bookkeeper. This action is complete when you have a functioning financial accounting process. |  | 69 | 14 | 2015-02-03 05:00 | 2019-12-12 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content updated --pb 2019-12-12 content updated --pb
175 | 219 | 212 | Develop process for receiving, tracking and reporting donations | Set up a process for receiving, tracking and reporting tithes and other gifts so your donors can benefit from the tax deductibility of their gift. | Donations to the church are tax deductible for the donor. But only if they can prove they made the donation. Now that you've made your software decision, it's time to set up repeatable processes so that everyone involved can know what needs to get done, how it gets done, and who is responsible to do each part of the process. The basic processes you'll need to develop are: Receive donations (check PO Box, log in to online giving, etc.) Record donation amount, date, donor, etc. (see below) Get physical donations to the bank (walk it in, scan with app, etc.) Send donation receipts and thank you's Send mid-year and/or end of year giving statements Here is an excerpt from <a href="https://www.irs.gov/pub/irs-pdf/p1828.pdf">IRS Publication 1828</a> regarding tax deductible donations: Substantiation Rules A donor cannot claim a tax deduction for any single contribution of $250 or more unless the donor obtains a contemporaneous, written acknowledgment of the contribution from the recipient church or religious organization. A church or religious organization that does not acknowledge a contribution incurs no penalty; but without a written acknowledgment the donor cannot claim a tax deduction. Although it is a donor's responsibility to obtain a written acknowledgment, a church or religious organization can assist a donor by providing a timely, written statement containing the following information: Name of the church or religious organization, Date of the contribution, Amount of any cash contribution, Description (but not the value) of non-cash contributions, Statement that no goods or services were provided by the church or religious organization in return for the contribution, if that is the case, Description and good faith estimate of the value of goods or services, if any, that the church or religious organization provided in return for the contribution, and Statement that goods or services, if any, that a church or religious organization provided in return for the contribution consisted entirely of intangible religious benefits, if that was the case. The church or religious organization may either provide separate acknowledgments for each single contribution of $250 or more or one acknowledgment to substantiate several single contributions of $250 or more. Separate contributions are not aggregated for purposes of measuring the $250 threshold. | Decide how to use your chosen software to keep track of tax-deductible donations. Document how you're going to receive, track and report charitable contributions. This action is complete when you have tested your system by processing the first donation. |  | 69 | 7 | 2015-02-03 05:00 | 2022-02-08 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content update& --pb 2019-12-12 content updated --pb
176 | 213 | 212 | Put financial checks and balances in place | Develop expectations for financial checks/balances, including money counting policies, to ensure finances are properly handled. | As noted in a previous PlanterPlan action, financial controls in the church are aimed at preventing two types of problems: Actual loss of proper control of finances The perceived loss of adequate control of finances Avoiding both of these types of problems is very important. The easiest way to get audited/investigated by the IRS is a public scandal involving money. In the extreme, a church can lose its 501c3 status, be fined, and prosecuted. These specific areas need defined expectations: Processing of Weekly offerings (counting cash) Will the money be counted immediately after church and put in the bank's after hour depository on Sunday? Who will count? Who will record the check information to keep track of charitable contributions? Does the money always have to be controlled by two people? What will the money be stored in from the time it's collected until it is deposited? Independence Does the same person who counts or handles deposits also write the checks and maintain the check book or are these different people? Can one person sign checks or are two independent people required to sign checks? Financial Audits How often will independent audits be conducted? Who will conduct them? How will they be reported? Oversight Who will be responsible for overseeing the financial systems? Who oversees this person? Financial Reporting What financial reports will be required? How often? Who gets them? How do you verify that only budgeted and authorized expenses are being made? Credit Cards Who is authorized to use credit cards? How do you ensure only authorized expenses are being charged (i.e. how do you substantiate the expenses after the fact since this bypasses the normal process of having a treasurer write a check). Compensation Process Who determines compensation packages? Are they fair and equitable? Are appropriate forms being maintained? Are applicable taxes being paid in a timely manner? Reimbursement Accounting System Is the system being maintained as approved by the Board? Are appropriate records being maintained? Are expenses being substantiated? Petty Cash Does the church allow a cash fund to be maintained in the office for minor expenses (e.g. stamps, etc)? If so, how is it maintained? How are each expenditure substantiated? Who is authorized to use it? What permissions are required? | Using the list above as a guide, determine which specific areas require checks and balances. Write down expectations for each area. Write down policies/procedures for each of the above areas based on your defined expectations. This action is complete when all of the questions above have been answered and there are healthy, functioning checks and balances in practice. |  | 69 | 14 | 2015-02-03 05:00 | 2019-12-12 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content validated --pb 2019-12-12 content validated --pb
177 | 215 | 212 | Implement IRS-compliant reimbursement process | Establish a formal and disciplined process for reimbursing individuals and organizations to comply with IRS regulations. | The IRS permits organizations to maintain accountable reimbursement plans so that employees can be reimbursed for normal business expenses without being taxed on the income. The plan must be approved and formally implemented. If you don't get this right, your employees may have to count the reimbursements as income and pay taxes on it! And if you get it really wrong, the church could potentially lose its 501c3 nonprofit status. Here is the excerpt from <a href="https://www.irs.gov/pub/irs-pdf/p1828.pdf">IRS Publication 1828</a>, Tax Guide for Churches and Religious Organizations: "Payment of Employee Business Expenses A church or religious organization is treated like any other employer as far as the tax rules regarding employee business expenses. The rules differ depending upon whether the expenses are paid through an accountable or non-accountable plan, and these plans determine whether the payment for these expenses is included in the employee's income. Accountable Reimbursement Plan An arrangement that an employer establishes to reimburse or advance employee business expenses will be an accountable plan if it meets three requirements: (1) involves a business connection, (2) requires the employee to substantiate expenses incurred, and (3) requires the employee to return any excess amounts. Employees must provide the organization with sufficient information to identify the specific business nature of each expense and to substantiate each element of an expenditure. It is not sufficient for an employee to aggregate expenses into broad categories such as travel or to report expenses through the use of non-descriptive terms such as miscellaneous business expenses. Both the substantiation and the return of excess amounts must occur within a reasonable period of time. Employee business expenses reimbursed under an accountable plan are (a) excluded from an employee's gross income, (b) not required to be reported on the employee's IRS Form W-2, Wage and Tax Statement, and (c) exempt from the withholding and payment of wages subject to FICA taxes and income tax withholdings." In summary, expenses must be for church business (ideally budgeted items) and must be "accounted for" and substantiated within a reasonable period of time, with any excess payments being returned to the church. Substantiation is required to be very specific and not lumped into broad categories. The church Board should approve the reimbursable accounting plan in writing. | Develop a customized reimbursement process. Obtain approval of the process by the church board or leadership team. This action is complete when the Management Team has approved the reimbursement process. | <a href="/resources/item/226">Sample Reimbursement Policy</a> by Passion for Planting | 69 | 14 | 2000-01-01 05:00 | 2020-01-29 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content reformatted & resource link updated --pb 2019-12-12 content updated --pb
178 | 217 | 212 | Implement financial records filing system | Develop a disciplined process to store historic financial records that meets IRS requirements. | The IRS is clear on the requirement to keep records to justify your tax-exempt status. The IRS gives considerable latitude in how to maintain the files. Virtually no direction is given other than advice on the types of records to keep. The IRS specifically cites the following types of records: Organizing documents (e.g., charter, constitution, articles of incorporation and bylaws) Meeting minutes Property records Financial records (general ledgers, receipts and disbursements journals, banking records, and invoices) Payroll records Be smart and set up systems to store records for each of these areas. Good Records are the Law Per <a href="https://www.irs.gov/pub/irs-pdf/p1828.pdf">IRS Publication 1828</a>, Tax Guide for Churches and Religious Organizations : Recordkeeping Requirements All tax-exempt organizations, including churches and religious organizations (regardless of whether tax-exempt status has been officially recognized by the IRS), are required to maintain books of accounting and other records necessary to justify their claim for exemption in the event of an audit. (See Special Rules Limiting IRS Authority to Audit a Church below). Tax-exempt organizations are also required to maintain books and records that are necessary to accurately file any Federal tax and information returns that may be required. There is no specific format for keeping records. However, the types of required records frequently include organizing documents (charter, constitution, articles of incorporation) and bylaws, minute books, property records, general ledgers, receipts and disbursements journals, payroll records, banking records, and invoices. The extent of the records necessary generally varies according to the type, size, and complexity of the organization's activities. The law does not specify a length of time that records must be retained; however, the following guidelines should be applied in the event that the records may be material to the administration of any Internal Revenue law. Type of Record Length of Time to Retain Records of revenue & expenses: Retain for at least four years after filing including payroll records return(s) to which they relate. Records relating to acquisition: Retain for at least four years after the filing of and disposition of property (the return for the year in which disposition occurs including real, personal, and investments) | Decide which records to keep and to set up files for. Purchase a file cabinet or similar. Set up the initial files. Define written expectations for the upkeep and maintenance of the files. This action is complete when you have put a filing system or record book to use. |  | 69 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content reformated& --pb 2019-12-12 content updated --pb
179 | 1302 | 1312 | Milestone: Take Care of Legal Requirements | File all the right paperwork in the right order to create the new legal entity of the church. | "Everyone must submit himself to the governing authorities, for there is no authority except that which God has established. The authorities that exist have been established by God." Romans 13:1 NIV Filling out government forms is not what most planters wanted to do when they grew up, but they are necessary for obeying the governing authorities in the spirit of Romans chapter 13. The tasks in the milestone will walk you step-by-step through filing state, federal and other legal paperwork in the US. |  |  | 234 | 212 | 2019-11-26 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: 2020-12-14 changed Due in # Days from 78& to 45& --pb&
180 | 335 | 1302 | Decide whether to have a voting church membership | Establish your congregation to have either a voting or non-voting membership. | Some planters argue that there is no evidence of voting membership in the New Testament. Others see voting as way to contextualize the church to the American culture. Membership means different things to different people. Some are healthy, some are not. Consider the following 'definitions' of membership: Social Connection - some people view membership as a social benefit, as with country clubs Personal Benefit - some people view membership through the lens of what they receive in exchange for committing to be part of the organization Community Connection - some people view membership as a way of building a sense of community belonging Voting Right - the IRS sees church membership as a distinction as to whether members have voting rights or not Commitment - some see membership as a way of clarifying expectations and memorializing commitment You have 3 decisions to make in this action: Will you have voting membership? If so, your bylaws and other legal entity formation paperwork (developed in a subsequent PlanterPlan actions) need to address the rights of members and how voting will be accomplished. Voting membership typically implies a democratic 'equal voice' approach. Churches that choose not to have voting membership typically give their Elders the voting rights. Essentially the Elders represent the rest of the church body. These churches often refer to their membership as 'functional' membership or 'informal' membership. What is the purpose of your membership? You need to clearly communicate the purposes of membership in order to establish and maintain a healthy culture of commitment and belonging (i.e. membership is about commitment and belonging, not benefits or rights). How will people become members? Will they sign a commitment/covenant? Take a class? Sign a ledger? Meet with a staff member? Etc... What the Government Means When the State or Feds ask, "Does your corporation have members?" they're typically asking about who has voting rights. You may need to answer the question No , depending on your context, even if you have a ecclesiastical but non-voting membership. | Decide whether to have voting membership. Clarify your vision/basis for having membership and be prepared to proactively communicate it. Whether you settle on a voting or non-voting membership, define the process for how people become members. This action is complete when the decision has been made about membership and if will there will be a formal membership process developed. |  | 53 | 7 | 2015-02-03 05:00 | 2019-12-10 05:00 | 2000-01-01 05:00 | template: standard 2019-12-10 content updated --pb
181 | 336 | 1302 | Incorporate the Church | Formally organize the church's legal entity in your state. | The most common and most strategic way to legally organize a church in the US is to form a corporation. Incorporation shields individual officers and directors from personal liability and sets the church up to become an official nonprofit organization. Articles of Incorporation (also called Articles of Organization or Charter) are the first step in becoming a legally recognized 501c3 nonprofit organization. Articles of Incorporation provide your state with the basic information about the new church (e.g. name, directors, location, organizational purpose, type of organization, membership structure, etc.). Where to File In most cases, the paperwork is filed with your Secretary of State (list of all 50 states & DC). Most states have websites that provide step-by-step instructions for preparing and submitting nonprofit Articles of Incorporation. Often they include a template the church may use. Most states now allow you to file online through their website, but for some states you'll mail or walk them in. What to File You'll file a simple form, typically 3 pages or less, that covers the basics of your new corporation. You'll get back an approved Certificate of Incorporation and/or copy of the original paperwork stamped with an approval. Corporate Citizenship This sets into motion several ongoing responsibilities. Every nonprofit corporation must: adopt Bylaws or a Constitution have an active Board of Directors maintain legal and financial records in most states, file an Annual Report to keep the corporation in good standing If you fail to maintain these things on an ongoing basis, a court may decide that your corporation doesn't really exist and the the employees, directors and officers are personally liable for the actions of the church. The Registered Agent Most states require the name and address of an individual in that state who will serve as the Registered Agent (aka Statutory Agent, Agent for Service of Process). This is the state's point of contact if legal papers have to be served (e.g. summons, subpoena). The Registered Agent is not held liable for anything the church does or does not do; the agent is just a messenger. If the planter has not already moved on site, he'll have to find someone in the destination state to volunteer. If he doesn't know anyone that already lives in the target state, he should network with his affiliation of churches to find someone willing to be his Registered Agent. If you are working with a Passion for Planting Project Manager, you will be getting significant custom support on this task. If not, follow the instructions in the subtasks to guide you. | Decide whether to prepare the Articles yourself or to pay a professional. Prepare the Articles of Incorporation based on state and church planting network guidelines. Review the Articles of Incorporation (with a lawyer if necessary) to ensure they meet the needs of the church. Approve the Articles of Incorporation (typically signed by an officer of the organization). Submit the Articles to your state for approval. Note that a small fee often applies. Ask for several certified copies of the approval certificate that the state will return to you. This may cost a few extra dollars but it's always easier and sometimes cheaper to get extra copies up front than to have to go back and request one later. This action is complete when you have received approved/certified copies of the Articles from the applicable state agency. |  | 60 | 21 |  |  | 2000-01-01 05:00 | template: standard 2017-05-24 content updated --pb 2018-05-04 added link to 50 states' SOS& --pb 2019-12-10 content updated --pb 2021-01-18 outdented from child to parent task --pb 2022-09-16 removed recommendation hyperlink to& StartChurch& --pb
182 | 337 | 336 | Draft Articles of Incorporation | Fill out the required paperwork to establish the new church as a legal entity in its state. | You will need to decide whether to prepare the Articles yourself or have someone else do them. The good news is that this has never been easier with all of the help available online. Most states have websites that provide step-by-step instructions for preparing and submitting nonprofit Articles of Incorporation. Often they include a template the church may use. Some state require you to file online through their website, but for most states you'll mail or walk them in. Considering downloading Passion for Planting's <a href="/resources/item/8">Articles of Incorporation Template</a> as a starting point. Articles of Incorporation should be kept to a minimum, typically three pages or less, and should include the minimum required information. They are difficult to amend, so only include the information required by the state and the IRS for 501c3 purposes, and not much more. State Requirements Call your <a href="https://www.llcuniversity.com/50-secretary-of-state-sos-business-entity-search/">Secretary of State's office</a> to find out if they have any other filing requirements: Must we use your form, or can we use our own custom format if it covers your basic requirements? Do you have to use "Inc." or similar in the name? Does it have to be notarized? If you're filing from out of state, do they accept digital or facsimile signatures (so it can be emailed to a friend to walk it in)? Does the Registered Agent have to sign an acceptance statement? Does it need to be published afterwards in a local paper or law journal? Will I automatically receive the Certificate, or will I need to download it from somewhere? What are the current filing fees? What are current processing times? If you're in a hurry, is there an fee for rush processing? Are there any other tips or tricks we should know about as we incorporate our new church? In some states (GA & AZ at least), you have to publish the incorporation in a local paper, usually within 24-48 hours. In Louisiana, you have to register your approved Articles with your local Parish within 30 days. Heads up! You will need to submit some or all of the following in your Articles of Incorporation (in descending order of commonality between states): Unique legal name Name of the incorporator (the person calling the corporation into existence) Physical address of corporation Name & address of your Registered Agent (aka Agent for Service of Process, Statutory Agent) Purpose clause that satisfies IRS requirements Dissolution clause that satisfies IRS requirements Additional provisions that set you up for IRS 501c3 nonprofit status Names & addresses of initial Directors Whether or not church members will have voting power Mailing address of corporation If you are working with a denomination or other affiliation, check with them regarding things they require you to include Church Bylaws, which are easier to change and do not require state approval, are typically a better place to put the other things you may be tempted to include in the Articles. IRS Requirements Your state may not require this to be included, so it's all too easy to file paperwork that satisfies your state but not the feds. Include this wording now to avoid problems later when filing your 501c3 application: a Purpose Clause This corporation is a RELIGIOUS CORPORATION and is not organized for the private gain of any person. It is organized under the Nonprofit Religious Corporation Law exclusively for religious purposes. This corporation is organized and operated exclusively for religious purposes within the meaning of Section 501(c)(3) of the Internal Revenue Code. a Dissolution Clause Upon the dissolution of this corporation, after paying or adequately providing for the debts and obligations of the corporation, all assets shall be distributed to [Name of Benefactor] which operates within the meaning of Section 501(c)(3) of the Internal Revenue Code. Should [Name of Benefactor] no longer exist, all remaining assets shall be distributed for one or more exempt purposes within the meaning of Section 501(c)(3) of the Internal Revenue Code or shall be distributed to the federal government, or to a state or local government, for a public purpose. Such distribution shall be made in accordance with all applicable provisions of the laws of the state of [Name of State]. On Forming a Board of Directors Most states will ask for contact information for the initial Board of Directors. Reference the previous PlanterPlan task Form a Management Team (oversight) if you do not already have a Board in place. The Registered Agent Most states require the name and address of an individual in that state who will serve as the Registered Agent (aka Statutory Agent, Agent for Service of Process). This is the state's point of contact if legal papers have to be served (e.g. summons, subpoena). The Registered Agent is not held liable for anything the church does or does not do; the agent is just a messenger. If the planter has not already moved on site, he'll have to find someone in the destination state to volunteer. If he doesn't know anyone that already lives in the target state, he should network with his affiliation of churches to find someone willing to be his Registered Agent. | Decide whether to prepare the Articles yourself or to pay a professional. Prepare the Articles of Incorporation based on state and church planting network guidelines. Review the Articles of Incorporation (with a lawyer if necessary) to ensure they meet the needs of the church. Approve the Articles of Incorporation (typically signed by an officer of the organization). This action is complete when you have signed the finalized Articles of Incorporation. |  | 53 | 14 | 2000-01-01 05:00 | 2022-09-16 04:00 | 2000-01-01 05:00 | template: standard 2017-05-24 content updated --pb 2019-12-10 content updated --pb 2021-01-18& outdented& from child to& parent task; due it days changed from 52 to 60 --pb
183 | 338 | 336 | Submit Articles of Incorporation | File the completed paperwork and get officially incorporated in your state. | Filing the Articles of Incorporation can be done online (in most states), in person, by mail, or by fax. The filing option you choose will have timeline implications. The Articles of Incorporation are an important first step in getting the church legally formed. You won't be able to pay salaries until you've done the following: obtained a Federal EIN (see subsequent PlanterPlan action) opened a checking account, and filed for appropriate state employer tax numbers You can't do any of these until you've incorporated. It is best to get the approved Articles back as quickly as possible. If you're Filing Online A word of caution - some of the states that require you to file online do not make it easy to include the extra language you need to make the IRS happy (see previous PlanterPlan task Complete Articles of Incorporation ). Look for an 'Other' field or 'Upload Addendum' function. If they don't allow you room for those important clauses (Kansas is a particular culprit), then you'll either have to file online and then submit an addendum later, or forgo the online option and mail in good, old-fashioned papers. | Determine if and where the Articles can be filed online with your state. Create an online required as required. Complete all the fields and be sure to include the clauses the IRS will require . If it is impractical or impossible to file them online, then determine which mailing address or fax number to send the paperwork to. Be sure to include proper payment or the papers will be delayed and/or returned. This task is complete when you have successfully submitted the Articles of Incorporation to the state along with proper payment. |  | 60 | 15 | 2015-02-03 05:00 | 2021-01-18 05:00 | 2000-01-01 05:00 | template: standard 2017-05-24 content updated --pb 2019-12-12 content updated --pb 2020-12-14 changed Duration from 14& to 7& --pb&
184 | 331 | 1302 | Get a Federal EIN for the church | A Federal Employer Identification Number (also known as an EIN) is required for any legal entity. | An EIN is kind of like a social security number for an organization. An EIN is required to pursue 501c3 status. It is also useful for other legal and organizational issues (e.g. opening a checking account, etc.). We recommend you reserve the church's legal name prior to obtaining your EIN. If you don't and you run into any issues finalizing that name at the state level, you'll have to file Federal name change paperwork later. Good luck with that. The best way to reserve your name is by filing Articles of Incorporation with the state. Some states allow you to reserve your name prior to the actual filing by completing another simpler form. Either way, you should check with the state to: find out what requirements they may have (does the name need to include "inc.") search to see if the name is available and either file the Articles of Incorporation or Name Reservation before you get the EIN. Step-by-Step Instructions The following recommendations do not necessarily apply to you and your situation. These are, however, the standard answers we provide the IRS for most of the churches Passion for Planting directly supports. Your answers may differ based on your circumstances. If you have any doubt, consult a lawyer familiar with applicable state and federal laws. Click Apply Online Now toward the bottom of the page. Click Begin Application . Select View Additional Types and then click Continue . Select Church (as opposed to other flavors of corporation) and the click Continue . Click Continue on the Please Confirm Your Selection page. Select Started a New Business and click Continue . Select Individual as the Principal Officer and click Continue . Input the requested information about the Principal officer (you, the planter), select I am the President/CEO... and click Continue . Input the address of the corporation as requested (No PO Boxes allowed) and click Continue . Input the requested information about the Corporation. It will be best to select December as the end of business year. Click Continue . Answer the first 4 questions (your answer will probably be No ) and for the 5th question, answer: Yes for the last question if the church will be paying anyone by W-2 (most employees) or No if there are no paid employees to start with, or only clergy on staff that have all opted out of Social Security. You may also select No for the 5th question if another church or ministry is paying your employees' payroll directly (a form of co-employment). Confirm on the next page that all the data has been input correctly with no typographical errors. Click Apply . It is imperative that you print and store the resultant form in a safe place. We recommend inserting it in your corporate records book and a secondary safe place. We also recommend keeping an electronic copy backed up in the cloud. | Visit the IRS website to <a href="https://www.irs.gov/businesses/small-businesses-self-employed/apply-for-an-employer-identification-number-ein-online">apply online</a> for the federal Employer Identification Number (EIN). Follow their interview-style application process. Receive the EIN assignment letter as a PDF document at the end of the application. Print and archive a copy of the letter in your corporate records book (see subsequent PlanterPlan action). Save the PDF file to your computer and to a backup location. This action is complete when you have obtained the federal Employer Identification Number (EIN). |  | 67 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2019-12-10 content updated --pb 2020-12-14 changed Due in # Days from 52& to 67 --pb&
185 | 355 | 1302 | Draft church bylaws | Adopt bylaws to provide structure and rules for operation for the new church. | Bylaws define the rules of operation for corporations. Some organizations refer to Bylaws as a Constitution. Bylaws are maintained by the church (prepared, approved, modified, etc.) and do not typically require any outside or government approval. Corporations must adopt some version of Bylaws. Though you don't need them approved by the government, you need to prove that you do have them when you apply for 501c3 tax-exempt nonprofit status. You'll also need to prove that you have them when you apply for postal permits. One key issue in Bylaws is whether or not the church will have official membership (per the IRS definition of membership) and whether all members have equal voting rights or whether the Elders make official decisions on behalf of the membership. Reference previous PlanterPlan task Decide whether to have a voting church membership . | Review the <a href="/resources/item/30">Church Bylaws Template</a>. Check online for additional sample bylaws. If necessary, find help online or check a book out of the library. Customize the Bylaws as necessary for the new church. Determine who will sign the Bylaws as legal agents and obtain their signatures. Minimally, have the Corporate Secretary sign. This action completes when the Management Team (or other appropriate oversight) approves the final Bylaws. | <a href="https://seniorpastorcentral.com/4210/3-by-law-changes-needed-to-break-100-200-400-and-600/">3 By-Law Changes Needed To Break 100, 200, 400 and 600</a> from seniorpastorcentral.com <a href="https://churchanswers.com/blog/six-common-problems-with-church-bylaws/">Six Common Problems with Church Bylaws</a> from thomrainer.com <a href="https://careynieuwhof.com/5-essentials-every-church-constitution-needs-in-the-future/">5 Essentials Every Church Constitution Needs To Thrive In The Future</a> from careynieuwhof.com | 60 | 14 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content validated --pb 2019-12-11 content updated --pb 2020-12-14 changed Due in # Days from 203& to 67 --pb&
186 | 354 | 1302 | Conduct initial board meeting | Begin behaving like a corporation by holding the first official board meeting. | The first task of the new corporation is to hold the first board meeting. You can do that either just before or just after filing the incorporation paperwork. Passion for Planting recommends holding the meeting before incorporation so that you can ratify all of the initial legal docs up front, including the not-yet-filed Articles of Incorporation. Minimally, you'll want to cover the following at that meeting: Appointing Directors Approving the Articles of Incorporation (even retroactively) Adopting Bylaws Appointing or electing corporate officers The minutes from this meeting must be signed by the secretary and filed promptly in the Corporate Records Notebook. Why Meeting Minutes are Important Most states practice a hands-off approach to churches: they don't want to mess with routine or random examination of a church's corporate records. However, if there is an examination, for a lawsuit for instance, you'd better have everything documented. The best way to be ready is to meet regularly as a board and keep good notes (meeting minutes). If the church doesn't have recorded meeting minutes or other proof of corporate activity, the judge may say, "What corporation?" If that happens, the board & staff may be held personally liable. As in, your car, house, retirement account, etc. | Notify your appointed Directors of the meeting or have them sign a Waiver of Notice of Directors' Meeting . Make sure someone is taking minutes and recording action items. Cover the items listed above and any other business that needs to be taken care of. Conclude the meeting and file the signed minutes in the Corporate Records Notebook. This action is complete when you have filed the minutes from the first Board Meeting in the Corporate Records Notebook. | <a href="https://www.lifehack.org/804185/meeting-minutes">How to Write Great Meeting Minutes so Nothing Gets Lost in Translation</a> on lifehack.org | 60 | 14 | 2015-02-03 05:00 | 2024-08-20 11:08 | 2000-01-01 05:00 | template: standard 2017-05-25 content and resource link updated --pb 2018-02-09 additional resource link added --pb 2019-12-10 content updated --pb 2022-09-16 removed recommendation hyperlink to StartChurch --pb 2022-11-21 updated links --sc &
187 | 361 | 1302 | Build a corporate records notebook | Simplify finding and updating your important corporate documents by creating a notebook or binder where all of they are held. | You'll create many different documents in the course of getting the new church started. Some of the originals will be difficult to reproduce, if not impossible. Keeping them in one safe place all together will keep them from being lost, misplaced, or coffee-stained. This will keep you from wasting time looking for them when you need them. The Corporate Records Notebook should include: Articles of Incorporation Bylaws Written Doctrines Federal EIN Letter Official policies of the board Federal 501c3 Determination Letter Board Meeting Minutes State Exemption Letter Employer withholding account documents (if applicable) USPS nonprofit pricing classification Other government correspondence Member's Register (if church is having membership) Insurance Policy Contracts Keep the Book in a safe place where it is unlikely to be destroyed by fire or water. It is also a good idea to scan each document and keep an electronic copy in the cloud. | Purchase a 3-ring binder or folio-style book. Scan each document and keep an electronic copy in the cloud. Insert all of the original documents listed above along with any other document that should be archived for safekeeping. Keep the book in a safe place. This action is complete when a Corporate Records Notebook has been filled with all of the corporation's founding documents. |  | 67 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-26 content validated --pb& 2020-01-21 content updated --pb 2020-12-16 changed Due in # Days from 210& to 128& --pb
188 | 1289 | 1302 | Apply for 501c3 nonprofit status | Complete and file the IRS 501c3 application so you can get discounts, donations, and stop paying sales tax (depending on your state). | The IRS grants churches an automatic 501c3 tax exemption. Basically, if you're organized as a church and behaving as a church, you're already a 501c3 nonprofit. But the IRS are the only ones that seem to know about that rule. Even the US Post Office doesn't honor the IRS' automatic exemption. Many states won't grant you a sales tax exemption unless and until you have a 501c3 determination letter from the IRS with your church's name on it. And increasingly, US corporations that offer grants and free or discounted products and services to nonprofits first check the IRS online database of approved 501c3's. If you're using the IRS' automatic exemption, they won't list you in that database. Therefore, some donors won't give you the time of day. So we generally advise US churches to formally apply for 501c3 exemption. It costs $600 to apply and takes quite a bit of work to complete, but it cuts through all of the confusion and opens doors of opportunity for your church. You'll get a letter with your church's name on it, and they'll publish you in their online database. The following subtasks will walk you step-by-step through completing, compiling and submitting the IRS application for 501c3 tax exemption. Compiling What You Need The IRS 1023 application for 501c3 tax-exempt status is a lengthy application that includes simple check box questions as well as long-answer essay questions. Putting together all of the requested information and composing all of the answers is well worth the effort, but will take some time. You will want to have the following information available as you sit down to fill out the 1023 form: The church's EIN (see previous PlanterPlan action) Full names and addresses of the officers/directors 3 years' worth of budget figures, especially offerings, salary and rent. These can be proposed figures if you haven't closed out your first fiscal year as a church. Approximate bank account balance and the value of actual tangible church property (laptop, trailer, sound system, etc.) at time of application As of January 31, 2020, the IRS put form 1023 Application for Recognition of Exemption online. You will create an online account according to the Actions steps below. They will required supporting documentation, but only allow you to upload one singe file. Create a single PDF file of all attachments; be sure the church name & EIN are on every page: Articles of Incorporation (along with any amendments in chronological order) Bylaws with any amendments Church Doctrines (if you've established a formal/written set of doctrinal statements) Any facility lease or rental agreement the church has signed Your r&eacute;sum&eacute; (optional, but recommended to support qualifications) | <a href="https://www.pay.gov/public/registration">Create a company account</a> on www.pay.gov. Use the search box to search on "1023" and begin the application. Upload your single PDF file of all attachments (per above). In the www.pay.gov 1023 application, use the PDF Preview button to download a completed but unsigned copy of your application and review it for accuracy. Double check that you have spelled the name of the church correctly on the first page of the form, and that it matches exactly the legal name on the Articles of Incorporation. Make sure that you have included all of the required supporting documentation in the single PDF attachment, and that the church's name and EIN are included on every page (in case they get separated). Make sure that the church planter's name is spelled correctly in each instance. Make any corrections to the online application. Officially submit the application and pay the $600 application fee. This action is complete when you have submitted the online 1023 Application for Tax Exempt Status. | <a href="https://www.startchurch.com/blog/view/name/3-myths-of-the-501c3">3 Myths of the 501c3</a> by StartChurch These helpful posts on churchplatingtactics.com: <a href="https://www.churchplantingtactics.com/church-plant-501c3/">How to Apply for Your Church Plant 501c3</a> <a href="https://www.churchplantingtactics.com/faster-501c3-application-processing/">How to Get Faster 501c3 Application Processing</a> <a href="https://www.churchplantingtactics.com/does-my-church-plant-have-to-apply-for-501c3-exemption/">Does My Church Plant Have to Apply for 501c3 Exemption?</a> <a href="https://www.churchplantingtactics.com/umbrella-501c3-exemption/">Should You Use Your Group's Umbrella 501c3 Exemption?</a> <a href="https://www.churchplantingtactics.com/are-missional-communities-501c3/">Are Missional Communities (or house churches) 501c3?</a> <a href="https://www.churchplantingtactics.com/nonprofit-discounts-for-churches-techsoup/">Get Tons of Nonprofit Discounts for Churches at </a><a href="https://www.churchplantingtactics.com/nonprofit-discounts-for-churches-techsoup/">TechSoup</a> <a href="https://www.churchplantingtactics.com/google-for-nonprofits/">Get These 3 Free Products from Google for Nonprofits</a> | 150 | 14 | 2019-10-14 04:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: 2020-12-16 changed Duration from 161 to 152& --pb&
189 | 351 | 1302 | File for nonprofit pricing classification with the US Post Office | File necessary paperwork to qualify for nonprofit postage rates. | You can save a ton of money when doing a big mailing if you're officially recognized by the Post Office as a nonprofit. Some churches will get their own bulk mail permit. However, if you work with a direct mail vendor that specializes in helping churches, you can piggyback on their permit and you don't need to pay for your own bulk mail permit ! Here are some companies that have served our planters in the past: <a href="https://outreach.com">Outreach Marketing</a> <a href="https://www.d2design.com/">D2Design</a> <a href="https://mailworksii.com/">MailWorks II</a> For the Post Office discount, there is no application fee or annual fee, but this form often takes 2-4 weeks to be approved. Complete it and submit to the post office at least a month before your first mailing. Applying for the nonprofit discount is tricky, though, because new churches are in a catch 22: you want save money announcing your Grand Opening, but the Post Office says you're not a church until you've had your Grand Opening. They will demand a copy of your 501c3 Determination Letter, but most churches won't get that back from the IRS in time. The vendors above will help you navigate this. If you are working with a Passion for Planting Project Manager, you will be getting significant custom support on this task. If not, follow the instructions below. | Offline Application Figure out which is your local "main" Post Office branch. We use their <a href="https://tools.usps.com/find-location.htm">location finder</a> and search for the branch that has US Passport services. You'll name this location in the application and go there to submit the application. Download the <a href="https://about.usps.com/forms/ps3624.pdf">Form PS 3624 - Application to Mail at Nonprofit Standard Mail Rates</a>. Complete all questions in Part 1. Compile and attach as many items from page 3 as possible. Sign the application. Carry the entire application packet in. Go around the back of the building to the Bulk Mail (business mail) counter, usually by the loading docks. Wait to hear back from USPS headquarters. Online Application Figure out which is your local "main" Post Office branch. We use their <a href="https://tools.usps.com/find-location.htm">location finder</a> and search for the branch that has US Passport services. You'll name this location in the application. <a href="https://reg.usps.com/entreg/RegistrationBusinessAction_input">Create a USPS online account</a>. Log in the <a href="https://gateway.usps.com/eAdmin/view/signin">USPS Business Gateway</a>. Select Postal Wizard > ps3624 . Complete the application and upload as many of the supporting documents from the list as possible. Wait to hear back from USPS headquarters. This action is complete when you receive the approved NPA number from the US Post Office by either means. |  | 167 | 14 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-05-25 contents validated --pb 2018-11-12 additional resources subsection added --pb 2019-08-21 new additional resource added --pb 2019-12-11 content updated --pb
190 | 345 | 1302 | Get your state sales tax exemption | File necessary paperwork to obtain sales tax exemption recognition from your state. | You can save thousands of dollars by not paying sales tax on purchases the church makes. It is clearly in the interest of the church not to pay unnecessary taxes. State sales tax is paid to the state each time your church purchases something (typically 4-8% on top of the purchase price). Obtaining state sales tax exemption saves considerable money throughout the life of a church and can save hundreds (and in some cases thousands) of dollars during the pre-launch phase. There are several categories that states fall in to (double check your state's requirements): there is no sales tax (AK, DE, MT, NH, OR) churches can submit sales receipts for reimbursement of the sales tax (including NC) churches can declare themselves nonprofit on an honor system and download an exemption form to use (including MI) churches can apply for nonprofit sales tax exemption on their purchases (most states) they do not grant any nonprofit a sales tax exemption (including CA, LA) - tough luck! In many states that have an application process, you will not be able to apply until after receiving your 501c3 Determination Letter from the federal government. Contact your state's Department of Revenue to find out what kind of exemption, if any, is available. Try searching on [name of state] sales tax exemption . If you are working with a Passion for Planting Project Manager, you will be getting significant custom support on this task. If not, follow the instructions below. | Obtain an application form for sales tax exemption. Complete the application form. Sign and submit the application form along with required supporting documentation. This action is complete when you have the state sales tax exemption certificate in hand. |  | 167 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-25 content updated --pb 2019-12-12 content updated --pb 2020-12-14 changed Due in # Days from 59& to 67& & Duration from 7 to 14& --pb&
191 | 313 | 1312 | Milestone: Create Church's Brand | Gain a clear understanding of what a brand is and why you should be intentional about building a positive one. | The new church will gain a reputation in the community either positive or negative. When they hear the church's name or see the church's logo, they will feel something about the church. Be intentional about presenting the church in a positive light. |  |  | 128 | 82 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-10-26 content validated --pb 2019-12-09 content validated --pb 2020-12-16 changed Due in # Days from 112& to 109& & Duration from 42& to 56& --pb&
192 | 314 | 313 | Read this branding overview | Understand some basic principles of branding so you can begin distinguishing your church within your community. | There is more to a brand than a logo and a color scheme. These are important pieces, but there are other factors that help a good brand stand out in an already crowded market. The bigger question is, "What do you want your church to be known for?" Your brand is the story people tell themselves about you. It is your promise to your community. The Ed Stetzer video below provides a brief overview that will get you up to speed on church branding. | Watch the Passion for Planting training video "<a href="/resources/item/16">Branding - Define Church Identity</a>" featuring Ed Stetzer. | <a href="https://churchjuice.com/blog/why-your-church-needs-a-brand">Why Your Church Needs a Brand</a> by Church Juice <a href="https://www.stevefogg.com/2012/11/21/branding-churches/">10 Common Branding Mistakes That Churches Make</a> by Steve Fogg | 54 | 1 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard Need to ensure video works (needs updated link). -----ds Just updated to our new media page:& <a href="https://planterplan.com/app/#/tutorial/media/16">http://planterplan.com/app/#/tutorial/media/16</a> Had a reference to dev& site...removed. 2017-10-26 content validated & link verified --pb 2019-12-09 content updated --pb 2020-12-14 changed Due in # Days from 84& to 54& & Duration from 7 to 1& --pb&
193 | 229 | 313 | Buy a domain name for the church | Buy the rights to a website address (domain name) that will be easy for people to remember and associate with your church. | Once you've finalized the name of the new church, one of your first steps is to buy a domain name. You will buy the domain name from a registrar like GoDaddy or NameCheap; other options abound. Here are 8 tips from the post <a href="https://www.wpbeginner.com/beginners-guide/tips-and-tools-to-pick-the-best-domain-for-your-blog/">How to Choose the Best Domain Name (8 Tips and Tools)</a> : Stick with .com [it's everyone's default guess] Use keywords [like "church", so search engines know what your site is about] Keep it short ( Make it easy to pronounce and spell Keep it unique and brandable Avoid hyphens Avoiddoubled letters Leave room to expand We also recommend testing your top choices for alternate interpretations: Is www.bethelame.com "Bethel AME" or "Be The Lame"? How would you interpret "kidsexchange.com"? Power Tip: consider a domain name that can also become your social username. For example, XYZchurch could become your website at www.xyzchurch.com and used for you Facebook page at facebook.com/xyzchurch, etc. Sites like <a href="https://www.namecheckr.com">www.namecheckr.com</a> will check for available domain names and social usernames simultaneously. | Brainstorm possible names and name combinations. Determine which possible names are available. Select your primary web name and any additional aliases desired (.net, .org, etc). Purchase the domain name(s). This action is complete when have purchased the church's new domain name. |  | 60 | 7 | 2015-02-03 05:00 | 2022-02-15 05:00 | 2000-01-01 05:00 | template: standard 2017-09-26 changed Parent ID from 228 to 225 in order to move this from child task to regular task --pb 2017-09-26 content updated --pb 2019-12-09 content updated --pb 2020-12-14 changed Due in # Days from 35 to 60 --pb&
194 | 230 | 313 | Set up email accounts with new domain name | Set up a church email account for each staff member to facilitate branded communication. | As soon as you purchase your church's domain name, you can set up email accounts. Your website and your email addresses will share the domain name, but they are unrelated services and one doesn't depend on the other. Popular Options There are plenty of options, but the common choices are: Your Registrar's Service Whoever you bought your domain name through commonly offers an email service. For example, GoDaddy will sell you <a href="https://www.godaddy.com/email/professional-business-email">email service</a> for as little as $2/user/month (teaser rate) PRO: simple setup since it's from your registrar; may be cheaper than the other options below CON: may not include state-of-the-art spam filter; may not include other services (see others below) Google Workspace If you've ever used gmail, google calendar, google drive, etc. you already know <a href="https://workspace.google.com/pricing.html?tab_activeEl=tabset-companies">Google Workspace</a>. It runs as little as $6/user/month. The difference is that you get to brand it all with your own domain name. PRO: comes with an entire suite of productivity apps plus 30GB of cloud storage per user; easy-to-use; best spam filter available CON: they can scan your email content to sell you ads NOTE: Google Workspace is free for approved nonprofits (once your get your 501c3 Determination Letter back from the IRS), but you have to agree to their non-discrimination policy Microsoft's Office365 You may be able to purchase this at a discount through your registrar, or you can purchase it directly from <a href="https://www.microsoft.com/en-us/microsoft-365/business/compare-all-microsoft-365-business-products">Microsoft</a> for as little as $8.25/user/month. PRO: comes with an entire suite of productivity apps plus 1TB of cloud storage; excellent spam filter; they do not scan your content to sell you ads CON: higher cost NOTE: Office365 is also free for approved nonprofits (once your get your 501c3 Determination Letter back from the IRS), but you likewise have to agree to their non-discrimination policy Pick the option that suits your budget and tech needs and either set it up yourself or get help from a tech-savvy friend. | Set up new email accounts based on the new website name. Decide whether to keep any existing email accounts. If so, decide whether to have all your email accounts forwarded to a single account or to set up multiple inboxes on your various devices. Create a generic address like info@ for publishing on your website. This action is complete when valid email addresses associated with the new domain name are properly functioning. |  | 60 | 7 | 2015-02-03 05:00 | 2022-12-23 05:00 | 2000-01-01 05:00 | template: standard 2017-09-21 content updated --pb 2017-09-26 changed Parent ID from 228 to 229 to keep as a child task --pb 2018-04-20 changed Parent ID to 225 & promoted to "task" 2019-12-09 content updated --pb 2020-12-14 changed Due in # Days from 42& to 60& & Duration from 28& to 7& --pb& 2022-12-23 change "G Suite" to new brand "Google Workspace", added Office365 grant language --pb
195 | 315 | 313 | Establish a relationship with a branding company | Choose a branding company that can guide you through the hard work of translating the church's identity into a new brand. | Since the church's name flowed out of your contextualization work, as soon as you choose the name you've already done the hard work to be ready to begin the branding process. Branding is way more than just a logo. Your brand is your story. Your brand is your promise to your community. Your brand is your identity. The first step, which is a big one, is to create the church's brand. Your brand will include: your colors, picked specifically for their psychology and style your official font your logo in multiple formats a tag line or brand promise a style guide that compiles all of these in one place An initial branding package may also include: business card design letterhead design social media cover image & thumbnail a fundraising brochure or booklet design vinyl event banner design But you'll have ongoing design needs even before your launch: website direct mail and/or door hangers facility signage sermon slides You can get various pieces from various designers, but consider the long game. Pick a branding company that will be able to help with ongoing design needs, which also helps with brand consistency. Be cautious of having a friend do the design for you for free. It might work out great. But common experience is that the friendship gets strained because of unmet expectations, missed deadlines, and hurt feelings on both sides. Only hire a friend or relative that you'd be willing to fire . Branding & Graphic Design Vendors Here are some companies that have served our planters in the past: <a href="https://www.brandarmy.org/">Brand Army</a> <a href="https://www.amywaggs.com">Waggoner</a> <a href="https://catalystchurchcreative.com">Catalyst Church Creative</a> <a href="https://outreach.com">Outreach Marketing</a> <a href="https://www.browncowdesign.com">Brown Cow Design</a> <a href="https://churchmediasquad.com/">Church Media Company</a> Other options abound. | Get referrals from friends and colleagues. Refer back to your budget for how much you allocated for branding. Determine what what you need in an initial design package. Look at each designer's portfolio to determine which designer's 'look' is a match. Get an initial quote for the work that needs to be done. This actions is complete when you have engaged a branding company to begin the branding process. |  | 74 | 14 | 2015-02-03 05:00 | 2022-11-22 05:00 | 2000-01-01 05:00 | template: standard 2017-10-27 content udpated& --pb 2018-02-09 vendors subsection added --pb 2019-12-09 content updated & links verified--pb 2020-12-14 changed Due in # Days from 84& to 74 --pb& 2022-11-22 undated links --sc
196 | 318 | 313 | Develop a brand style guide | Develop a consistent look and feel to your communication materials so that you can be effective in connecting with the people God is calling you to reach. | Brand recognition allows people to quickly identify your church and experience positive feelings about your marketing. Have you ever noticed that all McDonald's restaurants look basically the same? This is brand identity. Even young children know that at the restaurant with the golden arches they can order a Happy Meal and get a free toy. Eventually, people who see your marketing and attend events need something to tie everything together, something to relate all the messages they are hearing to the same place. They ought to know when they see your logo that 'this is the church where __________'. Based on your demographics research and Vision Frame, you'll develop a core identity to be communicated in all marketing materials and throughout all outreach events. The specific products of your brand identity include: your colors, picked specifically for their psychology and style your official font your logo in multiple formats (see subsequent PlanterPlan action) a tagline or brand promise (see subsequent PlanterPlan action) a style guide that compiles all of these in one place (the primary product of this task) Where to Start Your branding company may give you similar homework. Here are some great pre-work exercises that will make your branding process faster & smoother: Find 5 magazine ads that you like. Write down what you like about them. Find 5 logos that you really like. Write down what you like about them. Find 5 web sites that you really like. Write down what you like about them. Collect 5-10 pieces of direct mail advertising that you really like. Write down what you like about them. Download the <a href="https://churchbrandguide.com/how-to-create-your-churchs-brand/">How to Create Your Church's Brand</a> guide. The Style Guide A style guide serves as a standard for maintaining the integrity of your brand. The style guide lists the approved ways to use your logo, tagline, colors and fonts on marketing and promotional pieces. It includes things such as: A short description of the brand in qualitative terms. This paragraph highlights the uniqueness of the organization, its niche, etc. Primary colors of the organization (in both full color and gray scale) Primary logo of the organization and the ways it can be used / displayed including any allowed alterations Primary fonts / typefaces of the organization Primary tagline of the organization Other images used by the organization Any reputable branding company will offer you at least a simple style guide as part of your branding package. Great samples to learn from: <a href="https://drive.google.com/file/d/15NG4shAE8xBPMCFGR6xbmtLtZ8S5YbMV/view?usp=sharing">Connect Church brand book</a> <a href="https://open.life.church/items/122018-lifechurch-branding-guidelines-pdf">Life.Church style guide</a> <a href="https://drive.google.com/file/d/13n6x8fXr0I2RXAzFmzUcn-NVeB9Qqivv/view?usp=share_link">Village Church style guide</a> | Work with your branding company to translate your church's story and identity into a visual brand. This action is complete when you have the logo files and brand style guide in-hand. | <a href="https://a.co/foEeO9M">Purple Cow</a> (Seth Godin) <a href="https://a.co/fPrBNih">2015 Guide to Perfect Church Identity Branding</a> (Alex Miranda) <a href="https://a.co/5TS5fKN">Branding Faith: Why Some Churches and Nonprofits IMpact Culture and Others Don't</a> (Phil Cooke) <a href="https://a.co/4g3FljM">What Smart Churches Know</a> (Rod Arnold) the post <a href="https://churchmarketingsucks.com/2013/09/how-to-create-a-brand-style-guide/">How to Create a Brand Style Guide</a> on ChurchMarketingSucks.com Canva's built-in <a href="https://www.canva.com/pro/brand-kit/"> Brand Kit </a> where you can save your brand details (requires paid account) | 95 | 21 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-10-27 content and links updated --pb 2019-12-09 content updated --pb 2020-06-08 new sample & resource bullet points added --pb 2020-12-14 changed Due in # Days from 98& to 95 --pb& 2022-11-21 links updated --sc
197 | 319 | 313 | Develop a tagline | Summarize your church's identity and brand promise in a short tagline. | The tagline is a short motto or saying that conveys your church's identity and brand promise. It's usually 10 words or less (shorter is better), memorable, distinct, and catchy. It will become the mantra of the new congregation. Your tagline should flow from your Vision Frame (see previous PlanterPlan task). Your tagline is a key piece of your brand identity that literally says something about who you are. The other pieces of your brand identity stimulate the emotion through images (logo, font, color, etc...). The tagline is your chance to use words to communicate succinctly who you are. These may be 6 of the most powerful words you speak. Here are sample church taglines that are already taken: No perfect people allowed Church for the rest of us A place to discover God | Brainstorm potential themes for taglines. Group and prioritize similar concepts. Discuss with some unchurched friends what concepts they relate to. Develop a short tagline which communicates to not-yet-believers that key piece of vision you want them to know about your church. Test the finished product with the unchurched and seek their feedback on what the tagline communicates to them. Make adjustments as necessary. This action is complete when you have finalized the church's tagline. |  | 81 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-10-27 content updated --pb 2019-12-09 content validated --pb 2020-12-14 changed Due in # Days from 98& to 81 --pb&
198 | 320 | 313 | Design your logo | Create a logo that encapsulates your church's brand for use in your community. | A logo helps people quickly connect all your marketing efforts to your church. Your logo is a key part of your brand and should be included in your style guide (see previous PlanterPlan action). It may be the single most distinguishable part of your brand. Consider Google and Starbucks. You can see the Starbucks logo in your mind right now, can't you? Your logo should tell a story and capture the feel of your congregation. And no, not every church logo must include both a cross and a dove. Check out this super-helpful <a href="https://www.companyfolders.com/blog/design-perfect-business-logo-infographic">How to Design the Perfect Business Logo</a> infographic. Work with your branding company back and forth through several rounds of concepts and revisions. More than Just One Logo But you need more than just one logo. You need the same logo in 12 variations so you can use it in different contexts: the primary logo (typically in color and landscape-oriented) the reverse logo (if your logo is light-colored, this will be a dark version, and vice versa) the primary logo in B&W a reverse B&W a square version (color) a square reverse a square in B&W a square in reverse B&W just the icon in color (no words, just the 'mark') just the icon in reverse color just the icon in B&W just the icon in reverse B&W And more than that, you'll want the source file for each of these along with a JPG and PNG version of each. Yes, that's 36 files! | Hammer out the logo with your branding company. Make sure you get all the versions and file types you'll need. Save the original source files to your computer and to the cloud. This action is complete once you have backed up the final logo files to the cloud. | <a href="https://get.tithe.ly/blog/church-fonts">Your Church Font Matters More than You Know</a> by tithe.ly | 95 | 21 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-10-27 content updated --pb 2019-10-31 additional resources subsection added--pb 2019-12-09 content validated --pb 2020-12-14 changed Due in # Days from 112& to 95& & Duration from 30& to 21& --pb&
199 | 227 | 313 | Buy branded promo giveaways | Develop promotional materials to help communicate that a new church is being started. | A great way to get the word out is by buying branded promotional materials. These giveaways can range from bookmarks to frisbees. The idea is to use the promotional materials to help spread the word about the new church. Initially you may have to order items with no logo. That's actually OK if you include a website, social media address or other contact information. Key principles when deciding what to order: Life Expectancy : frisbees and ink pens might last for years but a disposable water bottle will get tossed the same day (that's not necessarily bad, but it should inform how much you're willing to pay per item) Bulk Discount: branded promo items are almost universally cheaper when purchased in quantity Plan Ahead : give yourself the better part of a month for design, production and shipment; rush fees are expensive Partner with Other Nonprofits : sometimes there are opportunities to co-brand items and split the expense with another group Set a Budget : you will be developing an overall church planting budget - be sure to include branded promo items Include Contact Info : it's easy to overlook, but your website should be on everything you print Branded promo items to consider: <a href="https://www.gotprint.com/products/club-flyers/order.html">club flyers</a> <a href="https://www.4imprint.com/sale?ss=pen">ink pens</a> <a href="https://www.4imprint.com/sale?ss=balloon">balloons</a> (don't forget the helium) fidget spinners disposable water bottles (custom branded or apply your own waterproof stickers) t-shirts sportpack, tote or shopping back sunglasses (make sure they block UV) Find a local vendor to order branded promotional items from. This will help you meet new people in the community and may save you on shipping costs. But always compare local quotes to the big online outlets to ensure you are getting the most from your dollar. | Brainstorm a list of ideas for promotional materials that will connect well in the community. Contact a local promo company and/or a national group like 4imprint to get some price quotes. Work with the vendor to get items designed; be sure to include website or other contact information. Order initial promotional materials. This action is complete when you have ordered initial promotional materials. |  | 109 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-09-15 content updated --pb 2020-01-24 content validated --pb 2020-12-14 changed Due in # Days from 60& to 109& & Duration from 28& to 14& --pb&
200 | 1389 | 1312 | Milestone: Create Initial Digital Footprint | Start claiming digital real estate and establishing the new church online even prior to having a fully developed brand. |  |  |  | 234 | 174 | 2021-01-15 05:00 | 2022-02-08 05:00 | 2000-01-01 05:00 | template:
201 | 565 | 1389 | Decide which social media apps to use | Discover which social media platforms your target families use and decide which ones the church will use. | There are hundreds of social media platforms out there, too many for you possibly to participate in. Besides, if the people you're trying to reach aren't using those sites, why even bother? Do a little research on which platforms are most popular generally, and then research which ones are most popular in your context. Chances are the resulting list will be relatively small since they have the same 'choice overload' your church suffers from. | Determine which social media sites will be most effective in reaching your community. Choose which social media sites your church will utilize from the start. Consider adding the Milestone: Connect Through Social Media to your launch plan. This action is complete when you've decided which social media platforms to focus on. | <a href="https://www.statista.com/statistics/272014/global-social-networks-ranked-by-number-of-users/" rel="noopener">Most popular social networks worldwide, ranked by number of monthly active users</a> [statista.com] <a href="https://en.wikipedia.org/wiki/List_of_social_platforms_with_at_least_100_million_active_users" rel="noopener">List of social platforms with at least 100 million active users</a> [wikipedia] <a href="https://whitepeak.io/blog/6-tips-for-successful-social-media-marketing/">6 Tips for Successful Social Media Marketing (with infographic)</a> [whitepeak.io] <a href="https://www.segmentationportal.com/mosaic7/">MOSAIC Segmentation Portal</a> [experian.com] - enroll in their free service and then get soft demographics for your zip code, which include social media preference stats <a href="https://churchcommunications.com/the-5-best-social-media-management-tools-for-churches/" rel="noopener">The 5 Best Social Media Management Tools for Churches</a> [churchcommunications.com] | 63 | 7 | 2015-02-03 05:00 | 2024-03-08 12:43 | 2000-01-01 05:00 | template: standard 2017-11-14 content updated --pb 2019-12-09 content validated --pb 2020-12-14 changed Due in # Days from 98& to 81& --pb&
202 | 592 | 1389 | Claim username on social media sites | Claim your brand online as digital real estate. | It's important to establish your digital footprint online and protect your brand. Not only does it allow you to own the digital real estate, a consistent brand online gets your church website ranked higher with search engines. If at all possible, grab the identical username at each site so that it's consistent and identifiable. Confusion One of the reason you want to claim a common user name is to prevent another church with a similar name accidentally picking it on another platform. If you're @examplechurch on Facebook, it would be tragic for @examplechurch on Twitter to be an entirely different church elsewhere in the country. There are sites where you can check name availability across the most popular platforms so you can know in advance if it's already taken, especially on the major platforms. These services also check to see if the web address of the same name is available: <a href="https://www.namecheckr.com">namecheckr</a> - "check domain & social username availability across multiple networks" (53+ domains & platforms) <a href="https://namechk.com/">namechk</a> - "see if your desired username or vanity url is still available at dozens of popular Social Networking and Social Bookmarking websites" (35+ domains, 122 social platforms plus the US Trademark database) <a href="https://knowem.com/">knowem</a> - "Search over 500 popular social networks, over 150 domain names, and the entire USPTO Trademark Database to instantly secure your brand on the internet" (<a href="https://knowem.com/signup-service.php">for a fee</a>, these guys will do the registering for you) Imposters Another reason you want to claim common usernames is that anyone with an email address can sign up for social media accounts. That means that anyone could potentially publish social media content under the name of your church. Celebrities have even gone to court to try and gain access to social media accounts created in their name. It's not difficult to imagine someone maliciously posting information to defame the church. To prevent this, your church should claim its real estate on multiple social media sites. Even though they may not be popular now, they could be next week's big thing. The general rule should be if you've heard of it, get a profile. With hundreds of social media sites available, there is no way to have a profile on all of them. Delegate this task to a team member or outside supporter. This is obviously a low priority task that can be accomplished either before launch or after. Do not lose a day yourself by going online and filling out profiles. These should be non-negotiables: <a href="https://www.facebook.com/">Facebook</a> <a href="https://twitter.com/">Twitter</a> <a href="https://www.instagram.com/">Instagram</a> <a href="https://www.youtube.com">YouTube</a> <a href="https://vimeo.com/">Vimeo</a> Consider these as well, along with myriad others: <a href="https://www.linkedin.com/">LinkedIn</a> <a href="https://www.flickr.com/">Flickr</a> <a href="https://www.pinterest.com/">Pintrest</a> <a href="https://www.tumblr.com/">Tumblr</a> <a href="https://www.stumbleupon.com/">StumbleUpon</a> | Find a social media username that you can claim across platforms. Claim that name on at least the 6 non-negotiable sites above. Recruit a volunteer to claim that username on other sites. Make sure each social media profile is completely filled out. This action is complete when the pages and/or profiles have been created at several social networking sites. |  | 77 | 14 | 2015-02-03 05:00 | 2021-10-22 04:00 | 2000-01-01 05:00 | template: standard 2018-02-16 content updated, links verified --pb 2020-01-31 additional resources subsection& added --pb 2020-12-14 changed Due in # Days from 128& to 84; name changed from "monitor online communications" --pb& 2024-03-08 overhauled content & resource links --pb
203 | 593 | 1389 | Create a response plan for online comments & reviews | Listen, engage and respond to online communication about the church. | This task is all about listening and being responsive. ### Outbound: What's the Online Chatter? People will soon be talking about your church online. How will you know what they are saying? Some of the most raw / honest feedback you can get comes from social media. Consider using one or more of these tools to listen to online communications about your church: Create a saved hashtag search using a social media management app (<a href="https://buffer.com/pricing" rel="noopener">Buffer</a>,& <a href="https://www.zoho.com/social/pricing.html" rel="noopener">Zoho Social</a>, <a href="https://vistasocial.com/pricing" rel="noopener">Vista Social</a>) Create a <a href="https://www.google.com/alerts" rel="noopener">Google Alert</a> with the "name of your church" in quotes Use advanced search on <a href="https://twitter.com/search-advanced?lang=en" rel="noopener">X (Twitter)</a> ### Inbound: How will You Respond to DMs and Reviews? Your Facebook page, WhatsApp, Yelp listing, Google Business listing, etc. should send you a notification for every direct message and review that someone posts. Make sure you're getting notified for all DMs and reviews on your listings, and be sure to respond to those promptly& to every review, whether positive and negative - usually the same day if at all possible. Many of those apps publish a rating for how quickly you respond! | Set up at least one of the 'listening' tools above. Have a friend or Launch Team member DM you through your new church social media page(s) to test that you're getting notifications. This action is complete when Google Alerts and Twitter RSS feeds have been set up to monitor online communication about the church. | <a href="https://promorepublic.com/en/blogpositive-review-response-examples/" rel="noopener">8 Powerful Examples of How to Respond to Positive Reviews</a> [PromoRepublic.com] <a href="https://www.playlister.app/blog/how-to-respond-to-negative-comments-about-your-church-on-social-media" rel="noopener">How to Respond to Negative Comments About Your Church on Social Media</a> [playlister.com] <a href="https://www.ourchurch.com/blog/how-to-respond-to-negative-online-reviews/" rel="noopener">How to Respond to Negative Online Reviews</a> [ourchurch.com] <a href="https://smallbusiness.withgoogle.com/free-google-training/how-to-respond-to-google-reviews/#!/" rel="noopener">How to reply to both positive and negative reviews</a> [google for small business site] <a href="https://growingleaders.com/podcast/three-ideas-to-handle-conflict-on-social-media/">3 Ideas to Handle Conflict on Social Media</a> [growingleaders.com podcast] | 84 | 7 | 2015-02-03 05:00 | 2024-03-08 13:17 | 2000-01-01 05:00 | template: standard 2018-02-16 content updated --pb& 2020-01-14 content updated --pb 2020-12-14 changed Due in # Days from 128& to 181& & Duration from 7 to 90; name changed from "create a facebook strategy" --pb&
204 | 1390 | 1389 | Publish simple 1-page website | Create a simple web page to publish basic information about the new church for your community. | Having already created a page or site for your donors, it's time to create a simple 1-page website for a different audience: Stage 2: Your Team As you network in the community and begin gathering a team, you're going to want a website to establish your credibility. If you're co-opting or transitioning your existing donor site, it's time to de-emphasize the 'money talk' and emphasize vision, community involvement, and recruitment. You'll write new content addressed not to the community at large, but to people that you're meeting personally. Bury the donor page in the menus or hide it from the menus so that only donors with the link can find it. If you're leaving the donor site running, you can launch another website at this point. But who wants to manage 2 websites? Stage 3: Your Community Several months before your digital launch or grand opening of in-person worship gatherings, you'll need to transition the website to its permanent audience: your community. That is covered in more detail in the subsequent PlanterPlan task <a href="/projects/project-tasks/[[project_id]]/all-tasks/584">Publish your website</a> . | Decide whether to keep your donor site running and start a 2nd website, or transition your one site to the new audience. Write basic content around vision, community involvement and recruitment. Publish the new content at the new domain name just established for your church. Have a friend test and proofread the site. This task is complete when the 1-page website is published and tested. |  | 74 | 14 | 2021-01-15 05:00 | 2021-07-27 04:00 | 2000-01-01 05:00 | template:
205 | 1391 | 1389 | Set up email capture system on church website | Install a form and/or popup on your website to encourage visitors to leave their email address. | Getting someone to visit your website can take quite a bit of effort, but that should only be another step toward getting more connected. It would be a shame if they visit your site and don't identify themselves, provide contact information, or otherwise take a next step in getting connected. Offer Something Think through what would encourage a website visitor in your context to give you their email address. Your form might say: let me know about upcoming events let me know about upcoming community service opportunities send me your monthly newsletter download free parenting guide (regarding parenting challenges in your context like drugs, porn, gangs, cyber bullying, etc) download free spiritual guide You get the idea. Just be sure you deliver on what you're offering them! | Create a plan for getting email addresses. Create the resource, etc. so you can deliver on your promise. Create the signup form or popup on your website. Use an email account you own to test the signup process. This action is complete when you have published and tested the email capture system. |  | 74 | 7 | 2021-01-15 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template:
206 | 398 | 1312 | Milestone: Develop a Staffing Strategy | Staffing (or planning for Staffing) can be one of the most important things you will do during the pre-launch period. | Staffing should come directly out of the vision for the new church. For example, if the vision includes reaching young families in the community, then an appropriate staff hire may be a children's pastor. Each staff hire should support the overall vision of the new church. In addition, each person hired should be sold out to the vision, beliefs and values of the new church. Staff members will be key players in setting the DNA of the church. A bad hire can cripple the new church and kill momentum. So the decision to hire a staff person should not be taken likely. Assess each staff member and seek the wisdom of your coach and oversight team before making any hiring decisions. This Milestone walks you through creating a custom staffing strategy and setting up your church's HR systems and the forms you'll need. | --no steps-- |  | 137 | 106 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-10-30 content updated --pb 2018-11-12 title changed from "Read this hiring staff overview" --pb 2019-12-20 content validated --pb 2020-12-14 changed Due in # Days from 63& to 51& & Duration from 7 to 1& --pb&
207 | 399 | 398 | Read this Staffing Strategy overview | Understand the impact your initial hiring decisions and HR systems have on your church plant. | Even if your first hire isn't immediate, there are some things you need to know about hiring church staff. The following tasks included in this Milestone will help you think through timing, hiring order, and setting up HR systems for your church. You Need a Process You need to follow a disciplined hiring process for several reasons: It helps you explain and set expectations with the candidate(s) It keeps you from skipping important steps It helps you avoid discrimination lawsuits In addition to having a good process, be sure to add an Employment Practices rider to your church insurance policy. Ministers and Housing Allowance Ministerial housing allowance is perhaps the last great tax advantage available to clergy. Calculating it and administering it can be tricky, so it will be important to learn some of the basics: The Management Team or oversight needs to approve housing allowance requests in writing in advance (never retroactively) The church should have some record of the pastor's ordination, commission or license to substantiate designating part of their pay as housing allowance Housing allowance income is only exempt from income taxes, not social security tax (technically self-employment tax) If they were a non-clergy employee, the church and the employee would each pay 7.65% tax for social security; on at least the housing allowance, the pastor has to pay the entire 15.3% themselves The church cannot withhold social security tax from the pastor's paycheck, but they can withhold extra income tax at the employee's request; that overpayment washes out the social security (self-employment) tax when the employees file their own taxes There are Hidden Costs If you've never been a hiring manager and budget creator before, you need to know that the price tag of each employee is higher than the pay package you'll offer them: The church must pay a 7.65% social security tax on the salary portion of their pay (not any housing allowance) In most every state, you'll also be paying for Workers' Comp insurance You may have software subscriptions that are per user; those costs will increase with a new hire (ex: email accounts) A good rule of thumb is to gross up their pay by 10% to estimate their true price tag for budgeting purposes (ballpark). So the cost of a part-time hire of $1,000/mo will cost your church closer to $1,100/mo. A Bad Hire Could Derail Your Church Plant It's crucial to make the right decisions the first time. An employee that goes rogue could split the church. An employee who consistently underperforms will create a financial and relational drag. But an employee with the right heart and team chemistry will grow your church's capacity to make an impact in your community. Calling, Character, Competency, Chemistry Hire slow and fire fast. Chemistry is the hardest of the 4 C's of Hiring to figure out in the hiring process (calling, character, competency & chemistry). Just remember that new skills can be learned. If the chemistry is bad, working with them will be like sandpaper. Churches tend to hire based Competency and fire based on Chemistry. Passion for Planting strongly recommends having all final-round candidates go through an online church planter pre-assessment (see tasks in the previous Milestone Affirm the Calling ). You'll get personality profiles and other important insights into your candidate. And if they're a full-time hire or someone who will be the 'face' of the church like your worship leader, consider sending them through a full assessment process prior to making a job offer. | Watch the <a href="/resources/item/98">Hire Staff training video</a> by Dr. Ed Stetzer. Take notes on what you learn; include your resulting actions steps into your written Staffing Strategy. This action is complete when you have watched the Hire Staff training video. |  | 51 | 1 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated, audience changed to coach --pb 2018-04-20 content updated, audience changed back to planter --pb 2018-11-12 title changed from "Call your coach about hiring staff" --pb 2020-01-24 content updated --pb 2020-12-14 changed Due in # Days from 63& to 57 --pb&
208 | 400 | 398 | Call your coach about staffing | Open a conversation with your coach about finding and hiring staff. | Staffing is one of the most important things you will do during the pre-launch period. Staffing should come directly out of the vision for the new church. If the vision is to reach young families in the community, then an appropriate staff hire may be a children's pastor. Each staff hire should support the overall vision of the new church. In addition, each person hired should be sold out to the vision, beliefs and values of the new church. Staff members will be key players in setting the DNA of the church. A bad hire can cripple the new church and kill momentum. Sample issues to process with your coach: Where to find staff How to set staff hiring priority order Creating a hiring time line Using interns Avoiding hiring mistakes | This action is complete when you have called your coach about hiring staff. |  | 57 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-10-30 content and links validated --pb 2018-03-07 Additional Resources subsection added --pb 2018-06-01& gdoc& template added --pb& 2019-12-20 content updated --pb 2020-12-14 changed Due in # Days from 77& to 71& & Duration from 7 to 14& --pb 2022-11-21 updated links --sc
209 | 401 | 398 | Craft a Staffing Strategy | Put together a document that includes everything about when and how you'll hire staff. | The Staffing Strategy will help you identify your initial plans for hiring. It takes all of the key output from the following sub-tasks tasks and puts it into a single document. Work through the following sub-tasks and put your completed answers in the Staffing Strategy Template (below). Identify which staff positions to pursue Determine hiring timeline Decide on staff fundraising expectations Decide on which benefits to offer, especially whether or not to offer health care insurance Create a step-by-step hiring process Be sure to include the following key information: Which roles you'll fill with paid staff Which roles you'll fill with volunteers How you might use interns Which jobs can be grouped together into a full-time staff role Prospective hire dates for each role | Download Passion for Planting's Staffing Strategy Template (<a href="/resources/item/67">MS Word</a> or <a href="/resources/item/377">Google Doc</a>). Fill in the blanks to develop your own Staffing Strategy. Complete all the subordinate PlanterPlan tasks. Send the written Staffing Strategy to your coach for feedback. This action is complete after you have sent your written staffing strategy to your coach for feedback. | <a href="https://www.executivepastoronline.com/finding-staff/">The "6 Steps" To Successfully Finding Church Staff Members</a> on executivepastoronline.com <a href="https://www.executivepastoronline.com/writing-job-descriptions/">Writing Job Descriptions</a> on executivepastoronline.com | 78 | 21 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-06-20 updated resource links --pb 2017-10-30 content updated --pb 2018-04-15 moved blog link to new Additional Resources subsection --pb& 2019-12-20 content updated --pb 2020-12-14 changed Due in # Days from 70 to 64 --pb& 2022-11-21 updated links --sc
210 | 402 | 401 | Identify which staff positions to pursue | Make strategic decisions about which staff roles should be filled first. | The order that you fill staff positions should come straight out of your Vision Frame. Decide which positions are most strategic to hire first. List out the first 5, regardless of when they might be hired: Does it make sense to hire a children's director before a worship leader? How about hiring a communications director before either of those? Does your hiring order support or contradict your strategy, mission and values? | Identify positions that are essential to implementing the vision. Note which could be full-time and which could be part-time hires. Identify positions that could initially be filled by key volunteer leaders. Based on all the above, rank the positions from highest to lowest priority. Incorporate the results into your Staffing Strategy document. This action is complete after you have identified the specific order of staff positions to pursue. | <a href="https://seniorpastorcentral.com/2830/staff-churches-under-600/">How to Staff Churches Under 600</a> on Senior Pastor Central <a href="https://theunstuckgroup.com/problems-too-many-church-staff/">Problems Develop When You Hire Too Many Staff</a> by Unstuck Group | 64 | 7 | 2015-02-03 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-11-10 content validated --pb& 2019-12-20 content updated --pb 2020-12-14 changed Due in # Days from 70 to 64 --pb&
211 | 403 | 401 | Set a hiring timeline | Set target hiring dates for each staff role. | Finding the right staff can take time. Set some timing goals for bringing new staff on board since it could take months to find the right people. Consider these factors that are in tension with each other: Hiring early allows more pre-launch tasks to be completed, more relationships to be established, and a healthier foundation for growth. In some cases, you need the staff on board early enough to prepare critical areas for the Opening Day of worship gatherings. For example, a worship leader needs several months to recruit, train and prepare a worship team for the Opening Day of worship gatherings. However, early hiring costs more money (unless new staff will raise their own support). Money may drive the timing of staff hires. Think in terms of both dates and trigger points. For example, you'll hire an administrator next Spring or when we get to average attendance over 200. | Contact at least one other church planter and ask them when they recommend hiring for various positions. Prayerfully consider the cost/benefit of when to hire each position. Set target dates and trigger points for hire for each staff position. Incorporate the results of this task into the written Staffing Strategy document. This action is complete after you have written down a target date and trigger point for hiring each new staff position in your Staffing Strategy. |  | 64 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-11-10 content updated --pb 2018-10-12 task rename from 'determine contents of compensation package' --pb 2019-02-08 added health insurance options subsection -pb& 2019-12-20 content updated and links verified --pb 2020-12-14 changed Duration from 21& to 14& --pb&
212 | 1241 | 401 | Decide on staff fundraising expectations | Decide whether or not you'll ask secondary staff to raise funds in order to come on payroll. | Church planters who start as paid staff almost universally have to raise funds for the church. They're not 'raising money for their salary', but the funds they raise do lessen the financial strain of the salary on the new church. If you're hiring secondary staff, will they have to raise funds, too? Some Things to Consider Your secondary staff may have less fundraising capacity than you: If they haven't been in ministry as long, they'll have smaller relational networks They probably won't have as much experience in raising funds as you If they're the first to come to Christ in their family, they may not have as much success getting commitments from their extended family If they grew up in an under-resourced community, the commitments they get may be smaller If you're hiring them part-time, they have less time to devote to fundraising than you do They may need to raise some funds before they come on staff. How else will you pay for their first month's salary? It's wise to set a commitment goal and/or a cash-in-hand goal as a prerequisite to going the paid staff. For example, the employee can start payroll when they have 75% of your goal in commitments and the equivalent 3 months' salary is on deposit in the church's account. One of the biggest decisions is what to do if their fundraising comes up short once they're on payroll: pay them anyway (and strain the church)? pay them according to their results (and strain their family finances)? something between those two? If their pay is tied to their performance, be sure to communicate a ceiling , too - if they raise $10,000 one month you're not going to pay them $10,000. Fundraising Requirement Options Here are common fundraising requirement constructs for secondary staff. These are conceptual - you may not want to use this as the exact legal language to put in writing. Pick a construct and over-communicate it to the candidate before they're hired : No requirement - secondary staff will not be required to raise funds Full support - secondary staff raise their full salary Half support with guarantee - staff raise the other half of their salary but are paid full salary regardless of their performance Half support with no guarantee - staff raise the other half their salary but may get paid as little as the church's half depending on their fundraising performance Other...? You'll need to be very specific | Decide whether or not to require secondary staff to raise funds. Decide what kind of progress, if any, they'll need to make before coming on payroll. Decide which fundraising requirement construct (above) you'll use. Include your decisions in your Staffing Strategy document. This action is complete when you have made decisions about staff fundraising requirements and will be able to articulate them clearly to all staff candidates. | <a href="https://www.churchplantingtactics.com/church-plant-staff-fundraising-requirements/">How to Give Your Church Plant Staff Fundraising Requirements</a> on churchplantingtactics.com <a href="https://www.churchplantingtactics.com/church-plant-staff-fundraising/">2 Important Ways Church Plant Staff Fundraising is Different</a> on churchplantingtactics.com | 64 | 7 | 2018-10-12 04:00 | 2019-12-20 05:00 | 2000-01-01 05:00 | template: 2018-11-12 new task --pb 2019-12-10 date fields found empty & 2019-12-23 content updated --pb & 2019-12-11 date fields re-entered manually --pb
213 | 404 | 401 | Decide which benefits to offer | Decide what will and will not be included in compensation packages for staff. | Compensation How you set appropriate pay? The amount should always be based on the responsibilities/demands of the position and the experience of the applicant. The IRS is also watching for the compensation to be no more than about what other churches of similar size or paying for those same staff positions, so do some comparison. Here are some useful tools for comparison: <a href="https://ministrypay.com">MinistryPay.com</a> <a href="https://www.xpastor.org/courses/church-compensation/">Compensation Survey</a> by XPastor.com <a href="https://www.churchsalary.com/">ChurchSalary</a> from Church Law & Tax <a href="https://www.amazon.com/dp/0917463765/ref=cm_sw_r_tw_dp_U_x_J6w.DbPX3RC5G">Compensation Handbook for Church Staff</a> by Richard Hammar <a href="https://compstudy.lifeway.com/homepage.do">SBC Compensation Study</a> Keep compensation levels "fair" between positions. A great way to do that is decide in advance what the staff position pay range is, based on responsibility and expectations. Then compare the pay range of the new position with what all other current positions are being paid. Benefits What should be included in a benefits package? You need to decide whether to include any of the following: Paid time off - Will the church pay vacation & sick leave, or combined PTO? Paid holidays? Health Benefits - Will the church pay all, none, or partial benefits? Will there be a group plan or will each employee get their own individual plans? Which health benefits will be included (e.g., major medical, dental, vision)? Housing Allowances -Ministers are allowed to designate a portion of their income as a non-taxable housing allowance. Will the church provide an actual parsonage or allow the minister to designate a housing allowance? Life Insurance? Disability Insurance? Retirement benefits? To avoid discrimination claims, don't decide individual benefit packages with each new hire. Decide in advance on benefits packages based on employment classification. For example: full-time, credentialed clergy get XYZ other full-time employees get XY part-time employees ( Health Care Insurance Options Popular options include: <a href="https://www.healthcare.gov/">healthcare.gov</a> (Obamacare for individuals) <a href="https://www.churchplantingtactics.com/obamacare-for-church-plants/">SHOP</a> (Obamacare employer plans) <a href="https://www.medishare.com/">Medishare</a> <a href="https://samaritanministries.org/">Samaritan Ministries</a> <a href="https://www.guidestone.org/Organization/Insurance">GuideStone</a> | Decide what will be included in benefits packages for each employment classification. Determine your philosophy for setting compensation. Incorporate these answers into your written Staffing Strategy. This action is complete when you have recorded your church compensation package details in your Staffing Strategy document. Additional Resources <a href="https://www.churchplantingtactics.com/how-much-to-pay-church-plant-staff/">How Much to Pay Church Plant Staff</a> (2 part series) on churchplantingtactics.com <a href="https://www.executivepastoronline.com/market-comparison/">Market Comparison: A Critical Part Of Any Organization's Compensation Program</a> on executivepastoronline.com <a href="https://www.churchplantingtactics.com/church-plant-health-insurance-options/">11 Church Plant Health Insurance Options</a> on churchplantingtactics.com <a href="https://www.churchplantingtactics.com/2-hidden-costs-in-hiring-church-plant-staff/">2 Hidden Costs of Hiring Church Plant Staff</a> on churchplantingtactics.com <a href="https://www.clergyfinancial.com/vacation-paid-time-off/">Is it Vacation or Paid Time Off?</a> on clergytaxnet.com <a href="https://www.churchplantingtactics.com/paying-church-interns-by-stipend/">Paying Church Interns by Stipend</a> on churchplantingtactics.com <a href="https://www.churchplantingtactics.com/church-plant-staff-fundraising-requirements/">How to Give Your Church Plant Staff Fundraising Requirements</a> on churchplantingtactics.com |  | 71 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-20 resource link updated --pb 2017-11-10 content validated; changed Parent ID from 398 (Milestone: Hire Staff) to 401 (Task: Issue Written Staffing Strategy); also changed Task Type to Child --pb 2018-02-21 additional resources subsection added --pb 2020-12-14 changed Due in # Days from 77& to 70& --pb & 2019-12-20 content updated and links verified --pb 2018-06-01& gdoc& template added --pb 2018-11-15 title changed from "Define and Implement Hiring Process", content updated, demoted to child task type --pb 2020-08-28 added LinkedIn& resource --pb 2022-11-21 updated links --sc
214 | 411 | 401 | Create a step-by-step hiring process | Create a disciplined and formal step-by-step process for hiring new staff. | You need to have a step-by-step process for hiring staff for lots of reasons: keeps the process consistent from candidate to candidate (so you don't get sued for discrimination) makes you do things in the right order so you don't sued (ex: asking for their date of birth for a background check before sending them a job offer letter - that's grounds for an age discrimination suit) helps you not accidentally skip steps that might have kept you from hiring the wrong candidate allows you to communicate clear next steps to candidates Brain surgeons use checklists because what they're doing is so important they can't afford to skip steps or do things in the wrong order. Follow their example as you hire staff for your church. You'll have a better experience (so will the candidate) and you'll be much less likely to make a bad hire. We have provided a starter hiring process in the Staffing Strategy Template for you! | Review the process already included in the Staffing Strategy Template (<a href="/resources/item/67">MS Word</a> or <a href="/resources/item/377">Google Doc</a>). Add, remove or reorder steps with great caution . This action is complete when you have finalized and committed to using a disciplined hiring process. | <a href="https://loganleadership.com/screening-interview-prospective-staff/">10 Steps for Screening and Interviewing Prospective Staff</a> on loganleadership.com <a href="https://www.hrministrysolutions.com/hiringtoolkit">FREE Church Hiring Toolkit</a> from HR Ministry Solutions | 71 | 14 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2017-11-10 content validated --pb 2019-12-23 content updated --pb 2020-12-14 changed Due in # Days from 84& to 78 --pb&
215 | 418 | 398 | Coaching Checkpoint: review and affirm Staffing Strategy | Ensure that the planter is equipped to hire staff. | Many church planters have never been a hiring manager before. It may come as second nature what position they should hire for next, or they may be making default assumptions that don't necessarily work in their context. Many more have never been involved in budgeting for hires nor making sure that basic HR procedures are followed in the hiring process. Most planters need a good check-up when it comes to staffing. Read the planter's Staffing Strategy document. The who and when of hiring should come directly out of the vision for the new church - each hire should support the vision. The planter should only hire candidates that are sold out to the vision, beliefs and values of the new church. Staff members will be key players in setting the DNA of the church. A 'bad hire' can cripple the new church and kill momentum. Given a planter's entrepreneurial wiring, they may be tempted to cut corners and rush the hiring process. Poke around and find out how they'll test the chemistry and really get to know the candidate before calling them to join the staff. The planter's Staffing Strategy should include: Staff positions to pursue A hiring time line Staff fundraising expectations Content of compensation package A step-by-step hiring process Consider the values and strategies included in the planter's Launch Strategy document and make sure that their Staffing Strategy adequately supports it. | Review the planter's completed Staffing Strategy. Challenge their assumptions and test their understanding. Give the planter feedback. This action is complete after you, the coach, have given the planter feedback on the Staffing Strategy. |  | 78 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-11-10 content updated and new resource link added --pb 2018-11-12 renamed from "Initiate personnel records filing system" to "create & secure personnel files" --pb &
216 | 1246 | 398 | Create initial HR forms | Compile a library of forms you'll use in the hiring process for prospective employees. | One of the disadvantages of establishing the church as a new, legally autonomous legal entity is that you have to create new HR systems from scratch. If you're hiring staff, they will be employees of the new church. You have legal and tax responsibilities to cover. And if a disgruntled employee sues, they're suing the new church, not some other entity. Do things right from the beginning by setting the new church up with responsible hiring practices that honor the employee and protect the church. HR forms you will need include: <a href="/resources/item/382">Job Description Template</a> <a href="/resources/item/385">Employment Application Template</a> <a href="/resources/item/245">Interview Questionnaire</a> <a href="/resources/item/248">Reference Check Questions</a> <a href="/resources/item/72">Job Offer Letter Template</a> <a href="/resources/item/384">Authorization to Release Information form</a> <a href="/resources/item/344">Personnel File Checklist</a> | Compile your library of HR forms by downloading and customizing each of the forms above. File the electronic versions of the forms where hiring managers and church leadership can access them. Commit to using these forms in every hiring process. This action is complete when you have created a starter library of HR forms in an electronic file/folder where leaders can access it. |  | 78 | 14 | 2000-01-01 05:00 | 2019-12-23 05:00 | 2000-01-01 05:00 | template: 2018-11-19 new task 2012-12-02 content validated --pb 2020-12-16 changed Due in # Days from 148& to 155 --pb&
217 | 437 | 398 | Create and secure personnel files | Comply with legal requirements by creating and maintaining a personnel file on each employee. | Begin personnel files for each of your employees on the date they are hired. Personnel files are used to keep track of important legal documents regarding the employee, as well as to keep a record of the employee's performance. What do you need to keep in the personnel files? You'll actually need 3 folders for each employee and 1 common file for the Federal I-9s. You have to do that because there are certain records that shouldn't be seen by supervisors but do need to be seen by an HR manager: Employee Personnel File Completed onboarding checklist R&eacute;sum&eacute; and cover letter Job application Job description Signed acknowledgements (policies, etc.) Performance reviews, awards & commendations Copies of ordination paperwork Training records Complaints against employee Disciplinary records Separation documents Confidential Records File Signed authorization to perform background check ADA accommodation records Anything that might identify a protected class (age, race, etc.) Compensation Records File Job offer letter Benefits information Employee's signed W4 Employee's signed State Withholding form (as applicable) Housing Allowance designation requests Direct deposit forms Vacation requests and/or records (salaried employees) Time cards (hourly employees) Federal I-9's one common file for all employees' completed I-9s In a church, it may seem overkill to keep all of this in personnel files. However, remember that as a pastor, part of your job is to train and equip. Keeping a detailed record of each employee's evaluations, yearly goals/plans, and even complaints can help you to maximize their potential. Accountability for performance should be taken just as seriously in the church as in the business world. | Download the <a href="/resources/item/344">Sample Personnel File Checklist</a> which includes all of the above. Determine where to house personnel files. If you don't have them already, purchase files and a locking file cabinet. Gather documents for any existing employee of the church and file them. This action is complete when you have created personnel files for each employee and developed a system for keeping them up to date. |  | 135 | 7 | 2000-01-01 05:00 | 2019-12-23 05:00 | 2000-01-01 05:00 | template: standard 2017-11-10 content updated --pb 2018-11-12 added "...for Current Staff" to title --pb 2019-03-25 additional resources subsection added --pb 2019-12-12 content updated --pb 2020-12-14 changed Due in # Days from 154& to 58 --pb&
218 | 446 | 398 | Create a Staff Policy Manual | Create a written Staff Policy Manual to set clear staff expectations and meet various legal requirements. | Clear expectations are critical to forming healthy staff relationships. A staff policy manual not only serves legal purposes, but helps the entire staff to know what is expected. It is far easier to proactively set and communicate expectations than to deal with controversy later. Having to let a staff member go is never easy. It will be harder if there is ambiguity or controversy surrounding expectations. You have several options for developing a staff policy: Borrow and adapt a handbook from another church Customize Passion for Planting's <a href="/resources/item/247">Staff Policy Handbook Template</a>. Develop a Staff Policy Manual from scratch Purchase a template from a commercial vendor and customize it Hire a church HR support ministry to help you craft it Consider policies on vacation, hours worked, and days off. As a manager, be very clear with new hires about the expectations of work at the church. Below is a sample index of topics recommended to be included in a staff policy manual: Major Topics Basics Housing Allowance Social Security Medical Allowance Salary Packages Travel Transportation Business Expenses Vacation, Work Days, and Work Hours Basic Expectations for All Staff Tax Reporting Policies and Forms Annual Housing and Medical Allowance Designation Form Mid-Year Amendment to Housing or Medical Allowance Request Medical Plan/Policy Travel Reimbursement Plan/Policy Travel/Vacation Request Form Travel Reimbursement Request Form Transportation Reimbursement Log Expense Reimbursement Plan/Policy Expense Reimbursement Request Form | Decide which option to pursue for developing a staff policy manual. Customize it. Adopt it by vote of your board or oversight team (several policies are required by the IRS to be approved by the Church Board). This action is complete when the Staff Policy Manual is approved by the Board and issued for use. | <a href="https://www.clergyfinancial.com/dont-let-your-employee-handbook-collect-dust/">Don't Let Your Employee Handbook Collect Dust</a> by Clergy Financial Resources <a href="https://www.executivepastoronline.com/how-to-write-a-staff-policy-manual/">How to Write a Staff Policy Manual</a> by Executive Pastor Online HR Ministry Solutions' <a href="https://www.hrministrysolutions.com/staffhandbooks">Custom Staff Handbook service</a> | 135 | 14 | 2000-01-01 05:00 | 2021-01-18 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content validated --pb 2019-11-20 title updated from "Develop a Reproducing Leader Culture" --pb 2019-12-03 content validated --pb 2020-12-16 changed Due in # Days from 168& to 159& & Duration from 14& to 111& --pb&
219 | 590 | 398 | Develop Social Media Policies | Create clear boundaries for staff social media engagement. | Eventually you'll need to have more than one person, whether staff or volunteer, actively participating in the church's social media. Before that happens, create some boundaries for consistency and safety. Promoting Community Impact Write out a clear set of expectations and boundaries so that anyone participating in social media on the church's behalf won't damage the church's reputation. Social media creates an impression. Careless, callous or prejudicial words have no place on a church's page. Nor does a tirade against the church's leadership belong on a staff member's personal page. Staff members represent the church even when they are not 'on the clock'. But simple maintenance can affect your impact, too. Just like a website that is poorly maintained creates a negative impression, a poorly maintained social media page will also create a negative impression. If someone comments on the church Facebook page and does not get a response for two weeks, they'll think you don't care about them. Safety Restrictions are important as well, especially for kids' sake. We all love posting about our own kids, but posting pictures of kids at church could reveal the location of certain kids to people who shouldn't know. Foster families are often legally restrained from posting images of their kids online. Just as we go the extra mile to protect kids with secure sign-in and sign-out procedures, we need to protect kids with good social media policies. That also means you can't have a public RSVP for events for youth or children. This is a safety hazard -it alerts sexual predators, estranged parents and others who would harm a child to the child's location. The policies should fall into two broad categories: Sample expectations: Posts should be made (daily/weekly) Spend at least (1 hour a week) maintaining the church's profile & feeds Publish all scheduled events to social media and the church website Sample restrictions: No pictures of kids without parental consent Never give out members' contact information No public RSVPs for events for youth or children | Create a list of social media expectations. These expectations should support the goals created in a previous PlanterPlan action. Create a list of social media restrictions, giving special attention to children. Create a social media policy for staff members. <a href="/resources/item/319">Here's a template to get you started</a>. Consider including it in your Staff Policy Manual. Communicate these policies with the staff and social media team. This action is complete when everyone participating in social media on the church's behalf understands the expectations and boundaries of their participation. | <a href="https://churchmarketinguniversity.com/social-media-policies-churches-ministries/">The Ultimate List of Social Media Policies for Churches & Ministries</a> by socialchurch.co [includes links to templates & samples] <a href="https://s3-us-west-2.amazonaws.com/church-marketing-university/Church+Social+Media+Policies/Lifechurch.tv+Social+Media+Policy.pdf">Sample Social Media Guidelines</a> (Life Church) <a href="https://churchmarketingsucks.com/2017/03/create-church-social-media-policy/">How to Create a Church Social Media Policy</a> by churchmarketingsucks.com | 135 | 7 | 2000-01-01 05:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: standard 2018-07-13 updated title & tweaked content --pb 2020-12-14 changed Due in # Days from 128& to 77& & Duration from 7 to 14; name changed from "create pages on social media sites" --pb&
220 | 1291 | 398 | Plan for effective staff meetings | Create a rhythm and format for regular staff meetings, whether with volunteer or paid staff. | Death by Meeting. It's such a common plague that business author Patrick Lencioni wrote a book about it. Does that sound like staff meetings you've been a part of in the past? You have the chance to set a new DNA for healthy, useful staff meetings in this new church. What you establish now will become the norm for years to come. Lencioni's <a href="https://files.tablegroup.com/wp-content/uploads/2020/12/14163149/Avoid-Death-by-Meetings.pdf">meeting model</a>, easily found online, is: Daily Check-Ins Weekly Staff Meeting Adhoc Topical Quarterly Off-site Review Whether you have paid staff or key volunteer leaders, you have the opportunity to create a culture of meetings that inspire and energize. | Decide how often to have staff meetings. Decide how long the meetings should last. Decide whom to invite to the meetings. Put the meetings on your calendar and invite your staff. This action is complete when you have recurring staff meetings on the calendar. " | <a href="https://www.amazon.com/dp/0787968056/ref=cm_sw_r_tw_dp_U_x_wH2SDbPMP69MT">Death by Meeting: A Leadership Fable About Solving the Most Painful Problem in Business</a> by Patrick Lencioni Watch <a href="https://www.youtube.com/watch?v=joAVJYqQ38Q">How To Run Your Meeting </a>by thetablegroup.com (Lencioni) | 171 | 14 | 2019-11-01 04:00 | 2022-11-21 05:00 | 2000-01-01 05:00 | template: 2019-12-03 due date fields found empty --pb 2020-12-11 changed Due in # Days from 55& to 49& & Duration from 7 to 1 --pb&
221 | 1271 | 1312 | Milestone: Begin Scouting for Facility | Begin actively searching for the facility that will accommodate your weekly worship gatherings. | While you aren't ready for weekly worship yet, it can take months to find the right facility, negotiate terms, and finally get to a signed agreement. Start that hunt now so that when you get to your 8th small group, you can put the pedal to the metal toward launching weekly worship gatherings. If you wait to hunt until you've launched your 8th group and it ends up taking 6-9 months to finalize, you may have forfeited your team's excitement and momentum. |  |  | 234 | 220 | 2019-10-14 04:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: 2019-12-10 date fields found empty 2019-12-11 date fields re-entered manually --pb 2020-01-14 fixed broken links that were pointing to resource on Dev server --pb 2020-11-19 added the section about Digital Tools 2020-12-11 changed Due in # Days from 21& to 36 & Duration from 7 to 14 --pb
222 | 705 | 1271 | Read this facility selection overview | Open your eyes to the various complicated things you have to consider when hunting for a facility. | When setting out to find your worship gathering facility, there are lots of things to consider: Capacity Constraints (what will you run out of first: seating? parking? etc) Atmosphere Reputation in the Community (How is this building perceived?) Location, Location, Location Accessibility for the Community Hidden Make-or-Break Topics Just as important as that initial checklist are some hidden make-it-or-break-it items: electrical capacity - is the whole worship room wired on one circuit? You'll trip the breaker for sure with all your AVL equipment competing events - how likely is it that your church would get moved to another room or bumped entirely by another event? included equipment - if they allow you to use their sound, projector, etc., is it worth the risk that a volunteer might break it? perception - would your target families be endeared or repelled by how they perceive the facility? restrooms - are they far, too close (flushing can be heard), without HVAC, permanently stinky, or have small-sized toilets for kindergarteners? cleanliness - does the school custodian clean the facility Friday after school or Sunday night before school starts the next week? aroma - Nightclubs, gymnasiums and older YMCAs can have a lingering or stale odor that is difficult to mask with aerosols and air fresheners social space - is there a big enough lobby, patio, etc. that people will linger and make friends? layout - is the parking on the opposite side of the building from the entrance? Will the children's ministry area be a day's walk from the worship gathering room? Pros & Cons of Different Facility Types Facility Type Pros Cons Schools High Schools are typically well-known locations Schools are typically well-respected in their community Diverse room sizes typically available - both for adults & children Sufficient electrical capacity Elementary schools are often tucked away in residential neighborhoods Elementary schools typical maximum capacity is 200/service Middle schools typical maximum capacity is 400/service High schools typical maximum capacity is 600-1600/service Movie Theaters No school boards or Separation of Church & State misunderstandings to overcome Large video screen already built-in Movie theaters are generally well-known locations Seeker friendly Refreshments allowed in worship gathering area Large parking lot Worship gathering area may be too dark to read handouts "High traction" flooring often included May have limited electrical capacity May have tight time constraints (have to be out before matinees start) Space for children's ministry is often a challenge Church Buildings You might get the space cheap or even free Can be a great partnership with another congregation Older buildings especially may have a hip, ancient-future vibe Probably a barrier for people who have never been to church May create confusion about which church is which Older buildings particularly may be worn/tired or not ADA-compliant Other Facilities Can attract young professionals not ready to 'go back to grade school' Can be more suitable for artisan/experiential worship Might be confusing or send mixed signals If it's not designed for audiences or presentation, it may have limited sight lines or insufficient stage area Can have limited options for children's ministry | Read the excerpt above from the Portable Church Industries blog. Read the article <a href="/resources/item/90">Finding a Facility</a> by Mark Driscoll (still a good read). Watch the Passion for Planting training video "<a href="/resources/item/89">Select a Facility</a>" featuring Ed Stetzer. Optional: Create a interactive map with <a href="https://support.google.com/mymaps/answer/3024454?hl=en">Google Maps </a>and share it with your Launch Team and Management Team. Create a secondary layer for potential worship facilities (layers can be toggled on/off). This action is complete when you have read the overview above. Some of this task description was adapted from "<a href="https://portablechurch.blogspot.com/2006/03/how-to-choose-right-facility-for-your.html">How to Choose the Right Facility for Your Portable Ministry</a>" by Portable Church Industries. |  | 32 | 1 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-22 content updated --pb 2017-05-31 audience changed to coach --pb 2019-12-17 content updated --pb 2020-12-14 changed Due in # Days from 98& to 38 --pb &
223 | 706 | 1271 | Call your coach about finding a facility | Open a conversation with your coach about finding a worship facility. | Identifying a worship gathering facility can be the biggest bottleneck in a church plant timeline. So many other decisions hinge on where you'll meet. Sample issues to process with your coach: A facility's effect on the church's DNA How to narrow the list Choosing between 2 imperfect options What do do about office space | This action is complete when you have called your coach about finding a facility. |  | 38 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-22 content & resource links updated --pb 2019-12-17 content updated & links verified --pb 2020-12-14 changed Due in # Days from 98& to 93; name changed from "Decide what's most important in a worship facility" --pb&
224 | 707 | 1271 | Set your worship facility selection criteria | Use this worksheet to decide what's most important in a worship facility before touring any potentials. | Sometimes selecting a facility comes down to choosing between 2 or 3 imperfect options. The Facility Selection Worksheet will help you think through your priorities before getting enamored with a particular facility that might not be your best choice. The worksheet has 2 simple steps. This PlanterPlan task guides you through completing the first: Step 1 - Rank Criteria : Decide in advance which criteria are most important to you in selecting a facility, such as children's space, parking, visibility of location, etc. The second step will be completed in the subsequent PlanterPlan task Rank Facilities Using the Facility Selection Worksheet . | Download the <a href="/resources/item/87">Facility Selection Worksheet</a> and rank your criteria for the perfect worship facility. This action is complete when you have decided on the most important deciding factor in choosing a worship facility. | <a href="https://www.churchplantingtactics.com/5-church-plant-facility-lease-surprises-avoid/">Five Church Plant Facility Lease Surprises to Avoid</a> on churchplantingtactics.com | 93 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2018-10-10 added 'additional resources' subsection --pb 2020-12-14 changed Due in # Days from 98& to 76& & Duration from 7 to 14& --pb&
225 | 708 | 1271 | Decide whether to rent or build out | Make an early decision on whether to hunt for rented Sunday-only worship space or lease a 24/7 facility you'll build out. | Finding a meeting place is a major issue for most new churches. Though some new churches might like to buy a facility, it's not possible for most. Usually the decision comes down to leasing a 24/7 facility or renting a one-day-a-week facility. In summary, the options include: Leasing a 24/7 facility - This can be very expensive, but may be necessary in certain contexts to establish credibility in the community. Construction always comes in late and over budget - more than one church planter has had to delay Opening Day of worship gatherings due to construction delays. Renting Space just for Worship - This is the less expensive option but it only gives you space for several hours on Sunday (or whatever day you meet). Some churches that take this path also rent 24/7 office space. For examples of Sunday space, download Passion for Planting's <a href="/resources/item/83">Facility Brainstorming Worksheet</a>. | Prayerfully consider the primary facility options in light of your financial resources and contextual needs. Decide whether to rent a worship-only facility or a lease a 24/7 facility for worship gatherings. This action is complete when you have made an initial decision on whether to rent or lease a facility. | <a href="https://www.portablechurch.com/2021/facility/facility-cost-comparison-matrix/">To Build, Buy, Lease or Rent&hellip; that IS the Question</a> on portablechurch.com | 76 | 14 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2019-12-17 content updated --pb 2020-12-14 changed Due in # Days from 127& to 143& & Duration from 90& to 82& --pb& 2020-12-23 name changed from "Secure a worship gathering facility" --pb
226 | 718 | 1271 | Identify a worship gathering facility | Work through the necessary due diligence to get to a signed worship facility contract. | The facility you choose will impact the church's ability to grow for years to come. Find a facility which is safe for newcomers and easy to find. Your facility also speaks volumes about who you are as a church and significantly shapes your community's first impression of the church. The subtasks following this will walk you step-by-step through: making contact with management as appropriate, getting on a waiting list touring top facilities prioritizing and narrow your list ranking the top prospects assessing demographics near top facilities making a final choice negotiating and signing a contract Start Making a List Start with the obvious choices you have undoubtedly been cataloging in your mind. Work the steps and you may just end up with an ideal facility. If you exhaust that list, brainstorm every possible facility option you can think of (schools, colleges, community centers, movie theatres, etc). Find out whether any new schools are being built and add them to your list. Visit your local county or city planning office and get a list of every organization with an occupancy permit of over 200 (or a lower number dependent on your expected attendance). This list will help you identify facilities in your area where large groups are allowed to meet. If you need more ideas, download Passion for Planting's <a href="/resources/item/83">Facility Brainstorming Worksheet</a>. | Jot down the obvious choices you've already been considering. If there are no obvious choices, or none of your first options are available, brainstorm a list of all possible meeting locations. Work through the following subtasks until you have a signed facility contract. This action is complete when you have a signed facility contract for the church's worship gatherings. | <a href="/resources/item/83">Facility Brainstorming Worksheet</a> by Passion for Planting | 135 | 74 | 2000-01-01 05:00 | 2020-12-23 05:00 | 2000-01-01 05:00 | template: standard 2017-05-22 content updated --pb 2019-12-17 content updated --pb 2020-12-14 changed Due in # Days from 108& to 110& & Duration from 48& to 49& --pb&
227 | 719 | 718 | Establish contact with management at prospective facilities | Establish a point of contact with each facility you are considering. | Meet in person with as many different facility contacts as possible. The purpose of the meeting is to establish a relationship with the facility management and to ask about whether they might rent it to a church for worship gatherings. The relationship with the management will be key to the success of the church for years to come. Starting on the right foot will pay dividends. Do everything in your power to make friends, not enemies. Your secondary purpose is to scout the facility to see if it might fit your needs. Get Contact Information This is a great networking opportunity completely independent of whether you contract their facility or not. Consider this your first major networking goal: to meet with every potential facility contact in your area. At a minimum, you need to get your contact's name and a phone number. If you're able, get an email address, too. The Decision-Maker Your local point of contact may or may not be the ultimate decision-making on renting the facility to you. But either way, it's their house you'd be renting. For example, if you're renting a public school, you'll initially build a relationship with the office manager or principal. It may be the district office or even school board that decides whether or not to rent to you. Even though your local contact isn't making the decision, you want them on your side! Going over their head to force them to rent you is very dangerous. Sometimes that local contact becomes your advocate. More than one planter has been denied by elsewhere decision-maker only to have the local contact fight for you and ultimately win over the decision-maker. | Call or drop by each facility to make a local point of contact. Get their contact information and save it. This action is complete when you have contact information for the management at your top facility prospects. |  | 110 | 49 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-22 content updated --pb 2019-12-17 content updated --pb 2020-12-14 changed Due in # Days from 108& to 110& --pb&
228 | 720 | 718 | Get on waiting list at each prospective location | Get on waiting lists to secure your interest and place in line for potential worship gathering facilities. | As church planting grows in popularity, so do to waiting lists for facilities best-suited for worship gatherings. Get on the waiting list at as many possible meeting locations as possible. Don't wait too long to get this done. You risk having to settle for your last choice or even creating a crisis right before Opening Day. It is never too early to start looking for facilities and getting on the waiting list. In Fairfax County, VA, every middle school and high school currently has a church meeting in it (at the time of this writing). To have any chance of renting one of these facilities, you'd have to get on the list as soon as you even think you might want to meet there. Send a Letter? Some planters have landed their facility by sending an introductory letter to the decision-maker at the prospective facility (remember that your local contact may or may not be the decision-maker). Be sure to include the following in that letter: a gracious introduction a mention of your previous interactions (request to rent the facility, request to be on the waiting list, etc) basic information about the church (target Opening Day, contact information, etc) a formal request to rent the facility | Contact each facility to find out its availability. Ask to be put on any waiting lists as necessary. This action is complete after you have checked the availability of each prospective meeting location and have been added to applicable waiting lists. Additional Resources <a href="/resources/item/86">Sample Facility Request Letter</a> from Passion for Planting |  | 110 | 30 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-23 updated content & resource links --pb& 2019-12-20 content updated --pb 2020-12-14 changed Due in # Days from 120& to 122& --pb&
229 | 722 | 718 | Tour top facilities | Collect important information about each potential worship gathering facility so that you can make an objective, informed decision about which one to lease. | After you narrow down the list of facilities to no more than the top 3, it is time to conduct a thorough tour of each facility. Before visiting, review your Opening Day Expectations document. Keep in mind the target goals. Determine how many rooms will be needed for children's ministry, etc. Also consider how many rooms you will want a year or two after launch. The facility should have adequate room to grow. Download and print off Passion for Planting's <a href="/resources/item/88">Facility Tour Checklist</a> to take with you to each facility. While on site, use it to take notes on: What entrance will be used? Where is the entrance in relation to worship space, kids rooms and restrooms? Are the restrooms clean and presentable? Is there space available to store equipment? How much furniture are in the rooms that will need to be removed and replaced each Sunday? Is there adequate lighting for the stage or will additional lighting need to be purchased? Will the church be allowed to use existing lighting and/or sound? Are the children's rooms easy to secure? Is there space for a caf&eacute;? Is this a facility unchurched people would feel comfortable coming into? | Call each facility to arrange a time for a tour. Review your Opening Day Expectations document. Print and review the <a href="/resources/item/88">Facility Tour Checklist</a> Write down any other questions to ask the facility director. Take dozens of pictures of the facility to review later. This action is complete when you have toured each of the top facility choices. |  | 122 | 14 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-23 content & Due in # of Days & updated --pb 2019-12-20 content updated --pb 2020-12-14 changed Due in # Days from 119& to 122& --pb&
230 | 723 | 718 | Narrow your list of promising worship locations | Boil the list of potential worship gathering locations down to the top 3 facilities to pursue more seriously. | After you make initial contact with the broader list of potential facilities, complete an initial assessment of each of the locations. Rule out the obvious no's and rank the remaining facilities in order of desirability. Based on preliminary findings, narrow the list down to no more than 3 of the most promising locations. You won't have time, attention and resources to seriously pursue more than 3 worship gathering facilities. | Review the prior list of facilities and add any additional facilities you have identified. Remove the facilities that obviously will not work. Narrow down the remaining list to the 3 best facilities. This action is complete when you can name the 3 most promising facility options. |  | 122 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2019-12-20 content updated --pb 2020-12-14 changed Due in # Days from 120& to 122& --pb&
231 | 724 | 718 | Rank your top 3 facilities objectively | Use a proven method to score each of your top 3 facilities and rank them in order of which one would serve the church best. | By this point, there may be a clear winner on your list of facility options. Depending on your community, you may be left with only one actual option, so your decision is made for you. But often it comes down to picking between 2 or 3 reasonably good options. If there's not a clear winner, now is the time to use the <a href="/resources/item/87">Facility Selection Worksheet</a> you prepped in the previous PlanterPlan task Read/Review Facility Selection Worksheet . With the <a href="/resources/item/88">Facility Tour Checklists</a> you've completed for each facility, you'll be able to finalize the <a href="/resources/item/87">Facility Selection Worksheet</a> to objectively determine which facility is the best choice for your church. Follow the instructions included in the Worksheet and assign scores to each of your top facilities. The worksheet does all the math for you in a user-friendly layout! It will show you which is the better facility for your situation. | Consider how each of your top 3 facilities will enable the new church to reach lost people. Finalize the <a href="/resources/item/87">Facility Selection Worksheet</a>. Prayerfully consider the results and present the rankings to your Management Team, Coach and/or anyone who may need to be involved in the decision. This action is complete when you have calculated which is your best facility option and which is your runner up. |  | 122 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-22 content && resource links updated & --pb& 2019-12-20 content updated & link verified --pb 2020-12-14 changed Due in # Days from 120& to 122 & Duration from 14 to 7--pb&
232 | 725 | 718 | Run demographics near your top facility option | Make sure the area immediately surrounding the worship facility doesn't contradict your choice. | Here's one last test before you finalize your worship facility choice: make sure the demographics confirm your choice. First, the facility should be near where the people you're reaching live. If they are concentrated on the west side of town, for instance, is the facility in that same area? And if you're reaching different socio-economic segments or different races, is the facility in a blended area that both groups feel comfortable with? Will the facility build bridges or put up barriers? Get updated demographic information for a 3-, 5- and 7-mile radius around your top facility. Assess your top facility choice in relation to the people God is calling you to reach. | Obtain demographic information for the area around your top facility choice. Review the demographics to confirm the facility is a fit for your target demographic This action is complete when you have determined that the demographics don't contradict your facility choice. | <a href="/resources/item/100">Demographic Information for Your Church Plant</a> by Passion for Planting, which includes links to over 2 dozen sites where you can get various kinds of demographics reports | 122 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2019-12-20 content rewritten; title changed from "Make Final Facility Decision" --pb 2020-12-14 changed Due in # Days from 127& to 129& --pb&
233 | 726 | 718 | Negotiate terms for the facility | Work with the manager or owner of the facility to agree on the terms of the church renting the facility. | You've decided on a worship facility through prayer and due diligence. And you've already been communicating with at least the local management about its availability, getting a tour, etc. Now its time to negotiate the terms. Almost everything is negotiable, from the price to the hours to what's included. Schools If you're renting from a public school, the price is probably fixed, though probably on a per-hour basis. Other things you might negotiate for are: Access to a storage closet or other on-site storage Setting up on Saturday night, at least at the beginning while you're learning the setup routine Donating and permanently installing a high-powered projector that both the church and school could use Donating more folding chairs to the school (so there's enough for the church to use) Access to the school's wi-fi Having the custodian clean the rooms you're renting Friday evening rather than Sunday evening In lieu of towing a trailer every week, purchasing an ocean freight container and keeping it behind the building; it could be donated to school upon your departure for their own storage needs Leaving your equipment set up all summer Theaters You may have more room to negotiate on price at a movie theater, though some are rented by a national chain that sets fixed pricing. Other things you might negotiate for are: Access to a storage closet, unused behind-screen space or other on-site storage Access to the theater's wi-fi Reduced-cost popcorn and/or soda after services Their donating or offering reduced-cost tickets; you could give them away at events or for volunteer appreciation Having the custodians clean your theaters late Saturday night instead of Sunday morning while you're there trying to set up Cordoning off the extra-wide hallway into classroom space Using the back fire doors to load equipment in and out Hotel If you're renting a hotel meeting room or banquet room, things you might negotiate for are: How much and where you can put signage Whether you can bring in your own coffee and snacks Be friendly make it a win for them. And if you don't ask, the answer is already no. | Arrange to meet with the decision-maker. Negotiate the terms, everything from price to access to length of contract. Make sure those terms get put in writing. This action is complete when you have agreed upon written terms with the decision-maker for the facility. |  | 129 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-23 updated content --pb 2019-05-16 additional resources subsection added --pb 2019-12-20 content validated --pb 2020-12-14 changed Due in # Days from 127& to 135& --pb& & 2019-12-20 content updated --pb
234 | 729 | 704 | Coaching Checkpoint: review and affirm facility selection | Review the facility selection and provide feedback to the planter. | Ensure that the planter has thought through each available facility and selected the one that is most consistent with the vision of the church and in best proximity to the people they are trying to reach. | Have the planter describe to you the facility options and discuss why the specific facility was selected. Provide feedback to the planter as appropriate. This action is complete when you, the coach, have reviewed and affirmed the planter's facility selection. |  | 143 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2018-10-29 content updated --pb 2018-10-30 title changed from "obtain..." to "purchase a..." --pb& 2019-12-20 content updated --pb 2020-12-14 changed Due in # Days from 133& to 150& & Duration from 21& to 30& --pb&
235 | 1392 | 0 | PHASE IV - COMMUNITY CONNECTION | [6 empty] | 2021-01-15 05:00 | 2022-01-20 05:00 | 2000-01-01 05:00 | template:
236 | 451 | 1392 | Milestone: Create a Community Networking Strategy | Devise a strategy to network in the community to learn about the community, develop partnerships for service and get the word out about the new church. | Community networking can easily be overlooked. However, it can be an essential tool for building relationships within the community. For example, one planter joined the local Optimist Club in order to meet other community leaders. Through those relationships, the planter learned of a need for meals for under-resourced families. He leveraged the influence of the leaders in the Optimist Club to mobilize a team of volunteers and donors to provide a week's worth of meals for 100 families in the community. In carrying out the plan, he connected with each school in the community and got a list of under-resourced families. The planter was then able to network with principals, guidance counselors and parent liaisons within the schools. Through this community initiative, the planter was able to work directly with the schools to assist these families with their ongoing needs. A team of 70 volunteers was recruited. Several of these volunteers became launch team members of the church. The church also gained lots of local press coverage and good PR. None of this would have happened if the planter had not been intentional about networking. The fruit of this particular networking was not seen for more than six months, but when it came, the harvest was large. This milestone will help you target key leaders in the community to network with, and to develop a plan for connecting with them. Often times God is working upstream of us. By networking, we learn about what God is already doing and how partnerships can be built around common goals. |  |  | 137 | 106 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2017-11-13 content validated; "sample networking strategy" link removed --pb 2019-11-26 content overhauled& --pb 2020-12-14 changed Due in # Days from 70& to 32& & Duration from 7 to 1& --pb&
237 | 452 | 451 | Read this community networking overview | Create a strategy for networking with community leaders to connect with the right people in the most effective way. | Networking is all about deliberately starting conversations with key community leaders. Why is networking important? The networking relationships you foster can open up community service, outreach and marketing opportunities. Sometimes they will lead you to the facility you'll end up renting for worship gatherings. Often the initial relationships open up their networks to you, people you'd otherwise not be able to meet with. Begin as a student of your community. Understand who the key organizations and leaders in the community are. There will be more leaders to network with than you will time for prior to your launch. You'll have to prioritize and be strategic. Community leaders have a good grasp on your community and can help you discover the best ways to serve. Chances are good that they've gotten to their current position because of their charisma and ability to network. You'll commonly find good vision-casters among them, too, which is a skill you will always need to hone. Your community leaders have the ability to influence others, so get them on your side. Networking is like a needle in a haystack. If you think there is no needle, you will not find it. But if you are certain there is, you will find it. God has placed people in the community that you need to find. Your networking strategy is one of the best ways to find them. Pray that God will reveal the several persons of peace in your community who will make a profound impact on the eternity of tons of people when they come to believe. Lastly, as the "CEO" of the church, you should be meeting with with other C-Suite leaders in your community. They're your peers. | Watch the Passion for Planting training video "<a href="/resources/item/181">Networking - Connect in the Community</a>" featuring Ed Stetzer. This action is complete when you have read this overview and watched the training video by Dr. Ed Stetzer. |  | 32 | 1 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated, audience changed to coach --pb 2018-04-20 updated content, changed audience to planter --pb 2019-11-26 content updated --pb 2020-12-14 changed Due in # Days from 70& to 38 --pb&
238 | 453 | 451 | Call your coach about networking in the community | Open a conversation with your coach about community networking. | Meeting leaders and civic influencers in your community will build your church's credibility, uncover community service opportunities, and may even help identify a worship gathering facility. Sample issues to process with your coach: Building relationships with leaders outside the church How to identify key leaders in your community Cold calling community leaders Finding time to network | This action is complete when you have called your coach about networking in the community. |  | 38 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2016-06-19 resource link updated --pb 2017-11-13 content & links validated --pb 2018-05-07 added& google& doc template version --pb 2019-11-26 content overhauled& --pb 2020-12-14 changed Due in # Days from 98& to 45& --pb&
239 | 454 | 451 | Craft a Community Networking Strategy | Document the approach you'll take to meeting leaders and influencers in your community. | The single best resource for understanding your community's needs are people in positions of power and influence in the community. These leaders will be heavily vested in the community and care deeply for it. With this common bond, conversations should be easy to start. These conversations are learning expeditions. You may not gain a single person to the launch team by talking with community leaders. But it's still a huge win if all you accomplish is learning the needs of the community, discovering opportunities for partnership, and planting the seed that your church is about serving the community. Look for areas where God is already working through these leaders and seek ways to partner. The two basic approaches to get your first meetings are to create a Top 20 list of leaders and cold call them, or somehow manufacture the first meeting and follow their introductions to other leaders. Your Community Networking Strategy will contain the following: A basic philosophy or approach to community networking A goal for how many leaders to meet each week A short list of questions to ask in person A way to keep track of contact information and important notes A system for circling back and following up so it's not a one-and-done "relationship" | Download Passion for Planting's Community Networking Strategy Template (<a href="/resources/item/182">MS Word</a> or <a href="/resources/item/358">Google Doc</a>). Think through how to prioritize community leaders to network with. Determine a goal for how many leaders to meet with. Compile all of your ideas and answers in the template. Send your completed Community Networking Strategy to your coach for feedback. This action is complete when you've sent your Community Networking Strategy to your coach for review. |  | 137 | 99 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content validated --pb 2019-11-26 content updated --pb 2020-12-14 changed Due in # Days from 105& to 52& --pb&
240 | 1303 | 454 | Set a goal for number of community leaders to meet weekly | Challenge yourself to a sustainable pace of meeting leaders and influencers in your community. |  | content pending... |  | 45 | 7 | 2019-11-26 05:00 | 2022-01-17 05:00
241 | 466 | 454 | Write questions to ask community leaders | Develop a short list of questions to ask community leaders when you meet with them. | You're going to start with a list of community leaders that is too big for you alone to meet with each of them. Of course you want to make as many connections as possible, but you're probably going to have to recruit others to help so you can meet with everyone on the list. If you're blessed with multiple staff, require each staff person to meet with community leaders, especially those in their sphere of influence (music, kids, etc.). Developing a list of questions or a script to give to staff and volunteers can go a long way to helping them feel comfortable. It will also help prepare you for your own meetings with community leaders. The one question that should always be asked toward the end of a conversation is, "Who else should I be sure to talk with (and would you introduce me)?" | Read the <a href="/resources/item/52">Sample Community Networking Interview Questions</a>. Write the list of questions in your Community Networking Strategy document. This action is complete when you have written out a short list of questions to ask community leaders. |  | 45 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content updated --pb 2019-12-09 content updated --pb 2020-12-14 changed Due in # Days from 140& to 137 & Duration from 38 to 45; name changed from "Conduct your community needs survey" --pb&
242 | 461 | 451 | Coaching Checkpoint: review and affirm Community Networking Strategy | Review the planter's Community Networking Strategy and provide feedback on his ideas for connecting with key leaders in the community. | The planter will send you their Community Networking Strategy . It should include the following elements: A basic philosophy or approach to community networking A goal for how many leaders to meet each week A short list of questions to ask in person A way to keep track of contact information and important notes A system for circling back and following up so it's not a one-and-done "relationship" Read over the strategy and provide feedback to the planter. Specifically, affirm the goal for the number of leaders the planter wants to connect with. Does the goal seem realistic? Does the goal seem too small? Spend time talking through the strategy. Provide wisdom and insight for how to get a meeting with the leaders and how to make the most of that meeting. | Read over the networking strategy provided by the planter. Affirm the goal for the number of leaders to network with. Affirm the questions the planter will ask leaders. Affirm the tracking and follow up process. Provide any other feedback as appropriate. This action is complete when you, the coach, have reviewed and affirmed the planter's Community Networking Strategy document. |  | 52 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content updated --pb 2020-12-16 changed Due in # Days from 160& to 137& & Duration from 83& to 93& --pb&
243 | 462 | 1392 | Milestone: Implement Community Networking Strategy | Put into practice the strategies laid out in the previous Milestone to connect with community leaders and influencers. | Now that your Networking Strategy has been developed, it's time to put those strategies into action. Take each action item resulting from the networking strategy and add them to this milestone. This can be done through the PlanterPlan tool. Networking will be an ongoing effort during the pre-launch phase of the church. Be sure to set realistic goals for completion. | --no steps-- |  | 137 | 99 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content updated --pb 2019-11-20 title updated from "Establish Community Contact Database" --pb 2019-12-09 content updated --pb 2020-12-14 changed Due in # Days from 83& to 58& --pb& 2020-12-23 name changed from "Choose strategic place to save contact info from networking" --pb
244 | 463 | 462 | Create a Networking database or address book | Establish a community contact database for keeping track of community leaders and organizations and their contact information. | As you network in your community, you will be meeting lots of people. Whether you dug up their contact information or they handed you a business card, you will be collecting lots of very useful contact information. It's time to think through a simple place to keep all that so it's together. You have 2 basic options for the database: keep the information in your church management software keep it elsewhere, for example: in your phone's contacts with a tag or folder for "network" in a spreadsheet you can access from all your devices in a free customer relationship management (CRM) app At least as important is keeping track of when you met with them and when is a good time to follow up with them, along with an occasional important note when you talked about something important you want to remember. So if your choice of database doesn't have that built-in, consider creating a sub-calendar dedicated to networking. You can save your appointments and schedule follow-ups there. | Decide whether to use your church management software or some other tool for keeping track. If you're starting with list of contacts, upload them to your app or recruit a supporter to do the data entry for you. Make sure your solution is easy to use while you're out and about. This action is complete when you have added your first contact to your database option. |  | 58 | 14 | 2015-02-03 05:00 | 2020-12-23 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content & links updated --pb 2019-12-09 content updated --pb
245 | 488 | 462 | Identify and join local civic associations | Develop relationships through civic associations to uncover opportunities and resources you wouldn't otherwise know about. | One easy way to network and get the word out about the new church is by joining a local civic organization. Consider joining: Chamber of Commerce Rotary Kiwanis Lion's Club Optimist Club etc. These organizations will put you in contact with multiple community leaders. These groups have events to serve the community. You may be able to partner with them at their events by providing volunteers to help make them happen. This can help you establish a positive reputation amongst the leaders in the community quickly. | Determine which association(s) to join. Call them or swing by to sign up. This task is complete when you have joined at least one local association. |  | 58 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2018-02-16 content validated --pb 2019-12-02 content update --pb 2020-12-16 changed Due in # Days from 128& to 128& & Duration from 34& to 37& --pb&
246 | 465 | 462 | Write a community needs survey | Develop a survey to use in the community so you can gain insight into its greatest strengths and needs. | The community needs survey should be limited to what can fit on one page. Passion for Planting has provided a <a href="/resources/item/53">Community Needs and Assets Survey Template</a> as a starting point. The questions you ask will largely influence the results of the survey. Keep the questions broad in nature, provide lots of multiple choice options and allow room for people to make comments. For example, rather than asking a specific question such as, "Do you think this community needs more recreational facilities?" ask, "The greatest areas in which our community needs to improve are..." Allow people to choose multiple answers. Especially if you're planting in an under-resourced neighborhood, don't just ask about its needs. Ask about its strengths. Search for areas of opportunity within the community. Then your church can work with the community to meet needs while developing the good already being done. To learn more on asset based community development visit <a href="https://resources.depaul.edu/abcd-institute/">ABCDinstitute.org</a> The larger the population of the community, the more surveys you will want to collect to get a good sampling. As you collect the surveys you should begin to see trends emerging as to what the greatest strengths and weaknesses of the community are. In the template you will notice the suggestion to give a gift or have a drawing for participants. This provides incentive for people to fill out the survey. It also gives you a reason to have additional contact with them through email. One strategy is to use the survey as a means to collect emails for a community database. Then you can invite them to volunteer at your next community service initiative. Online Surveys Consider creating surveys that can gather information via the internet. If you have a presence on Facebook, consider creating a Facebook survey and ask people to share it with as many local people as possible. Make sure the survey is clear that only residents of your community should take it. As a safe guard, the first question can be a simple yes or no, do you live in [name of community]? Other free online survey options include: <a href="https://www.surveymonkey.com">SurveyMonkey.com</a> <a href="https://docs.google.com/forms/">Google Forms</a> <a href="https://www.pollfish.com">PollFish.com</a> | Download the <a href="/resources/item/53">Community Needs and Assets Survey Template</a>. For inspiration, also see the <a href="/resources/item/338">Sample Community Needs and Assets Survey</a>. Write your own community needs and assets survey. This action is complete when you have composed your own community survey. |  | 92 | 14 | 2000-01-01 05:00 | 2019-12-09 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content update --pb 2019-11-26 content updated --pb 2020-12-14 changed Due in # Days from 91& to 45& --pb&
247 | 468 | 462 | Have your team conduct the community needs survey | Recruit your team members to get completed surveys from people in the community. | Once the community needs and assets survey has been written, determine the forum for collecting them. The more surveys collected, the better. Keep in mind that the denser the population is in the community, the more surveys you will need to collect in order to get a good representation. Also, keep in mind that the more diverse your community is, the more difficult it will become to get a good sampling. Be intentional about choosing the forums for collecting surveys to ensure that a good representation of the community is present: A great forum for collecting surveys are at community events. Consider purchasing booth space to conduct the survey. Another great forum are big box stores and grocery stores. Approach the management and ask them to partner in with you in doing the survey. Another option is to conduct the surveys online (see options included in previous PlanterPlan task). Once the surveys have been collected, you must analyze the data. Through your analysis, determine what community needs have been revealed. Compare these results with what was learned by networking with community leaders. | Recruit volunteers to help conduct the survey. Determine the forum(s) for conducting the survey. Get out there and collect surveys. Analyze the results. This action is complete the results of the community needs assessment have been analyzed. |  | 137 | 45 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2017-11-13 content updated --pb 2019-12-09 content updated --pb 2020-12-14 changed Due in # Days from 140& to 111& & Duration from 21& to 60& --pb&
248 | 469 | 462 | Meet with community leaders | Get face time with civic leaders and influencers to build relationships and learn about your community. | Scheduling face to face meetings with leaders is key as you begin to build bridges in your community. Leaders identify with leaders. Asking for face time with these key people will communicate your own level of commitment to the overall community picture. In a previous task, you set a goal for the number of leaders to meet with prior to launch. You also prioritized your list to identify specific people you want to meet with. Now the rubber meets the road. The brief first impression you get with these high-profile leaders gets you off on the right foot in the community. Think through what you really need to talk about in your initial meeting. Once in the meeting, take time to ask about their background (birthplace, education, family, job journey). Finding common talking points helps to move the conversation along. Look for a transition into discussing why you are there and what your vision is. Be prepared to answer the question, "How can I help you?" Use this question to throw out ideas of future potential partnerships with them. Ask questions about the community needs/assets and demographics. Finally, ask permission to meet with them again in the future. Sometimes it may be appropriate to close in prayer. Power Tips: Try and do some research about the leader you are preparing to meet with. They may have a profile on their website or LinkedIn. Dress appropriately. Which community leader you are meeting with may dictate how you dress. Carry with you: your calendar a notepad (so you're not distracted by technology) and at least a business card or pre-launch brochure Take mental notes of the leader's personal info (name, title, background details, family, etc...). Only take written notes if the leader begins to give you data, community info, people to contact, etc. | Pursue meeting with the leaders on your prioritized list. Meet with them. After each meeting, jot down notes and schedule your next follow-up with them. This action is complete after you have met with the first 10 community leaders prioritized in your networking strategy. |  | 111 | 60 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-11-13 content updated --pb 2019-12-09 content updated --pb 2020-12-14 changed Due in # Days from 84& to 58& --pb&
249 | 375 | 1392 | Milestone: Create a Launch Team Development Strategy | Build the team that will be the church and get the regular worship gatherings launched. | Developing the Launch Team is the most important thing the planter will do. Studies like Ed Stetzer's <a href="https://www.newchurches.com/">The State of Church Planting in the U.S. Research Report</a> continue to show that the size of the Launch Team prior to launch is a leading indicator of the church's health and sustainability after launch. Churches that launch with more than 40 adults on the launch team have fewer problems with common struggles like leadership development, financial stability and volunteerism. Development of the Launch Team is the single most important health metric of the new church. You can develop plans, strategies, and have all the needed resources, but without a Launch Team, a new church will not be birthed. |  |  | 71 | 21 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-06-09 content and links updated --pb 2019-12-23 content updated and links verified; removed broken hyperlink to missionglue.com blog post --pb 2020-12-14 changed Due in # Days from 56& to 51& & Duration from 7 to 1& --pb&
250 | 376 | 375 | Read this Launch Team Strategy overview | Understand the importance of building a Launch Team and gain a frame of reference for the work ahead. | Developing the launch team is the most critical piece of launching worship gatherings. Studies like Ed Stetzer's <a href="https://www.newchurches.com/product/churchplantingresearch/">The State of Church Planting in the U.S. Research Report</a> continue to show that the size of the Launch Team prior to launch of worship gatherings is a leading indicator of the church's health and sustainability after the launch. Your Launch Team is the group of committed adults & teens that have signed up to help the church launch worship gatherings. They will be the inviters and the worker bees. Some will become your key team leaders. You Launch Team should be comprised of some percentage of people with little or no church background. Maybe they just said yes to Jesus, or maybe they're checking this whole Jesus thing out. But if you haven't reached any lost people prior to launching weekly worship gatherings, that may very well become your long-term legacy. Your ability to gather people and build a team is the single best indicator of how healthy the new congregation will be after launching worship gatherings. You can have all the best strategies and all the resources you need, but without a Launch Team, the worship gatherings won't ever come together. The Church is people, after all. | Read the overview above. Watch the training video <a href="/resources/item/149">Develop and Grow Launch Team</a> by Ed Stetzer. Read one or more of the posts linked below. This action is complete when you have a clear understanding of what a Launch Team is and why you need one. | <a href="https://scottball.net/how-to-build-a-launch-team/">How to Build a Launch Team</a> on scottball.net --> <a href="https://exponential.org/how-big-should-your-launch-team-be/">How Big Should the Launch Team Be?</a> on exponential.org <a href="https://www.churchplantingtactics.com/church-plant-launch-team-should-you-include-believers/">Who Should Be Included/Excluded from the Launch Team?</a> on churchplantingtactics.com <a href="https://exponential.org/setting-your-church-plants-dna/">How Do I Build Momentum with the Launch Team?</a> on exponential.org | 51 | 1 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2018-04-20 updated content, changed audience to planter --pb & 2019-12-23 content updated --pb
251 | 377 | 375 | Call your coach about building a Launch Team | Open a conversation with your coach about building a Launch Team. | As a church planting veteran, your coach will have lots of practical experience with growing a Launch Team. It is one of the primary tasks of planting a new church - meeting people and getting them on mission together. Sample issues to process with your coach: Whether to include lost people on the Launch Team Closing the deal on an invitation to join Where to meet people Communicating expectations What to do at Launch Team meetings | Call your coach about forming and growing a Launch Team. This action is complete when you have called your coach about building a Launch Team. |  | 57 | 7 | 2015-02-03 05:00 | 2019-12-23 05:00 | 2000-01-01 05:00 | template: standard 2017-06-09 content & resource links updated --pb 2018-06-01 added new Gdoc& template format --pb 2018-10-12 changed title from 'develop a launch team strategy' (planters confused it with the launch strategy) --pb 2018-11-12 additional resources subsection added --pb & 2019-12-23 content updated --pb
252 | 378 | 375 | Craft a Launch Team Development Strategy | Create a written strategy document outlining your contextual approach to finding people, building a team, and planning meetings. | To help you with the complexity of this strategy, key building blocks are laid out in the subtasks that follow. Download the Launch Team Development Strategy Template (below) to use like a fill-in-the-blank worksheet as you work through: talking to your spouse about their role developing a covenant or commitment agreement developing a process for accepting people into the team determining what types of info meetings to host deciding what to do at Launch Team meetings picking calendar dates for meetings identifying training material to use with the Launch Team Set a Goal Set a prayerful goal for the number of people who will join the Launch Team. You should have already dreamed one up in your Opening Day Expectations document. Look back in that document at the ministry teams you dreamed of having. Then ask, "How many workers will need to be on the Launch Team in order to support this vision?" Now ask, "How many workers will we need so that we can work out some kind of serving rotation and not burn everyone out?" Set a Date Set a target date to to hit your goal. You may find it helpful to break that number down into several smaller goals and set target dates for each along the way. For example, if the goal is to have 50 adults on the launch team by August, you might set a goal of 25 people on the team by June, and before that, 10 people on the team by April. Be sure to allow adequate time to train launch team members before the start of worship gatherings. It would be amazing to be recruiting Launch Team members right up to the night before, but how equipped will they be to serve the next day? How much will they have internalized the common vision? Whatever your goal is, back your due date up a good 30 days before the launch of your worship gatherings. | Download Passion for Planting's Launch Team Development Strategy Template (<a href="/resources/item/325">MS Word</a> or <a href="/resources/item/368">Google Doc</a>). Complete each section as you work through the subsequent child tasks in PlanterPlan. Refer back to the Opening Day Expectations document. Calculate how many workers will be needed to support that vision for the Opening Day of worship gatherings. Send the written Launch Team Development Strategy to your coach for feedback. This action is complete when you have sent your Launch Team Development Strategy to your coach for feedback. | <a href="https://outreachmagazine.com/features/church-planting/33577-4-practical-steps-recruiting-church-plant-team.html">Four Practical Steps for Recruiting a Church Plant Team</a> by Ed Stezter | 67 | 10 | 2000-01-01 05:00 | 2022-12-23 05:00 | 2000-01-01 05:00 | template: standard 2017-06-12 content updated --pb 2020-02-24 additional resources subsection added --pb & 2019-12-23 content updated --pb
253 | 379 | 378 | Talk to your spouse about their role | Decide how much or how little your spouse will work on during the planting process so that they are not overlooked or overworked. | Your spouse is a partner in ministry. Spouses play a critical role in the new church, and their gifts and passions should always be considered. What do they want to do? Invite them into that area of ministry. But also don't overwork them to the point of breaking. Also, be very hesitant to make your spouse fill in on a ministry team that doesn't line up with their passion. They may be able to fill the role credibly in the short term, but burnout is all but inevitable. Maybe your spouse will lead a particular ministry team. Or they may take point on items in the launch plan but delegate the work to other team members. Maybe their best fit is serving on a team that someone else is leading. Whatever the case, don't assume anything about your spouse's involvement. Clear communication regarding expectations will alleviate great amounts of marital stress. | Invite your spouse to the PlanterPlan project (use project > manage team ). Review the PlanterPlan task list with your spouse to determine which actions they'll be responsible for. Assign those tasks to them using the Lead dropdown on each task (their initials will be listed). This action is complete when you and your spouse have reviewed the PlanterPlan task list and determined which actions the spouse will take charge of. | <a href="https://www.reviveourhearts.com/articles/whats-your-role-church-planters-wife/">What's Your Role as a Church Planter's Wife?</a> on reviveourhearts.com | 64 | 7 | 2015-02-03 05:00 | 2020-02-24 05:00 | 2000-01-01 05:00 | template: standard 2017-06-12 content & resource link updated --pb& 2019-12-23 content updated --pb 2020-12-14 changed Due in # Days from 56& to 64 --pb&
254 | 380 | 378 | Set Launch Team expectations | Have a clear picture of what you're inviting people to when you ask them to join the Launch Team. | People need to know exactly what you're asking of them and exactly what they're committing to. Chances are good you've been part of a team that didn't have clear expectations or a common goal. How did that work out? Creating community, common culture and team commitment includes setting clear expectations on the front end. What you don't want is a 4-page list of expectations that no Pharisee could ever live out. Or a 10-page software license agreement that no one ever reads. Keep it simple &mdash; no more than 3 to 5 points. The list should be catalytic and inspiring, not oppressive and demanding. Most importantly, it should be memorable because you'll want your team members to recruit forward. The expectations you list should be a version of the Strategies from your Vision Frame (see previous PlanterPlan task). What the church does after the launch of worship gatherings should not be terribly different from what you're asking them to do prior to Launch. Keep the expectations realistic. Are you asking them to commit so much time to serving on the team that they won't have time left to build relationships with friends, neighbors and co-workers? Is the bar set so high that only full-time, vocational pastors could live up to them? Speaking of that, do you already live up to the expectations? Think through how lost people might respond; you want them on your team. Do you have the same expectations of them? Will they be second-class citizens? Develop the list in some kind of written form. Consider including your mission statement somewhere on that page. And consider whether or not to include a time aspect, like committing to 6 months, 12 months, etc. In a subsequent task, you'll decide whether people should sign the commitment/covenant or not. For now, simply craft the list of expectations. | Review the <a href="/resources/item/148">Sample Launch Team Expectations</a> but don't copy them . Ask around and review copies of what other planters have used. Develop your own short list of expectations. This action is complete when you have finalized a written list of expectations for launch team members. |  | 64 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-09 changed 'plan' to 'strategy' --pb 2017-06-12 updated content --pb & 2020-12-14 changed Due in # Days from 56& to 64 --pb& 2019-12-23 content updated --pb
255 | 381 | 378 | Decide how people will sign up to join the Launch Team | Determine how you'll invite people to join the Launch Team and how you'll direct them to respond. | Have you ever been part of a team and not known it? We didn't think so. The process for accepting people into the Launch Team does not need to be complex. It should involve an opportunity for the planter to share the vision either one-on-one or in a group. And it needs to include some kind of opportunity for them to respond. The response generally falls into one of three broad categories. Choose the one that is the most meaningful to people in your target area: Verbal - they respond to the invitation verbally, which may or may not be followed by a handshake, etc Symbolic - they respond to the invitation by signing their name to a poster, adding their puzzle piece with their name on it, or other symbol of the team Covenantal - they respond to the invitation by signing the expectations document (aka agreement, contract, covenant) Think through whether the process will make it relatively easy or difficult for unchurched people to join the Launch Team. A Positive "No" Equally as important is the process for gently rejecting people who express interest but should not join the team. Most planters experience some version of unhealthy or downright toxic believers wanting to join the team, usually to drive a personal agenda. The vision God has entrusted to you is not for sale. How will you let the toxic believer know that they aren't welcome to join the team? | Write a short paragraph that describes how you will make the invitation to join the Launch Team. Determine how you will direct people to officially sign up to join the team. Include these in the Launch Team Development Strategy document. This action is complete when you have decided on a process for people to sign up to join the Launch Team. |  | 64 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-09 changed 'plan' to 'strategy' --pb 2017-06-14 updated content and hyperlinked book --pb & 2019-12-23 content updated --pb
256 | 382 | 378 | Determine What Type of Informational Meetings to Have | Decide how to leverage vision casting in group settings to build the launch team faster. | You won't be able to connect with enough people 1-on-1 to build a big enough Launch Team. Just do the math: what if you could get 1 yes out of every 4 invitations? You'd need to have 200 one-on-one meetings to get the Launch Team to 50. At some point, you need to leverage group settings. You'll encourage your early team members to invite their friends and family to Launch Team meetings, which will help. And yet there will be people in your community who might very well join the team, but don't know anyone already on the team. How will they get invited? Some planters have rented a meeting room or facility and hosted a Vision Night. People are invited to hear about the new church and dream about what it might look like. There is a formal pitch to join the Launch Team that night before they leave. In Ralph Moore's book, <a href="https://www.amazon.com/Starting-New-Church-Ralph-Moore/dp/0801018099/">Starting a New Church</a> , he talks about how when starting a new church, they would take an ad out in the local newspaper. The ad invited anyone who would be interested in being a part of a new church to come meet at a local restaurant. Ralph Moore says that often several initial Launch Team members will be recruited from those meetings. Others have held cookouts our put on a movie night in the park and invited the community to come hear about the new church and enjoy the entertainment. These types of events are easy for existing Launch Team members to invite friends to as well. Just be careful not to bait and switch. Regardless of your particular strategy or what you call it, look for opportunities to use group settings to get the word out about the new church and to build the Launch Team. | Brainstorm a list of ideas for holding Vision Nights or Info Meetings. Determine which of those to put on and assign a date and cost to each meeting. Add the meetings to your calendar and costs to your budget. This action is complete when you have determined what types of meetings to hold and added them to the Launch Team Development Strategy document. |  | 64 | 7 | 2015-02-03 05:00 | 2020-03-27 04:00 | 2000-01-01 05:00 | template: standard 2017-06-09 changed 'plan' to 'strategy' --pb 2017-06-14 content validated --pb 2019-12-23 content updated --pb & 2020-12-14 changed Due in # Days from 56& to 64 --pb&
257 | 383 | 378 | Plan out what to do at Launch Team meetings | Develop a strategy for using meetings to build and train the Launch Team. | Once you have recruited the initial Launch Team members, you need to figure out how to train, teach and equip them. Launch team meetings are a natural forum for getting that done. Launch team meetings can serve one or more the following purposes: Expanding the Launch Team Invitation should be a primary focus of all Launch Team members. Everyone on the team has the job of recruiting people from their spheres of influence. You'll have to consistently remind the Launch Team of this goal. You'll want to include a welcome and basic overview info at Launch Team meetings; consider adding an invitation to join the team, too. Fostering Fellowship It is important for the Launch Team members to get to know each other. They should have opportunities to fellowship and develop friendships around the common cause of launching the church. Fellowship is a part of any gathering. But sometimes, it is good to plan an event solely for the purpose of fellowship. For example, have the launch team over to watch a big football game together. Casting Vision God has entrusted you with a vision for the new church. You have already cast that vision with launch team members individually. However, vision is leaky. You must continually cast the vision for what the new church is going to be like. Many planters rely heavily on oral presentations to communicate vision. Sometimes, though, the best way to make vision stick is by living it together. For example, if serving the community is a part of the desired DNA, rather than talking about it, schedule a gathering where the launch team actually serves the community. Training There are several jobs for the launch team to do in order to hold worship gatherings and accomplish the ministries of the church. Launch Team members have to be trained for each ministry and task that needs to be done. For example, choose to plan a Launch Team meeting to train the launch team on setting up the portable equipment. Maybe you'll create a rhythm that you follow at every Launch Team meeting, like Head, Hands & Heart . Maybe you'll structure it with large group time and then have the teams break off for team vision and training. Whatever it is, be intentional. Don't Default to Bible Study Bible study and church groups are important. But the launch season won't come around again, so make Launch Team meetings be different. Certainly, include some scripture. But Launch Team meetings should be about vision, some housekeeping, and a lot of conspiring to invade the community. | Brainstorm a list of ideas for Launch Team meetings in each area above. Decide how to structure your meetings and/or vary them. Assign a date and cost for each gathering and add it to the calendar & budget. Include them in the Launch Team Development Strategy document. This action is complete when you have determined what type of launch team meetings to have. |  | 64 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-09 changed 'plan' to 'strategy' --pb 2016-06-14 content & hyperlink validated --pb& 2019-12-23 content updated and link verified --pb 2020-12-14 changed Due in # Days from 56& to 64 --pb
258 | 395 | 378 | Set calendar date for initial Launch Team meeting | Commit to a specific date for the very first Launch Team meeting so you can make plans and work out details. | Every team needs time together. Your Launch Team is one of your best assets, but only if they're actually a team. You've already decided what to do at the Launch Team meetings. Now you just need to get the first one on the calendar. Hold the first Launch Team meeting at least 6 months before the launch of worship gatherings. Get in the routine of meeting on a regular basis: Passion for Planting recommends weekly leading up to the Opening Day of worship gatherings. In no case should it be less than once a month - vision leaks and there's just too much to do! | Decide the schedule for ongoing gatherings. Secure a location. Set the date for the first meeting. Invite all the team members. This action is complete when you have scheduled the first Launch Team meeting. |  | 64 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-14 content validated and resource link updated --pb
259 | 384 | 378 | Pick training materials for the Launch Team | Identify books, resources and tools you'll use to increase your Launch Team's capacity. | One way to create community, culture, and common language is to lead your team through some kind of training material or church campaign together. There is no need to reinvent the wheel. You may want to plan a half-day or all-day training event. Maybe you'll want to include the training as a regular segment of your Launch Team meetings each week. Some planters have their Launch Team read a book together, one that ignites their imagination and inspires them to get on mission. Consider using the book that was foundational to you in your decision to plant the church. That will help people's hearts beat closer to yours. Other planters have picked ready-to-use solutions like: <a href="https://www.experiencerooted.com">Rooted</a> <a href="https://alphausa.org/about">Alpha</a> etc Others still have used evangelism-focused trainings that are widely available. | Review the plan for Launch Team meetings for which ones will need specific training materials. Contact other planters and pastors to learn what they have used. Include your decisions in the Launch Team Development Strategy document. This action is complete when you have picked training resources to use with your Launch Team. | <a href="https://www.slideshare.net/jasoncondon/handout-2013-0223-new-city-boston-tc-moore-launch-teams-training">Launch Team Training Day</a> training packet from New City Covenant Church | 64 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-14 content updated& --pb 2020-01-13 updated content --pb 2020-12-14 changed Due in # Days from 64& to 67& & Duration from 14 to 7& --pb&
260 | 386 | 375 | Coaching Checkpoint: review and affirm Launch Team Development Strategy | Review the planter's Launch Team Development Strategy document to ensure that it is thorough and realistic. | The Launch Team Development Strategy document is a culmination of multiple tasks in PlanterPlan. The planter will use the template to record decisions they've made and specific strategies they'll employ. Their Launch Team Development Strategy document should include: decisions about their spouse's role what it means to sign up how people will sign up to join the team how to leverage group settings to recruit content of Launch Team meetings date of the first meeting training materials to use with the Launch Team | Review the planter's Launch Team Development Strategy document. Provide feedback where necessary. This action is complete when you, the coach, have reviewed and affirmed the planter's Launch Team Development Strategy document. |  | 71 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-14 content validated --pb 2020-12-14 changed Due in # Days from 77& to 90& & Duration from 14& to 30& --pb&
261 | 1290 | 1392 | Milestone: Implement Launch Team Development Strategy | Put into practice what you decided to do when crafting your Launch Team Development Strategy. | Now that you've strategized how to recruit locals to your launch team and what to do with them once gathered, it is time to put those strategies into action. Invite people, build community, and train & empower them. It's go time! |  |  | 234 | 212 | 2019-10-14 04:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: 2019-12-10 date fields found empty& 2019-12-11 date fields re-entered manually --pb 2022-11-21 updated links --sc
262 | 385 | 1290 | Develop a Vision Frame & beliefs handout | Create a summary handout or presentation to make sure Launch Team members understand the vision, values and beliefs of the new church. | The Launch Team members have to become the DNA carriers of the new church. They must be on board with the plans that God has given you for what type of church this will be. For brand-new believers, this will be a helpful reference point for what church is about. For transfer believers, there may be some baggage they'll have to ditch to align themselves with the vision. Some believers may quit your Launch Team because it's just too different or not a good match. Now is the time to find that out. At this point, you've hammered out your entire Vision Frame . Now put it in a simple form that can be used with the Launch Team and, eventually, church members. Hesitate to design this handout yourself, even if you have design skills. You should be spending that time with people instead of behind a computer screen. That said, it can be designed simply for printing at home or designed professionally for high-quality printing. Work with the designer to be sure they include the right things and represent the church's brand well. | Review the Vision Frame . Enlist a graphic designer and direct them what to include in the summary handout. Print them in house or send them out for professional printing. This action is complete when you have the handout printed and in hand. |  | 67 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-09 updated 'plan' to 'strategy' --pb 2017-06-14 content validated, audience changed to coach --pb& 2019-12-23 content updated --pb
263 | 388 | 1290 | Recruit First 10 People to the Launch Team | Grow the Launch Team to the initial milestone of 10 adults so that the team dynamic begins to form and momentum is developed. | Getting the first few people for a Launch Team is often the hardest part. Be intentional about how and where people will be approached about being recruited to the Launch Team. That will help ensure the right people are included. As the planter begins networking in the community, meeting neighbors, and conducting community events, he should identify and recruit Launch Team members. Initially, the Launch Team meets regularly as a small group. You invest significant time with the Launch Team members building relationships, communicating vision, and creating momentum. Often the first 10 people are: Old Friends Family Friends of friends or family who live in the area Christians living in the area who are commuting a considerable distance to attend a church like the one you are starting. Your church now gives them an option closer to home People you befriend and build relationships with after moving to the new area. These are often some of your best stories of life change Disgruntled Christians who hop from church to church looking for just the right place to satisfy their needs or agenda Cast a wide net to everyone you know across the country. Ask them to identify people they know who live in your target area. Pray specifically for God to identify an initial core of people to join the team. Look in unexpected places. Assume that every interaction you have with someone you don't know is the start of a new relationship with someone who needs to join your Launch Team. See each person as a potential member. If only one out of ten people you ask to consider joining does, then you have to talk with over 100 people to recruit your first ten. Expect rejection. Be prepared for it. Circle back on people in the future. Don't let one "no" be the final interaction. Just as new converts are often the greatest evangelists, new Launch Team members have the potential to be the best recruiters of new Launch Team members. Challenge each new Launch Team member to bring at least one additional person along on the ride. Continually challenge your team to be praying for new people. Ask each of your team members to share the names of 3 people they are praying for and building relationships with. | Identify the people to specifically ask to be a part of the team. Present the vision and expectations to the individuals. Be bold in approaching and asking people to join. Encourage them to pray about their role. Obtain a commitment from the interested people. Ask each committed member to identify 3 additional people as potential prospects. This action is complete when the planter had identified and recruited the first 10 members. |  | 90 | 30 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-14 content validated --pb 2017-05-04 content tweaked --pb 2020-01-24 content updated --pb 2020-12-14 changed Due in # Days from 120& to 151& & Duration from 14& to 60& --pb&
264 | 389 | 1290 | Expand Launch Team to 25 people | Grow the Launch Team to 25 adults so that momentum and excitement continue to grow. | Without at least 50 adults on your Launch Team, you will struggle with volunteerism, developing leaders, and financial sustainability after launch. Expanding the Launch Team to at least 25 people is an important milestone in getting to 50. Expanding a Launch Team might seem overwhelming. The pressure can be frightening. Don't fret. Take things one day at a time. Nearly every great team in history started small and grew healthily. Consider the following factors when you put a plan together for expanding the Launch Team: Pray It is God's church and we are called to cooperate. We are joining him in what he has planned. If we believe it is his church then we must trust he will provide the people. We have to figure out what it means to cooperate. That starts with prayer Communicate Vision People are drawn to a clear and compelling vision. You must be able to communicate the vision with passion and you must teach your entire team to do the same. Your current team members need to be disciples of the church vision Build Relationships People are skeptical of religion and church. However, they are open to spiritual things. Relationships break down barriers to start conversations. Conversations are the starting point to building trust. Trust leads to cooperation. You can't spend enough time building relationships. One or two key relationships almost always open the door to many other relationships. Look for these key relationships. Often they are found in unexpected places Cast a Wide Net The more people you and your Launch Team pray for, the more people who will join your team. It's that simple. More conversations. More people Be Persistent Some people need to be asked multiple times before they respond. Don't pester people but also don't give up after one "no" Challenge Your Team Your current Launch Team members are your best assets for growing the team. The DNA / culture you establish with them carries forward to future years. If the team is not praying for and inviting friends, neighbors and co-workers, you will have a problem with evangelism later. Challenge your team regularly to pray for and to invite their friends. Talk about the people you are praying to reach at every single gathering of the Launch Team. Spend time having each person tell about the specific people they are praying for. It cannot be stated strongly enough how important the investment of time in people will prove to be later in the launch process. Planters who don't spend enough time building relationships with those they hope to reach regret it later. Don't get discouraged. Growing the team from 10 to 25 is often the harder than growing from 1 to 10 (previous PlanterPlan Action) or from 25 to 50 (next PlanterPlan Action): in growing from 1 to 10, you leverage your existing relationships from 10 to 25 you are reliant on new relationships from 25 to 50 you leverage the existing Launch Team to reach their networks | Identify people to pray for and to build relationships with. Challenge your team to do the same. Be specific. Present your vision to as many people as possible. Cast a wide net. Be bold in approaching and asking people to join. Encourage them to pray about their role. Obtain a commitment from the interested people. Ask each committed member to identify 3 additional people as potential prospects. This action is complete once you have recruited 25 Launch Team members. |  | 151 | 60 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-14 content validated --pb 2020-12-14 changed Due in # Days from 150& to 212& & Duration from 60& to 90 --pb&
265 | 390 | 1290 | Expand Launch Team to 40 people | Grow the Launch Team to 40 adults so that critical mass is achieved and basic ministry roles for the Opening Day of worship gatherings can be filled. | Expanding the Launch Team to at least 40 people is a significant step to ensuring a large opening day launch. With 40 committed servants, most new churches will be able to live out their vision for opening day. Expanding a Launch Team might seem overwhelming for some planters. The pressure can be frightening. Don't fret. Take things one day at a time. Nearly every great team in history started small and grew healthily. Consider the following factors when you put a plan together for expanding the Launch Team: Prayer It is God's church and we are called to cooperate. We are joining him in what he has planned. If we believe it is his church then we must trust he will provide the people. We have to figure out what it means to cooperate. That starts with prayer Communicating Vision People are drawn to a clear and compelling vision. You must be able to communicate the vision with passion and you must teach your entire team to do the same. Your current team members need to be disciples of the church vision Relationships People are skeptical of religion and church. However, they are open to spiritual things. Relationships break down barriers to start conversations. Conversations are the starting point to building trust. Trust leads to cooperation. You can't spend enough time building relationships. One or two key relationships almost always open the door to many other relationships. Look for these key relationships. Often they are found in unexpected places Casting a Wide Net The more people you and your Launch Team pray for, the more people who will join your team. It's that simple. More conversations. More people Persistence Some people need to be asked multiple times before they respond. Don't pester people but also don't give up after one "no" Challenge Your Team Your current Launch Team members are your best assets for growing the team. The DNA / culture you establish with them carries forward to future years. If the team is not praying for and inviting friends, neighbors and co-workers, you will have a problem with evangelism later. Challenge your team regularly to pray for and to invite their friends. Talk about the people you are praying to reach at every single gathering of the Launch Team. Spend time having each person tell about the specific people they are praying for. It cannot be stated strongly enough how important the investment of time in people will prove to be later in the launch process. Many planters do not spend enough time building relationships with those they hope to reach. | Identify people to pray for and to build relationships with. Challenge your team to do the same. Be specific. Present your vision to as many people as possible. Cast a wide net. Be bold in approaching and asking people to join. Encourage them to pray about their role. Obtain a commitment from the interested people. Ask each committed member to identify 3 additional people as potential prospects. This action is complete once the planter has recruited 40 launch team members. |  | 212 | 91 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-14 content validated --pb 2020-01-13 content updated --pb 2020-12-14 changed Due in # Days from 120& to 122& --pb&
266 | 668 | 1290 | Talk to your Launch Team about money | Conduct a financial stewardship lesson or series well before Launch to make generosity and giving part of the new church's DNA. | The early financial health of the church will depend a lot on your willingness to talk with the Launch Team about money as a matter of being a disciple. The Launch Team should participate in the financial life of the new church. Talking about generosity and taking up offerings needs to happen at some point before Launch. But when? Planning and conducting financial stewardship training before Launch is one way to help the team understand the cost of what they are undertaking. And it may even be a good outreach event to serve people in your community who are struggling financially. Consider these financial training resources: <a href="https://www.ramseysolutions.com/ramseyplus/organization">Financial Peace University</a> <a href="https://goodsensemovement.org/">Good Sense</a> <a href="https://www.crown.org/">Crown Financial Ministry</a> If not an entire series, plan how to weave talking about generosity & sacrifice into your Launch Team meetings. | Discern the attitude of your Launch Team about giving. Select an appropriate financial training resource. Put the training date on the calendar. Conduct the training. This action is complete when you have taught the/first financial stewardship lesson to the Launch Team. | <a href="https://get.tithe.ly/blog/106-bible-scriptures-about-giving">Tithing in the Bible: A Short Guide to Tithes & Offerings (a breakdown of over 100 Bible verses about generosity)</a> by tithe.ly | 120 | 29 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content & links updated --pb 2018-04-20 moved to Preaching milestone --pb& 2020-01-24 content updated --pb 2020-12-16 changed Due in # Days from 110& to 180& & Duration from 7 to 14& --pb&
267 | 509 | 1290 | Schedule Preview Services | Get at least 4 preview services on the calendar ahead of Launch Sunday. | Preview services benefit the new church in many ways: Practice There are lots of details to take care of to pull off a worship gathering, particularly when you are mobile. Preview services give you a chance to get the kinks out. Outreach Conducting preview services gives your launch team an excuse to invite friends, family and co-workers. It's a good opportunity to expand the launch team and build momentum toward launch. Vision Preview services give you an environment to cast vision to the entire launch team and helps paint the picture for what worship gatherings will be like. The 2007 survey of over 2,200 church plants in <a href="https://a.co/3xHybAk">Planting Fast-Growing Churches</a> by Stephen Gray demonstrates a significant difference in the post-launch health and growth of churches that conduct multiple preview services: Of churches that conducted 3 preview services, 23% were fast-growing and 53% were struggling (p.115) Of churches that conducted 4 preview services, 25% were fast-growing but only 7% were struggling (p.115) Plan your preview services early - they impact the timing of other tasks in the launch plan: when to sign a facility contract when to order equipment when to execute your marketing campaign etc... To get 4 preview services in, you may have to plan them every other week leading up to the launch. That many monthly previews would require a very long on-ramp. | Get a calendar and work backwards from your prospective launch of worship gatherings. Watch out for holiday weekends, local school district breaks and major local festivals/events. Schedule at least 4 preview services. Add dates for preview services to the church calendar. This action is complete when you have scheduled preview services. | <a href="https://www.churchplantingtactics.com/what-is-a-church-plant-preview-service/">What is a Church Plant Preview Service?</a> on churchplantingtactics.com <a href="https://www.newchurches.com/resource/from-preview-to-launch/">From Preview to Launch</a> by Ron Sylvia on newchurches.com | 130 | 21 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard This task needs a complete review/update - request Pat's input.& ----ds I asked tom to do this for us ---pcf I consulted with Dave and Tom. I then simplified it. --sc 2017-03-31 removed rogue tags/formatting --pb 2017-11-15 content updated --pb 2022-11-21 updated links --sc 2018-01-24 moved additional resources to Actions section --pb 2018-08-21 tweaked title --pb 2018-10-30 replace broken link to dreamgrow.com with& infographic links --pb 2020-12-14 changed Due in # Days from 98& to 63 --pb& 2024-03-08 updated content & resource links --pb &
268 | 394 | 1290 | Delegate PlanterPlan tasks to others | Delegate actions from PlanterPlan to Launch Team members so that you are freed up to do what only you can do. | There are some things the lead planter cannot delegate. But most of what's here in PlanterPlan can be done by other people. Free yourself up to do the most important things that only you can do. Delegate. Now is the best time to establish a culture of delegation. If you want to establish a culture where the church grows beyond what you alone as the leader can accomplish, you have to delegate responsibility. In a church plant, delegating responsibility to Launch Team members is a healthy part of the process of getting people to take ownership for the vision. Once a Launch Team begins to come together, review all the outstanding tasks here in PlanterPlan (with a focus on the ones with your name on them) and identify tasks that can be delegated to people on the Launch Team. But don't limit yourself to just your Launch Team. Many tasks can be done virtually by extended family, friends, former neighbors, financial supporters or supporting churches. Some tasks require you to make a leadership decision after someone else has done the research or heavy lifting. If you don't have a volunteer, delegate the heavy lifting to a part-time, minimum wage helper (like a high school or college student). | Do an initial review of the outstanding tasks here in PlanterPlan for: tasks that only you can do tasks where someone else can do the heavy lifting for you tasks that anyone can do with a little oversight and/or training Think of a volunteer who could do each of the tasks not in the first category above. For volunteers with only 1 or 2 tasks, use PlanterPlan's email and/or print buttons to delegate the tasks. For key volunteers, leaders and staff that will have many tasks, invite them to collaborate on your PlanterPlan project using Project > Manage Team . Go through the list again and see if there are clusters of unassigned tasks that could be farmed out to a part-time seasonal hire. For any remaining unassigned tasks, get your Prayer Team praying for people to fill the gaps. This action is complete after you have identified and delegated every possible action from the PlanterPlan task list to someone else. |  | 122 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-14 content validated --pb& 2019-12-23 content updated --pb
269 | 396 | 1290 | Check in on your Opening Day Expectations | Revisit the Opening Day Expectations document to determine if the church plant is on track or if the track has changed. | Every plan needs to be flexible and adapt to a changing environment. Early in the planning process, you should have completed the <a href="/resources/item/197">Opening Day Expectations Worksheet</a>. Not all things will go according to plan. Assumptions that were made at the beginning of the planning process are subject to change. For instance, you may have planned to bring on additional staff early in the pre-launch process in order to more quickly build the Launch Team. However, a qualified staff member was not found. That changes the plan. Or perhaps, the plant had few partners in the beginning, but since then large donors have begun supporting the work. This has enabled the planter to hire additional staff and conduct a more robust marketing campaign. The result should be expectations for a larger Launch Team and larger attendance at opening day. It is important that the Oversight/Management Team and Launch Team have a good understanding of what is being worked towards. If original assumptions have changed, update the Opening Day Expectations document. It is important not to make these decisions alone. Seek the counsel of the Management Team when making changes to the Opening Day Expectations. This will ensure that you are making good decisions and that the church will be launched in a healthy manner. | Review the Opening Day Expectations Document created in an early PlanterPlan action. Based on new information, determine if it needs to be updated. Present any proposed updates to the Management Team for insight and affirmation. Communicate changes in the plan to the Launch Team. This action is complete when you have reviewed and updated the Opening Day Expectations Document. |  | 181 | 7 | 2000-01-01 05:00 | 2020-01-24 05:00 | 2000-01-01 05:00 | template: standard 2017-10-30 content validated --pb 2020-12-16 changed Due in # Days from 154& to 171& & Duration from 105& to 121& --pb&
270 | 679 | 1392 | Milestone: Implement Groups Strategy | Pull the trigger on the strategies you laid out in the previous Milestone to launch groups at the new church. | Now that the Groups Strategy has been planned based on context, aim and vision, it is time to execute the strategies. The first groups launched will have significant impact on the DNA of groups for years to come. |  |  | 155 | 95 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2018-03-29 overtyped legacy content about "add custom tasks to milestone" with new content --pb 2019-12-03 content validated --pb 2020-12-14 changed Due in # Days from 147& to 105 & Duration from 7 to 14 --pb&
271 | 680 | 679 | Build out groups in your church management software | Keep track of how many groups you have and utilize advanced groups functionality in your church management software. | All modern church management software (ChMS) platforms come with a groups module or feature. You will be able to create each group and add details like time, location, etc. You will also be able to assign its leader(s) and members. In the short run, you may be able to remember all of your current groups in your head. But that system is not scalable in the long run. Plus, many ChMS platforms provide extended functionality that you need to start practicing now, such as: taking attendance recording and sharing prayer requests summary reports from group leader to their coach group finder plugin for your website | Build each current and planned group in your ChMS. Decide which features to use and train groups leaders in using them. This action is complete when you have all of your groups built in your church management software. |  | 105 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2018-03-29 content updated --pb 2018-11-19 content updated & moved to subtask of #695 Issue Written Assimilation Strategy from #679 2012-12-02 content updated --pb 2020-12-16 changed Due in # Days from 137& to 155 --pb&
272 | 676 | 679 | Select group curriculum or content | Make strategic decisions about the content of the groups. | There are lots of options for the curriculum or content of the groups. Some of that may be driven by the kind of group in question. Common approaches include: Have the entire church going through the same curriculum simultaneously Have groups review the sermon and go deeper into the text Write your own curriculum in-house Use a simple Bible study framework (ex: <a href="https://soapstudies.com/">SOAP</a>) Allow small group leaders to choose curriculum based on the felt needs of the group etc. If you're going to let leaders choose their own curriculum, consider creating an approval process or publishing a list of approved resources. Group curriculum resources from theological camps different than yours are readily available online. | Decide on the format or content of each category of group you're starting. Include it in your Church Groups Strategy document. This action is complete when you have articulated the content or curriculum of each group type. | <a href="https://churchleaderinsights.com/small-group-curriculum-free-download/">Approved Small Group Curriculum</a> by Church Leader Insights | 74 | 14 | 2015-02-03 05:00 | 2022-11-16 05:00 | 2000-01-01 05:00 | template: standard 2019-11-26 content updated --pb 2020-12-11 changed Due in # Days from 154& to 67 --pb&
273 | 682 | 679 | Schedule first group leader training | Put the first group leader training on the calendar to proactively begin growing new leaders towards multiplying the groups. | Once a training plan has been developed and a job description has been written, set the wheels in motion to train new leaders. When you schedule the first training will depend some on the leaders and potential leaders God has provided. Anticipate the need to multiply groups and leaders, then put a training event or turbo group on the calendar to be ready. | Identify potential small group leaders. Have the ICNU conversation with each one. Based on who you have and how many groups you'll need, put leader training on the church calendar. Invite the leaders to the event. This action is complete when you have invited leaders & potential leaders to the first training event. |  | 74 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content updated --pb 2018-03-29 "small groups" changed to "groups" --pb 2019-12-03 content updated --pb 2020-12-14 changed Due in # Days from 168& to 90& & Duration from 7 to 30& --pb&
274 | 683 | 679 | Start first group(s) | Hold the first meeting of the first group and set the DNA of what groups will be like at the church. | You've dreamed up strategies for how to run groups at the new church. Now is the time for the rubber to meet the road! Start with the end in mind and be very intentional about what happens at the first group meeting. This becomes the precedent for how other groups are started. | Schedule a time and place for the first group meeting. Determine what the group leader will facilitate or lead during the meeting. Begin meeting on a regular, ongoing basis. This task is complete when the first group begins meeting on a regular basis. |  | 90 | 30 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 changed plan to strategy --pb 2017-12-26 content updated --pb 2012-12-02 content updated --pb 2020-12-16 changed Due in # Days from 147& to 162& --pb
275 | 489 | 1392 | Milestone: Develop an Outreach Strategy | Craft a thoughtful and coordinated approach to living out your values and beliefs in the community. | Outreach is being the hands and feet of Jesus. It is translating our good intentions into good deeds. James put it well: "In the same way, faith by itself, if it is not accompanied by action, is dead." James 2:17 As did John: "Dear children, let us not love with words or speech but with actions and in truth." 1 John 3:18 This milestone will help you translate your church's values and beliefs into works of service in the community. It encompasses both go and serve outreach (community service) as well and come and see outreach (events). |  |  | 135 | 44 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2018-02-16 content updated --pb 2012-12-02 content validated --pb 2020-12-14 changed Due in # Days from 112& to 108& & Duration from 7 to 1& --pb&
276 | 490 | 489 | Read this outreach overview | Brief yourself on what goes in to a cohesive outreach strategy and the process you'll follow to create one. | The tasks in this milestone will walk you step-by-step through crafting an outreach strategy that inspires your people to serve, makes a real impact in your community, and is sustainable. Your outreach strategy will contain: A brief philosophy of outreach A summary description of your community Brainstorm of potential events to participate in or host Goals for how many and what kind of events A plan to debrief events A pre-launch schedule of events you commit to The decisions you make here and the kinds of outreach you do in the first year will have a lasting impact of your church's culture and its reputation in the community. | Watch the Passion for Planting training video "<a href="/resources/item/201">Outreach - Starting Conversations</a>" featuring Ed Stetzer. This task is complete when you have read the content above and watched the training video by Dr. Ed Stetzer. |  | 108 | 1 | 2000-01-01 05:00 | 2022-08-26 04:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated, audience changed to coach --pb 2012-12-02 content validated --pb 2020-12-14 changed Due in # Days from 112& to 114 --pb&
277 | 491 | 489 | Call your coach about outreach | Open a conversation with your coach about outreach. | Outreach is the ministry where the church lives out its values and beliefs in the community. Spend time with your coach thinking through how to strategically reach out in the community. Sample issues to process with your coach: How to discover/discern the best ways to serve in the community The difference between outreach and community service Outreach and building your launch team Strategic community partnerships Sustainable pace of events | This task is complete when you have called your coach about outreach. |  | 114 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' and updated hyperlinks --pb 2018-02-16 updated content --pb 2018-06-01 additional resources subsection added,& gdoc& template added --pb 2020-02-26 outreach ministries list added --pb 2012-12-02 content validated --pb 2020-12-14 changed Due in # Days from 125& to 121& & Duration from 7 to 30& --pb& 2021-10-21 added Dad Camp --pb
278 | 492 | 489 | Craft an Outreach Strategy | Create a strategy for outreach in your community that both demonstrates your church's values and creates culture in your church. | Your written outreach strategy is simply the culmination of each of its subtasks. It will be a document that you can share with Launch Team members to help cast the vision for what you are trying to accomplish and to help individual members take ownership for the strategy. Your outreach strategy will contain: A brief philosophy of outreach A summary description of your community Brainstorm of potential events to participate in or host Goals for how many and what kind of events A plan to debrief events A pre-launch schedule of events you commit to | Download Passion for Planting's Outreach Strategy Template (<a href="/resources/item/200">MS Word</a> or <a href="/resources/item/375">Google Doc</a>) Fill in the blanks to craft your own Outreach Strategy. Add each scheduled event to your church calendar. Send the written outreach strategy to the coach for review. This task is complete when you've written down your strategy to reach out to your community. | <a href="/resources/item/199">Sample Outreach Ideas</a> from Passion for Planting Franchise/template outreach ministry ideas: <a href="https://generosityfeeds.org/">Generosity Feeds</a> <a href="https://www.mops.org/">MOPS</a> <a href="https://www.celebraterecovery.com/">Celebrate Recovery</a> <a href="https://www.ramseysolutions.com/ramseyplus/coordinator/guest?">Financial Peace University</a> <a href="https://alphausa.org/">Alpha</a> <a href="https://victorykidsports.org/church-partnerships/">Victory Kids Sports</a> <a href="https://www.loveinc.org/">Love, Inc.</a> <a href="https://www.mensfraternity.com/">Men's Fraternity</a> <a href="https://www.fathersinthefield.com/the-ministry/ministry-overview/">Fathers in the Field</a> <a href="https://www.dadcamp.info/dadnation.html">Dad Camp</a> | 135 | 44 | 2000-01-01 05:00 | 2021-10-21 04:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2018-02-16 content updated, additional& resources added --pb 2012-12-02 content validated --pb 2020-12-14 changed Due in # Days from 125& to 121& & Duration from 7 to 30& --pb&
279 | 493 | 492 | Research current events in the community | Investigate local events, festivals and causes that you may be able to partner with. | Western Christianity has a reputation for having a savior complex. You can minimize the "We're here to save the day!" effect when you partner with the good that's already happening in your community. There are major and minor events already happening all over your community that provide ample opportunity to jump in and help. To choose the best events to reach your target community, first understand what events are already happening in the community, and which are successful. This will help you determine which events best meet real needs in your community. Look for opportunities to participate in and even partner with local events. Participating might look like: renting a booth for a hydration or diaper changing staffing a children's bounce house or play area recruiting a team to clean up after the event etc. Many events have local sponsors who receive lots of publicity for sponsoring the event. Check into the cost of sponsorship to see if it's affordable. Sites for researching community events: <a href="https://www.meetup.com">meetup.com</a> <a href="https://nextdoor.com">nextdoor.com</a> <a href="https://www.eventbrite.com/">eventbrite.com</a> <a href="https://www.facebook.com/groups/explore/">facebook.com</a> - look for community groups <a href="https://craigslist.org">craigslist.org</a> <a href="https://patch.com">patch.com</a> your local online newspaper your local <a href="https://www.chamberofcommerce.com/chambers">chamber of commerce</a> your city's website Also do some offline research: check out local HOAs and community associations. And ask your friends and neighbors about events they know of, especially ones they usually attend. Don't try to compete with local events. They're usually done on a larger scale and with more excellence than a new church has the resources to pull off. Rather than investing all of your time in creating your own events from scratch, partner up. | Using the sites & ideas above, compile a list of your community's events. Determine which events to partner with and add these events to your outreach strategy document. This action is complete once you have compiled a list of current community events and determined which events can be partnered with. | <a href="https://www.churchplantingtactics.com/3-online-ideas-for-connecting-in-your-community/">3 Online Ideas for Connecting in Your Community</a> - churchplantingtactics.com | 121 | 30 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2018-02-16 content updated --pb 2012-12-02 content updated --pb 2020-12-14 changed Due in # Days from 119& to 121& & Duration from 14& to 7& --pb&
280 | 500 | 492 | Identify opportunities to partner with existing community leaders | Investigate other organizations and churches in your community that are already addressing the need(s) you've identified. | As you talk to individual community leaders, you'll probably start to notice recurring themes and patterns of community needs. When that's the case, you're not the only one to have noticed. Chances are there's already at least one organization in the community that is addressing that need(s). Ask around. Who are those groups? Who leads them? What are their events and programs? Who else can each of them introduce you to? Also dig around online. Do general searches based on the need and the name of your city. You can also look for directories of nonprofits in your area: <a href="https://www.guidestar.org/NonprofitDirectory.aspx">GuideStarg.org</a> <a href="https://www.melissa.com/v2/lookups/">MelissaData.com</a> <a href="https://apps.irs.gov/app/eos/">Exempt Organization Select Check</a> on IRS.gov When you partner with existing groups, it often results in your launch team serving side by side with pre-Christians who share a passion for meeting a specific need. That creates opportunities for your launch team not only to meet needs, but to build bridges with pre-Christians as they serve alongside them. | Strategically evaluate the community need(s) God is calling you to address. Investigate who is already meeting these needs in the community. Evaluate and document the opportunities for partnerships with various community leaders and groups. This action is complete when you have developed a list of partnership opportunities. |  | 121 | 30 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2018-02-16 content updated --pb 2012-12-02 content validated --pb 2020-12-14 changed Due in # Days from 132& to 128& --pb
281 | 499 | 492 | Assess passions and resources of launch team | Lay the groundwork for successful outreach by discovering the common heartbeat of your people. | Once you've identified community needs, assess not only your own passions, but also the passions of the team of people God has gathered to start the new church. Where their needs intersect with your team's passions will be the heart of missional ministry. Review the results of your own community needs research with them. See which needs resonate with the team. Ask the team how they would begin to meet the needs and what resources would be needed. Also consider your team's skills, professions and life experiences. It's not unusual to find a common thread that wasn't initially apparent. For instance, you may discover that half of your team works in the medical field. Or most of the team already volunteers for various nonprofits that protect the environment. Also re/visit the <a href="/resources/item/356">Collective Potential worksheet</a> provided by Auxano previously addressed in the Philosophy of Ministry milestone. Pray that the Spirit reveals what He had in mind when He called your initial team together. | Review your community's needs/assets with the launch team. Re/visit the <a href="/resources/item/356">Collective Potential worksheet</a> provided by Auxano. Determine which needs the team is most passionate about. This action is complete when you have assessed the passions and resources of the launch team. |  | 114 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2018-02-16 content updated --pb 2012-12-02 content validated --pb 2020-12-14 changed Due in # Days from 119& to 121& & Duration from 21& to 30& --pb&
282 | 494 | 492 | Determine your outreach philosophy | Articulate an outreach philosophy that will inspire your people to action. | Your brief outreach philosophy will answer the why . Serving in the community won't be sustainable without a Jesus-centered reason. Why should the church do outreach? Why should your people participate in outreach? What should outreach accomplish? How does outreach help make disciple-makers? Given your limited resources, what category/cause will you focus on? Cross-Check You developed your Vision Frame in a previous PlanterPlan milestone. Make sure your outreach philosophy fits within your Strategies and is consistent with your Values . Measuring Success Decide now how you're going to measure success. That might be: Number of marketing touch-points associated with an event Number of events joined or hosted Event attendance totals Number of conversations started with people at events Number of friends inviting friends to events | Review your Vision Frame, especially looking at how your values affect outreach. Using the principles above, write out a philosophy summary in your Outreach Strategy document. This action is complete when you have considered and prayed about these options and developed an outreach philosophy for the new church. |  | 121 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2018-02-16 content updated --pb 2012-12-02 content updated --pb 2020-12-14 changed Due in # Days from 119& to 121 --pb&
283 | 495 | 492 | Set a goal for number and type of outreach events | Set a challenging but reasonable expectation for how many and what kind of outreach events you'll execute prior to launching worship gatherings. | Too many planters get to opening day and wish they had done more outreach events. Types of Events There are at least 3 different categories of events: With Your Community - These events focus on partnering with the good that's already being done in your community In Your Community - These events focus on providing fun activities to build trust, create community and provide inviting opportunities for your team; these can be large-scale event you host collectively or smaller-scale events you encourage your team members to host For Your Community - These events are focused on community service and meeting real needs around you A solid outreach strategy has a mix of the different types of events. One approach is to try and partner with other organizations for big, regional events, and to focus most your time and money on smaller, relational events. Set a Goal Things that get measured get done. If you schedule 10 events, you're more likely to actually execute on 7 events than a planter who doesn't schedule any events but hopes to hit 7. Hope is not a strategy. Set a goal for the number of events you'll host or participate in. Passion for Planting strongly recommends that the you participate in or host at least one major event per month in the 4 months leading up to your launch. Also consider setting an expectation that every staff person or every family on the launch team will host at least one smaller event (block party, cookout, open house). At the very least, determine the total number of events you'll participate in during the 6 months leading up to launch, even if you don't specify the breakdown of large and small events. Remember that at this point, you're setting expectations, not selecting the exact events and dates. Establish the number and type, but be flexible to allow the specific events to change with time--simply hold yourself accountable to the number you set as an expectation. | Prayerfully determine how many events you should conduct in the 6 months leading up to launch. Identify a specific number goal for each of the three major types of events listed above. This action is complete when you have set a goal for the number of each type of event to be conducted prior to launch. |  | 121 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2018-02-16 content updated --pb 2012-12-02 content updated --pb 2020-12-14 changed Due in # Days from 119& to 121 --pb
284 | 496 | 492 | Develop a strategy for connecting with people at events | Decide in advance how you'll empower your Launch Team members to build relationships during outreach events. | At least one of the purposes of outreach should be starting conversations with strangers and making friends. But that doesn't come naturally for everyone on your team. Help them out by laying down some simple guidelines for making connections. Types of Events Keep in mind that the strategies will probably be different depending on the category of event: With Your Community - These events focus on partnering with the good that's already being done in your community In Your Community - These events focus on providing fun activities to build trust, create community and provide inviting opportunities for your team; these can be large-scale event you host collectively or smaller-scale events you encourage your team members to host For Your Community - These events are focused on community service and meeting real needs around you For example, if you're partnering with your community to clean up the trash after the local festival, your people may have less opportunity to engage strangers. A neighborhood block party hosted in your community by a Launch Team family should provide a different level of opportunity. Help your people think through the 'win' for each type of event. Simple Tools There are some simple things you can give to your people that will make connecting easier. Some ideas are: Have them memorize 2 stock questions for starting a conversation with complete strangers At a Launch Team meeting, get them to role-play starting conversations Order professionally-printed handouts like info business cards, bookmarks, or small postcards Order branded t-shirts for them to wear at the event Get a banded vinyl banner to hang from the booth you rent at the festival Order branded promo items like pens or helium balloons Create a 3-question community needs survey for people to fill out | For each type of event, hammer out a simple strategy to empower your people to start conversations. Order any tools you'll need for each event. Train the launch team on how to connect with people; consider some role play so they can practice getting the words out before the event. This action is complete when you have identified strategies for connecting with people at each outreach event. |  | 121 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-02 resource links updated --pb 2018-02-16 content updated --pb 2019-12-10 content updated --pb 2020-12-14 changed Due in # Days from 119& to 135& & Duration from 7 to 14& --pb&
285 | 501 | 489 | Coaching Checkpoint: review and affirm Outreach Strategy | Review the planter's outreach strategy and provide feedback on the ideas for serving and building bridges in the community. | Your planter's outreach strategy needs to be well thought through and coordinated in advance. The plan should be focused and intentional, rather than left to chance. It needs to: be appropriate to their target community and target family coordinate events and efforts to work together support the vision & values of the church plant The written outreach strategy document should include the following elements: A brief philosophy of outreach A summary description of his community Brainstorm of potential events to participate in or host Goals for number & types of events A plan to debrief events A pre-launch schedule of event commitments Read over the written outreach strategy and provide feedback to the planter. Specifically, affirm the number of outreach/serving events planned. Spend time talking through the strategy. Provide wisdom and insight for effective community outreach. | Read over the outreach strategy provided by the planter. Affirm his philosophy of outreach. Affirm the goals for number and types of events. Affirm the pre-launch calendar of events. Affirm that the budget supports the scheduled events. Affirm to the Network Partners in the coaching report that the planter's strategy is sufficient. This action is complete when you, the coach, have reviewed and affirmed the planter's Outreach Strategy. |  | 128 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard Need to update the process on how to add new tasks to a document. Does the text exist somewhere within the database already? Resources # 78 & 79& --am I added this text on how to add tasks. --sc 2017-03-31 updated from 'plan' to 'strategy' --pb 2019-12-10 content validated --pb 2020-12-16 changed Due in # Days from 139& to 135& & Duration from 32& to 14& --pb&
286 | 502 | 1392 | Milestone: Implement Outreach Strategy | Put into action the strategies laid out in the previous Milestone to build bridge with and in your community. | Now that your Outreach Strategy has been developed, it's time to put those strategies into action. This milestone already contains tasks common to most church plants. Take other action items resulting from the outreach strategy document and add them to this milestone. You can do that right in the PlanterPlan tool. Outreach will be an ongoing effort during the pre-launch phase of the church. Be sure to set a sustainable pace that will continue on after Launch Sunday. | --no steps-- |  | 130 | 74 | 2015-02-03 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template: standard 2019-12-10 content updated --pb 2020-12-14 changed Due in # Days from 125& to 128& & Duration from 14& to 7& --pb&
287 | 323 | 502 | Order a banner for events | Design and order a banner to create brand awareness at events. | Buy a banner to use at events you join or host. It helps with visibility and begins to establish the church's identity in the community. The banner should be generic enough so you can use it at any event. Basic banner types are: vinyl banner (make sure there's a place to hang it at the event!) flag or sail banner A-frame or sidewalk sign At a minimum, the banner should include your logo. If you have a website up, you should include your website address, too. Church Sign Vendors Here are some companies that have served our planters in the past: <a href="https://store.groupimaging.com/">Group Imaging</a> <a href="https://outreach.com/Church-Banners/?ref=TopNavJS">Outreach Marketing</a> | Browse sign companies to determine what type of sign to use for events. Work with your graphic artist or the sign company to design the banner. Have the banner printed. This action is complete when a banner for events has been ordered. |  | 128 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-10-27 content updated --pb 2019-12-10 content updated --pb 2020-12-14 changed Due in # Days from 112& to 128& & Duration from 14& to 7& --pb&
288 | 503 | 502 | Determine how to get the word out about outreach events | Create an intentional plan to get the word out to the community regarding outreach events. | Advertising outreach events serves two purposes: First, it will draw more people to the event so they can meet your people. Second, it will make people who don't come to the event aware of you and your church. Either way, it may help anyone who gets word have a good first impression about the church because they see you are active in the community. For events that you host or plan a major role in, determine to get the word out both online and offline. Create a goal to hit for each event, such as: post and promote the event on Facebook, and post 50 fliers in local business windows, and set up A-frame street signs, and send out photocopied mailers in the community There are lots of things that you can do to get the word out about each event: publicize on the church website send out a church e-mail blast include it in the preview service bulletin encourage your team to share it on social media post it on community calendars submit press releases submit it to local radio as a public service announcement Most of these methods are free. Create a simple publicity checklist of the tools that will be used for each event. | Brainstorm all the methods you might regularly use for getting the word out about events. Research the cost, timeline, and feasibility of each method. Create a publicity checklist that will be used for every event. Customize the checklist for each event as appropriate. Put the checklist into the hands of whoever is responsible for the event(s). This action is complete when the person responsible for planning each event has the publicity checklist and understands what expectations you have for getting the word out about the event in the community. |  | 128 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-02-16 content updated --pb 2019-12-10 content updated --pb 2020-12-14 changed Due in # Days from 125& to 128 --pb&
289 | 504 | 502 | Determine outreach equipment needs and purchase timeline | Plan ahead to purchase or rent any special equipment you'll need for your outreach event(s). | Depending on what you have planned, you may need special equipment for outreach events. It could be anything from commercial popcorn machines to bounce houses. Equipment can either be borrowed, rented, or purchased. Depending on how many times you're going to need the equipment, it may be better to buy it outright rather than keep renting it. For example, a commercial popcorn machine may cost $100 to rent and $1,000 to buy. It will only take 10 uses for the machine to pay for itself. Also consider in your decision where you'll store the equipment. Maybe you'd like to buy it but have no place to store it. For ideas on kinds of special events equipment to purchase, check out the <a href="/resources/item/74">Church Plant Equipment List</a>. | Review each event to determine what special equipment may be needed. Get price estimates and how much lead time you'll need to rent or purchase each piece of equipment. Decide what equipment to purchase. Make sure it's included in the budget. Add the equipment to your list of equipment to purchase. This action is complete when you have identified equipment needs and a purchasing timeline to support your outreach events. |  | 128 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard -- ok; verified by& amg 2017-03-31 updated from 'plan' to 'strategy' --pb 2018-02-16 content updated --pb 2020-01-13 content updated --pb 2020-12-14 changed Due in # Days from 126& to 130& & Duration from 7 to 21& --pb&
290 | 497 | 502 | Select and schedule outreach events | Put specific outreach events and service projects on the calendar and in the budget. You won't do what you don't plan | The list of possible outreach/service events is way bigger than your church will be able to accomplish. It probably wouldn't take you very long to make a list of over 200 different opportunities. You need a filter through which to decide what events to actually pursue. Here are a few considerations in developing your filter: Understand your target demographic and their felt needs - For example, if your target is young families with children, Bingo nights are probably not the right answer. Understand what other churches and organizations are already doing - Establish your own niche. Don't try to duplicate what is already being done well. Understand the reputation you are trying to establish - You will become known to your community as the " church". Outreach events will shape how people think of you. That's your brand. You may be known as the fun church, the legalistic church, the service oriented church, the church with the big building, or something else; but you will have a reputation. Use outreach events to build that reputation. Determine the intended size and/or reach of events - Some events are quick and easy to pull off. They don't take a lot of time and effort; others do. Obviously there is a trade off: you might be able to do 10 small neighborhood events for each large regional event. However, you will get 10x as many people and name recognition with a regional event as you will with a local neighborhood event. Plan a balanced mix of different size events. For example, you may plan one large regional event the weekend before launch Sunday. In the three months prior to launch, you may have one community event each month. In addition to these community and regional events, you may challenge your launch team to take ownership for local neighborhood events. There is no shortage of great outreach event ideas. Ask around your ministry circles and review Passion for Planting's <a href="/resources/item/199">Sample Outreach Ideas</a>. Wherever possible, meet with local community leaders to discuss their knowledge of the community and which events may be most strategic. Review these lists and add additional potential events based on your knowledge of the target area. After a thorough review, consolidate the list to include only those items which are strong possibilities for your target area. This process of removing items from the list will be largely driven by your personal preferences and understanding of the target area. If you have trouble narrowing the list down, use the <a href="/resources/item/80">Outreach Event Selection Worksheet</a>. Each church will earn a reputation in the community. Choose outreach/service events deliberately to help shape and form a positive reputation. Every event on your shortlist will not necessarily come together. Think of it as a 'wish list' of events. Avoid events which are already common in the area. For example, if three other churches already have successful fall festivals, do something different in the fall, or maybe use a festival concept at different time of year. Although the schedule may change over time, it is super helpful to tentatively schedule events as early as possible (even before you are certain about them). This will give you the opportunity to pray through the calendar and consider what types of events may be successful during specific times of the year (back to school, summertime, Holidays). | Grab your list of events and service projects already happening in your community. Review the <a href="/resources/item/199">Sample Outreach Ideas</a>. Brainstorm additional ideas to add to your list. Get input from your launch team and add those to the list. Identify existing events being conducted by the community and decide whether to pursue participation in these events (e.g., sponsoring kids programming at a community celebration). Use the filters above to narrow the list down. Select specific events consistent with the goal you set for how many to do. Do not worry about getting exactly the right events. It's OK to change a specific event later. Put them on the calendar now as place holders to ensure that you do an event during that time frame. Tentatively select dates for each event and put them on the church calendar. Identify a budget for each event (rough estimate, not exact numbers). This action is complete when you have developed an initial schedule of events. |  | 135 | 14 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2012-12-02 content updated --pb 2020-12-14 changed Due in # Days from 105& to 114& & Duration from 14& to 7& --pb&
291 | 1393 | 1392 | Milestone: Develop Strategy for Streaming Content | Create a strategy to stream devotionals, sermons and/or worship services prior to the launch of in-person worship gatherings. | [content pending] |  |  | 112 | 21 | 2021-01-15 05:00 | 2022-01-20 05:00 | 2000-01-01 05:00 | template: 2022-01-20 changed "digital launch" to "streaming content" language
292 | 1394 | 1393 | Read this service streaming overview | Understand why streaming devotionals, sermons or worship services prior to the launch of in-person worship gatherings is becoming a non-negotiable. | There are several reasons you should stream content prior to gathering weekly in person. People Will Check You Out Online Before you go to a new restaurant, hotel, dentist, etc. you check them out online, right? You want to know what their offerings are and what people are saying about them. The same will be true of your in-person worship gatherings. Come your first anniversary, it's highly likely that guests will have binge-watched your church's video content before showing up in person the first time, even if they've been invited by a friend. If you start posting sermons & similar content only beginning with your grand opening of in-person worship gatherings, what will people base their decision to come on? You need to have a library of sermons, lessons, devotionals and/or even worship services already published. Launching streaming content will allow you to engage with people now and provide the discipline to create content consistently. You Can Reach People Now There are some people in your community that you'll never meet unless you run into them online. And whether it starts with a social media interaction or else-wise, especially online they're going to check you out first. If that's where they're spending hours and hours each day, meet them where they live and be ready to engage them with content. It Helps Your Website Rank It takes time and consistency to get found by search engines like Google. Would you rather get to the grand opening in complete online obscurity or with established online credibility and web rank? The hands-down best thing you can do to increase your website rank is to post new, relevant content on a regular basis. Fortunately, launching streaming content is easier than ever and not terribly expensive. And there are different ways to approach it; it is not one-size-fits-all. | Read the content above. Commit to planning out some version of a streaming content launch that will happen ahead of the launch of in-person worship gatherings. This action is complete when you have read the content of this overview. |  | 92 | 1 | 2021-01-15 05:00 | 2022-01-20 05:00 | 2000-01-01 05:00 | template:
293 | 1395 | 1393 | Call your coach about launching streaming content | Open a conversation with your coach about how to utilize streaming teaching and/or worship as a steppingstone toward in-person worship gatherings. | The pandemic forced churches to create an online church option, which has quickly become an expectation that all churches follow suit. Talk to your coach about how you will utilize a content streaming launch as part of your overall launch strategy. Sample issues to process with your coach: What the coach has learned recently about having taken their church online How similar or different online church should be to in-person worship gatherings Whether to edit video in-house or hire it out Which platform(s) to stream or broadcast on When to start streaming content in relation to the in-person launch | This action is complete when you have called your coach about launching content streaming. |  | 98 | 7 | 2021-01-15 05:00 | 2022-02-08 05:00 | 2000-01-01 05:00 | template: 2021-04-19 video content added --pb 2022-01-20 changed "digital launch" to "streaming content" language, updated broken video link
294 | 1396 | 1393 | Craft a Content Streaming Launch Strategy | Put together a document that includes your philosophy and strategy for using a content streaming launch strategy in conjunction with your in-person launch. | [content pending] |  |  | 105 | 7 | 2021-01-15 05:00 | 2022-01-20 05:00 | 2000-01-01 05:00 | template: 2022-01-20 changed "digital launch" to "streaming content" language; fixed broken video hyperlink --pb
295 | 1397 | 1396 | Define what a successful content streaming launch looks like | Quantify what a 'win' looks like for your content streaming launch so you can know if you've hit it. | <a href="https://drive.google.com/file/d/13qAgHIG9mM-FkZmI_WLNBuhTtzK_wq-b/view?usp=sharing"> </a> | Watch the video above. Paint a word picture of what a successful content streaming launch looks like. Articulate what you'll measure and prayerfully set a goal for each. This task is complete when you have written out the narrative and metrics for your content streaming launch. |  | 105 | 7 | 2021-01-15 05:00 | 2023-10-18 15:10 | 2000-01-01 05:00 | template: 2021-04-19 video content added --pb 2022-01-20 changed "digital launch" to "streaming content" language
296 | 1398 | 1396 | Determine your approach to reaching non-christians with streaming content | Choose ways and means to connect online around your streaming content that is likely to open conversations with those who don't believe, or are even antagonistic toward church. | <a href="https://drive.google.com/file/d/1R6pfMbjXWByF9VqOrcOg_VMUqgSIsz91/view?usp=sharing"> </a> | Watch the video above. Interview multiple non-Christians in your community and/or target audience about where they connect with people online, and what would be a way they'd welcome someone starting a spiritual conversation with them. Choose specific platforms you'll use to reach your target audience based on where they spend time online. Describe in writing how you'll generally open spiritual conversations with people online (prompts, guidelines, etc). This task is complete when you have a written, actionable approach to reaching non-Christians online. |  | 105 | 7 | 2021-01-15 05:00 | 2022-01-20 05:00 | 2000-01-01 05:00 | template: 2022-01-20 changed "digital launch" to "streaming content" language
297 | 1399 | 1396 | Determine your strategy for creating community online | Create an intentional plan for getting those who show up online for your streaming content into an ongoing relationship with each other. | <a href="https://drive.google.com/file/d/1AfTBdYWT9vpVPx5HaUA1BOgV6vastPr-/view?usp=sharing"> </a> | Watch the video above. Ask several people within your target audience about where they find community online, especially those that are non-Christians. Write out the several practical steps you will take to get online participants into relationship. This task is complete when you have written out a practicable strategy for creating community online around your streaming content. |  | 105 | 7 | 2021-01-15 05:00 | 2022-01-20 05:00 | 2000-01-01 05:00 | template:
298 | 1400 | 1393 | Coaching Checkpoint: Review and affirm Content Streaming Launch Strategy | Ensure the planter has made contextual decisions on how to utilize streaming devotionals, sermons or worship services in conjunction with the launch of in-person worship gatherings. | Review the planter's Content Streaming Launch Strategy document. Either encourage the planter to rework the insufficient section(s) or affirm that it is a workable and contextual strategy. The document should include: A definition of 'success' and/or goals for a content streaming launch A strategy to reach non-christians and what that target audience looks like for them An understanding of the content that the target audience expects A strategy to get participants to interact online and begin forming community | Review the planter's Content Streaming Launch Strategy document and provide feedback where necessary. This action is complete when you, the coach, have reviewed and affirmed the planter's Content Streaming Launch Strategy document. |  | 112 | 7 | 2021-01-15 05:00 | 2022-01-20 05:00 | 2000-01-01 05:00 | template:
299 | 1401 | 1393 | Purchase AVL hardware for content streaming launch | Get your hands on the equipment you'll need to stream or broadcast online content. | [content pending] |  |  | 112 | 7
300 | 605 | 1392 | Milestone: Develop a Marketing Strategy | Create an intentional strategy to let your community know about the new church. | You cannot avoid marketing the new church. Whether you're intentional about communicating with the community at large and unchurched individuals, every time they see or hear about the church, that is marketing . Marketing is simply communication. "The greatest Message deserves the greatest marketing." -Mark Batterson This milestone will take you through the exercises of putting together a consistent and comprehensive marketing strategy that is customized to your community. You will also create a marketing budget and be stretched to think creatively about marketing. | --no steps-- |  | 227 | 183 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-11-29 content updated --pb 2018-10-26 content updated --pb& 2019-12-23 content updated --pb 2020-12-14 changed Due in # Days from 119& to 115 & Duration from 7 to 1& --pb&
301 | 606 | 605 | Read this Marketing Strategy overview | Brief yourself on what goes into a Marketing Strategy and the process you'll follow to create one. | Before you jump into cooking up a marketing strategy, there's some pre-work you need to do: 1. Uncover Your Assumptions You have them. You need to be able to name them before you move forward so that you'll be open to new ideas and the Spirit's prompting. 2. Study Your Community Get to know your community and the kinds of people God is calling you to reach. Understanding their lives, their stories, and their motivations will help you meet them where they are with your marketing. And not every marketing medium works in every context. Research what works in your community and find creative ways to test your message before you spend big bucks on getting the word out. Start vs Launch "When you start something, you tiptoe in and quietly offer it to your community. When you launch something, you make a big deal and announce its arrival to the people in your community and beyond." Rich Birch on <a href="https://unseminary.com/5-lessons-church-leaders-can-learn-from-the-all-day-breakfast-trend/">unSeminary.com</a> This Milestone The tasks in this milestone will walk you step-by-step through crafting a marketing strategy that makes sense for your church, your community and your wallet. Your marketing strategy will contain: A brief philosophy of marketing Description of the stages of connectedness What your message will actually say Potential methods brainstorm Specific media choices | Read the brief overview above. Watch the Passion for Planting training video "<a href="/resources/item/166">Marketing - Communicate Your Identity</a>" featuring Ed Stetzer. This task is finished when you've read the content and watched the video. | <a href="https://www.churchplantingtactics.com/5-practical-church-plant-marketing-tips/">5 Practical Church Plant Marketing Tips</a> from ChurchPlantingTactics.com | 115 | 1 | 2000-01-01 05:00 | 2020-12-23 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2017-05-31 updated content, changed audience to coach --pb& 2019-12-23 content updated --pb 2020-12-14 changed Due in # Days from 119& to 121 --pb&
302 | 607 | 605 | Call your coach about marketing | Open a conversation with your coach about marketing. | You have to get the word out about the new church. Gone are the days of putting out a shingle and waiting for people to show up. You need to have a well-thought-out plan of proactively communicating with the community about the new church. Sample issues to process with your coach: Apprehensions or reservations about marketing Affording marketing What's working right now Measuring ROI How to incorporate digital and social media marketing | This action is complete when you have called your coach about marketing. |  | 121 | 7 | 2015-02-03 05:00 | 2021-07-27 04:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' and fixed hyperlinks --pb 2017-12-15 content overhauled & new links tested --pb 2018-06-01& gdoc& template added --pb 2018-07-09 content updated to reflect changes is subordinate task names --pb& 2019-12-23 content updated --pb 2020-12-14 changed Due in # Days from 133& to 142& & Duration from 7 to 28& --pb&
303 | 609 | 605 | Craft a Marketing Strategy | Create a strategy for marketing your new church to the community in a way that can be heard by the community. | The Marketing Strategy document is aimed at crafting a well-thought-through approach to telling your church's story in a way that your community can relate to. Work through the following sub-tasks and put your completed answers in the Marketing Strategy Template (below). Wordsmith your messaging Determine the best ways to get the word out in the community Estimate marketing costs and lead times Be sure to include the following key information: A basic philosophy of church marketing Who you audience is What you're going to say to them What you want them to do (call to action) How you'll maximize word of mouth invitations Which other media to use What your post-launch marketing will look like Repetition is Key In your strategy, take a "six to stick" approach: get at least six positive touches to every household in your target area before you launch expensive media campaigns like direct mail postcards. It takes at least 6 positive touches to build name recognition. A touch is any interaction with a person including: personal conversations web pages views service events (serving or being served) social media engagement signs & flyers etc... It doesn't take tons of money to get 6 positive touches. It does take coordination and planning to ensure the networking, marketing and outreach strategies are integrated and complimentary. This is so important that you should consider postponing the launch if you've had only minimal marketing exposure in your community. | Download Passion for Planting's Marketing Strategy Template (<a href="../../../resources/item/169">MS Word</a> or <a href="../../../resources/item/371">Google Doc</a>). Work through the subtasks which follow. Compile all of your ideas and answers in the template. Send your completed Marketing Strategy to your coach for feedback. This action is complete when you have sent your Marketing Strategy document to your coach for review. | <a href="../../../resources/item/168">Sample Marketing Strategy</a> from Passion for Planting Book Review: <a href="../../../resources/item/50">Church Marketing 101</a> | 227 | 183 | 2000-01-01 05:00 | 2024-07-16 20:41 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2017-12-15 content updated --pb 2019-12-23 content updated & links verified --pb 2020-12-14 changed Due in # Days from 125& to 142& & Duration from 7 to 14& --pb&
304 | 1402 | 609 | Articulate your church's brand promise | Put into words the promise your church is making for its community. | Your church's brand is its promise. It's a promise about who you are and what you have to offer your community. Your brand is not your logo. A logo should help you communicate your brand, but it's not the brand itself. Your brand is not even who you say you are. Your brand is what others think about the church. What people think about when they interact with your church will become your brand whether that interaction is online, in person, or through a marketing piece. Since branding plays such a big role in what your community associates with the church it's imperative that your church intentionally shapes its brand. That way your promise to the community accurately represents who the church is and what it values. Now is the time to develop your brand promise. As you're laying the foundation for the church it's time to describe in words the brand of your church, how you want to be perceived by your community. Spend time developing language to describe the promise you're making to your community about your church. This language should reflect your church's vision, mission and core values. Are you a fun church? A friendly church? A hip church? A family-oriented church? A community-focused church? A loving church? You may think, "We're going to be all those things," but you won't be. Plus, your brand will be stronger the more focused, unique, and distinctive it is. Once you've decided what your church brand will be, you'll then need to work to make sure your church reflects that promise. For instance, if you brand yourself as a friendly church, you'll need to make sure your church makes newcomers feel welcome the moment they begin to interact with your church whether in person or online. If you brand yourself as a fun church, people better not struggle to stay awake during your worship gatherings. If they do, you'll quickly become the boring church. So what is your church's promise to the community? What do you want them to feel and experience at your church? What do you want people to think when they visit your website and review your social media posts? Think about the answers to those questions and then put into words what you want your church to be known as and for by your community. | This action is complete once you've articulated what people in your community will be sure to experience when they check out the church. |  | 135 | 14 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template:
305 | 1296 | 609 | Wordsmith your messaging | Craft the message(s) you will use in your various marketing media with the unbeliever in mind. | The actual words your marketing delivers is more important than the medium itself. If you use churchy, insider language, you're only going to reach people that already go to church (or maybe a few that stopped going). The Unbeliever Filter Write everything as if you were talking with someone that has zero church background. Overwhelmingly in US culture today, people don't want to hear about church. And yet, overwhelmingly, people are open to hearing someone's story about Jesus. How does that reality influence what you say in your marketing? Also, you need to check your assumptions about what might be important to them in a church if they decided to check it out. It's not "rockin worship". Here are some phrases we suggest not using in your marketing: Spirit-filled worship Contemporary liturgy We only use the ____ version of the Bible We're another church to choose from On the other hand, it's easy to bash the established churches in your city in an effort to differentiate yourself. "We're awesome, and the other churches are old and sucky!" is not a Kingdom win. Heartstrings & Misconceptions "We're a brand new church having a grand opening," is not particularly newsworthy or compelling these days. You need messaging that really connects with people in your community. One way is to address felt needs in your community. Communicate that you get them and what they go through. Connect on heartstring issues like relationships, money, purpose, self-worth, anxiety, loneliness, etc. Another way is to lovingly address common misconceptions about the Church. If people in your area think the Church just tells people what to do, your message might be, "A safe place to ask questions." If they think the Church is judgemental, your message might be, "Church for the rest of us." Test before You Spend Whether you're going to spend $1,000 of a Facebook campaign or $10,000 on a direct mail campaign, wouldn't it be great to know that your message resonates with your audience? There's an old marketing trick that will help you refine your message and make sure it connects with the people in your community: the A/B Split Test. Basically, you put 2 different ads out there and see which one performs better. Both Facebook and Google have this functionality built in and will provide you with the analytics to know exactly how much better the one is doing. At the very least, ask your non-Christian friends for brutally honest feedback. Or ask people at the coffee shop for feedback. Don't just cross your fingers and hope for the best. | Spend quite a bit of time in prayer about the messaging. Craft several initial messages. Test those messages to see which one connects better. Finalize your messaging to include in various marketing media. This action is complete when you have tested and finalized your marketing message. |  | 142 | 14 | 2019-11-01 04:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template:
306 | 610 | 609 | Determine best ways to get the word out | Become a student of your community to determine which forms of communication and marketing will connect with your target families. | Just doing some marketing won't produce results. Doing the right marketing will. Certain types of marketing are more effective in specific geographic areas. You need to learn which types of marketing are most effective in your local area. Quickly. If you're not sure, talk with neighbors and strangers to get their input on what gets their attention. Also pay attention to what local advertisers are doing, like Realtors, dentists, etc. | Brainstorm a bunch of different ways of getting the word out. Ask locals about what marketing they have received that got their attention. Observe what marketing methods local businesses use. This action is complete when you've developed a brainstorm list of the marketing methods that will be the most effective in your community. Additional Resources <a href="/resources/item/167">Sample Church Plant Marketing Ideas</a> by Passion for Planting <a href="/resources/item/97">Church Plant Guerrilla Marketing</a> by Passion for Planting <a href="https://churchmarketingsucks.com/2007/11/lessons-in-not-sucking-cheap-marketing-ideas-for-church-planters/">Cheap Marketing Ideas for Church Planters</a> by Brad Abare |  | 142 | 14 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-12-15 content updated --pb 2018-07-09 title changed from "determine marketing costs..." to "estimate marketing costs..." --pb& 2019-12-23 content updated --pb 2020-12-14 changed Due in # Days from 125& to 135& & Duration from 14& to 7& --pb&
307 | 611 | 609 | Estimate marketing costs and lead times | Do some initial research into how much time and money each of your most effective media options will take. | Before you can make informed decisions about your marketing methods, you need to know if you have enough time and money to pull them off. Traditional media like direct mail, billboards and radio ads can take 60+ days from contract signing to broadcast. It just plain takes time to design, produce and deliver the goods. Giving yourself enough time will also save your money. For example, promotional giveaway items like pens and Frisbees are generally less expensive the further out they can be ordered. If you wait until the last minute, you might still get the items on time, but you'll pay rush fees and other versions of the 'stupid tax'. And don't forget: your website needs to be live before your marketing hits the streets. Publishing a website always takes longer than expected. | For each effective marketing method you brainstormed in the previous task, identify 1 or 2 reputable providers that will provide a quality product or service. Enlist team members and supporters to contact each provider to find out what their time frame is for production and how much the product or service will cost. Delegate this research out as much as possible. Compile all of the research into a quick chart or spreadsheet such as P4P's <a href="/resources/item/391">Church Plant Marketing Plan Template</a>. This action is complete when you have compiled all of the research. |  | 135 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2017-12-15 content update --pb 2018-07-09 title changed from "develop marketing schedule..." to "finalize marketing schedule..." --pb 2020-01-24 content updated --pb 2020-12-14 changed Due in # Days from 126& to 151 --pb&
308 | 589 | 609 | Develop social media goals | Develop social media goals to discern if your time invested is effective or better invested elsewhere. | In crafting social media goals, you'll need to decide: Why are we getting involved in Social Media? What is the motive? What does the 'win' look like? What is the daily or weekly time involvement expectation? Who can help me do this? Write down quantifiable goals and communicate them to staff and ministry leaders. Here are some suggestions: number of posts follower count average post reach number of shares or retweets number of visitors from social media sites to your church website church website bounce rate for visitors linking from social media sites number of conversations through social media | Consider the questions above. Write out your goals (monthly growth, year-end goal, etc). Clearly communicate the goals to your team. This action is complete when you have distributed written goals to key staff and ministry leaders. | <a href="https://careynieuwhof.com/some-awkward-questions-about-how-to-measure-online-church-attendance-5-growth-strategies/">Some Awkward Questions About How to Measure Online Church Attendance (+5 Growth Strategies)</a> by Carey Nieuwhof <a href="https://www.churchproduction.com/education/analytics-for-live-streaming/">Analytics for Live-Streaming?</a> on ChurchProduction.com <a href="https://socialchurch.co/how-to-create-social-media-strategy-7-steps/">How to Create a Social Media Strategy in 7 Steps</a> by Social Church <a href="https://unseminary.com/10-churches-you-may-not-have-heard-of-to-follow-for-social-media-inspiration/">10 Churches (You May Not Have Heard Of) to Follow for Social Media Inspiration</a> by unSeminary | 142 | 7 | 2015-02-03 05:00 | 2021-10-28 04:00 | 2000-01-01 05:00 | template: standard 2017-11-17 content updated --pb 2018-03-21 additional resources subsection added --pb 2020-12-14 changed Due in # Days from 105& to 135& --pb& 2022-11-21 links updated --sc
309 | 613 | 605 | Coaching Checkpoint: review and affirm Marketing Strategy | Review the planter's Marketing Strategy and provide feedback on the ideas for getting the word out in his community. | The planter has done research to determine which marketing methods will be effective and affordable in the local context. That research and other key decisions will be compiled in the Marketing Strategy document, which should include: A basic philosophy of church marketing Who the audience is What he's going to say to them What he wants them to do (call to action) How he'll maximize word of mouth invitations Which other media to use What post-launch marketing will look like Read over the Marketing Strategy and provide feedback to the planter. Spend time talking through the strategy, providing your wisdom and insight. | Review the written marketing strategy. Affirm that the messaging has been contextualized to the planter's community. Affirm that the volume of media chosen will be sufficient to reach the community. Affirm that the variety of media chosen will be make the message unavoidable in the weeks leading up the grand opening of worship gatherings. Affirm that the planter has planned out enough time and money to execute the strategy. This action is complete when you, the coach, have reviewed and affirmed the planter's Marketing Strategy. |  | 149 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2020-12-16 changed Due in # Days from 245 to 227& & Duration from 170& to 153& --pb&
310 | 1403 | 605 | Set initial marketing budget | Determine how much money your church will allocate for marketing. | The Coca-Cola company spends over 4 Billion dollars a year on marketing. That's approximately 18% of its yearly earnings. That's a lot of money, but yet again in business oftentimes you have to spend money to make money. Like businesses, church can spend large portions of their budget on marketing. They can build and host dynamic websites, contract with digital marketing companies to manage their social media platforms, saturate their community with a direct mail campaign, and run countless online ads in every crack and crevice of the internet. If your church wanted to spend thousands of dollars on marketing, there would be no shortage of ways to do that. The question you need to wrestle with is how much money you want to spend on marketing. Spend time reviewing your church's budget. Think about how much you've dedicated to budgeting. Once you've settled on a number you're comfortable with (make sure you have the funds committed), then it's time to develop an initial marketing budget. This budget will break down how you will spend money allocated for marketing. Don't settle for a one line marketing budget. Break it down into specific categories. Identify how much money will be spent on which types of marketing (branding, website, promotional material, direct mail, social media ads, etc.). Finally, once you've decided how much money to spend in each category it's time to determine when you'll spend that money. Most church planters don't have a lump sum of money just waiting to be spent, so for cash flow purposes it's important that you incorporate the marketing budgeting into the overall budget to make sure you're not planning on spending money you don't have. | Estimate the amount of money you will spend on marketing. Break down that amount into what you'll spend on specific marketing methods. Schedule when you'll be spending money on marketing and account for those by adding them into your church budget. This action is complete when the marketing budget has been added to the church's budget. | Church Budget Template (<a href="/resources/item/25">MS Excel</a> or <a href="/resources/item/366">Google Sheet</a>) by Passion for Planting <a href="/resources/item/22">Sample Church Plant Budget</a> by Passion for Planting <a href="https://www.churchplantingtactics.com/create-a-church-plant-budget/">How to Create a Church Plant Budget</a> on churchplantingtactics.com <a href="https://www.churchplantingtactics.com/how-to-review-a-church-plant-budget/">How to Review a Church Plant Budget</a> on churchplantingtactics.com | 149 | 7 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template:
311 | 614 | 1392 | Milestone: Implement Marketing Strategy | Pull the trigger on the strategies you laid out in the previous Milestone to announce your new church to your community. | Now that the marketing strategy has been carefully planned based on audience, time tables and budget, it is time to execute the strategy. There will be a big push leading up to the launch, but marketing needs to be an ongoing discipline for the life of the congregation. | --no steps-- |  | 227 | 183 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2017-12-15 content update --pb 2020-12-14 changed Due in # Days from 170& to 167& & Duration from 7 to 1& --pb &
312 | 615 | 614 | Read this marketing implementation overview | Execute your marketing strategies so that everyone you've been interacting with in the community gets invited to the launch of worship gatherings. | Marketing your church's grand opening of worship gatherings is both a sprint and a marathon. Some media you selected may be months in the execution. You've got one chance to celebrate the launch of your worship gatherings. Now is the time to make the most of it. Marketing done poorly will hurt you. Put the time and effort into the design process to ensure all your marketing efforts are coordinated and effective. Delegate as much as possible. There are many things in church marketing your capable staff and volunteers could do well so you can spend your time building teams, investing in leaders, and staying out in the community. | Put important design, production and delivery deadlines on your calendar. Delegate as many tasks as possible. Follow up with all marketing actions to be sure that they are carried out on time and within budget. This action is complete when you have an accountability process in place and have pulled the trigger on all of your marketing media. |  | 167 | 1 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-15 overwrite legacy "press release" content with new online review content --pb 2017-05-15 changed "due in # of days" from 231 down to 171 to push it earlier in the process --pb 2018-08-02 updated bing & apple maps with strikethroughs& --pb 2019-12-11 additional resources subsection added --pb 2020-01-24 content updated --pb 2020-05-29 'disappearing reviews' section added, image added --pb 2020-12-14 changed Due in # Days from 171& to 196& & Duration from 14& to 30& --pb&
313 | 1404 | 614 | Get 50 professional photos of team members and events | Capture high-quality photos at launch team events and gatherings to highlight in your marketing efforts. | You want to be able to share your church's story with your community. While you'll be able to do this through personal conversations, you'll also be able to do this through various mediums like your website, social media and other marketing tools. Since a picture is worth a thousand words, it's helpful to have high quality photos of your team to help you share your story with the community. From your very first team gathering have a photographer snaps some pictures of you and the team. Whether it's at a Bible study, a community service event, or a launch team party, make sure you're capturing these events with photos. Unfortunately, there are many new churches that have to fill their website and social media platforms with stock photos because they overlooked this task. Their website ends up looking like a Sears catalog, instead of a unique, authentic, life-giving spiritual community. Don't settle for bland marketing. Share what's really going on with your church through photography. | Identify someone on your team or a friend who's a professional photographer. Ask them to come to some of your first events to take pictures. Get 50 pictures from the photographer showcasing your events that you can use for marketing purposes. This action is complete when you have these 50 photos. |  | 98 | 7 | 2021-01-15 05:00 | 2021-05-03 04:00 | 2000-01-01 05:00 | template:
314 | 1405 | 1404 | Create media disclaimer sign | Create a media disclaimer sign and page for the church website. | Capturing photos at church events is a must for churches. Photos and videos from service events and launch team gathering will help you share your church's story. However, not everyone who comes to your church gatherings will be comfortable having their picture taken and shared on the internet or even on print material. That's why it is important to create a media disclaimer sign that you can put up at events when you'll be snapping pictures or recording video. What should this sign say? Google Church media disclaimer sign and you'll find several examples of what to say on the sign. Basically, it'll say you're taking pictures or video that may be included in church promotional material and if anyone does not wish to have their image recorded and shared to let the church know. If you have church insurance, you should check to see if they have a media disclaimer already developed for you. Keep in mind we're not lawyers, so consulting with a lawyer in your area and asking them about how to capture and share media safely is advised. | Read <a href="https://prochurchtools.com/how-real-churches-get-photo-release-forms-ep-178/">How Real Churches Get Photo Release Forms</a> by Pro Church Tools. Check with your church's insurance company about a media disclaimer form. Develop language to put on a sign that you can display at church events. Design and print the media disclaimer sign. This task is complete once the media disclaimer sign is in your possession. |  | 98 | 7 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template:
315 | 1406 | 1404 | Get signed media release forms for minors | Obtain a photo release form that asks guardians for permission to capture photos or video of their children at church events. | Sharing pictures and videos of children at church gatherings without consent from their parents or guardians is asking for trouble. That's why you should develop and distribute a media release form that grants your church permission to take pictures and video of their children and publish them. Your church insurance company probably already has a form like this. Take their form and modify it to fit your church's brand. Here's an example from <a href="https://www.brotherhoodmutual.com/resources/safety-library/risk-management-forms/photo-use-agreement1/">Brotherhood Mutual</a>. Consider including this release form as a part of the registration form for your children's ministry. | Develop your church's media release form for minors. Add this form to your children's ministry registration form. This task is complete once the form has been developed and is ready to be distributed to parents/guardians. | <a href="https://www.churchplantingtactics.com/church-photo-release-forms/">Free Church Photo Release Forms</a> by ChurchPlantingTactics.com | 98 | 7 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template:
316 | 612 | 614 | Finalize your marketing schedule and budget | Lay out a calendar and budget for the specific marketing methods you are committing to. | Previous PlanterPlan tasks walked you through brainstorming marketing methods you might use. This task helps you commit to specific methods through the lens of time and money. There are lots of free ways to get the word out. Use those and commit some of your church plant budget to a few paid media. It matters a lot less what your total budget is if you set yourself up to be your community's best-kept secret. Timing is important not only for being strategic about the window of delivery, but also for cash flow. For example, if you have a $10,000 donation coming in September, but you need to pay a bill for marketing in August, you might have a problem. By scheduling each marketing method and determining how much it costs, you can determine if the timing works within the overall budget of the church. | Download Passion for Planting's Marketing Plan Template (<a href="/resources/item/391">Google Doc</a>) and fill in the specifics for each of the marketing methods you have decided to use. Make sure the amounts you need to spend and when are already covered in your church budget. If not, work with your oversight team to approve a new budget or to approve extra-budgetary spending. Confirm that the church's projected cash flow is still healthy after adding these expenses to the budget. This action is complete when you have clear design & productions deadlines on a calendar and have confirmed that your cash flow supports the timing of your media buys. |  | 151 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 created Debugle& trouble ticket for content overwrite error --pb 2017-04-02 updated the description from backup -- dp 2017-12-15 content updated --pb 2020-12-14 changed Due in # Days from 133& to 149& --pb& & 2019-12-23 content updated --pb
317 | 584 | 614 | Publish your website | Publish and promote your website as the front door and first impression of your church. | Now that you have written all the content and worked with your designer to customize your site and build out its functionality, it's time to publish your site and announce it to the world! As soon as it goes live, make sure to update all the church's social media pages with the website address. Celebrate its launch across social media with your friends and followers. Make sure you include the website address on everything your print, publish or brand going forward. | Build out the site's menu and page structure Paste your content in to each page (paste raw, unformatted text; pasting from MS Word will ruin your site) Select stock photos, custom photos and/or videos Optimize your site for search engines Publish your site Link your church social media pages to the new site and vice versa Publish fresh, ongoing content regularly to your site (blog, pictures, etc.) This action is complete when you've published and announced your website that appeals to your target audience. |  | 227 | 183 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-11-16 content updated --pb 2019-12-09 content validated --pb 2020-12-14 changed Due in # Days from 135& to 105& & Duration from 14& to 21& --pb&
318 | 566 | 584 | Determine audience and goals of website | Create a filter to guide all of your decisions about your website's style, tone, lingo, pages names, etc... | Your website is for people who aren't already connected to your church. It's all too easy to lose focus on that as you build it. If you're not intentional, you'll slip into writing for your own people, or some other audience. And even more specifically, write intentionally for your Average Target Family (see PlanterPlan task Define Average Target Family ). The site content must flow from who the audience is. It shouldn't contain any christianese terms. The home page and main tabs should be centered around how to get there, what to expect and who the church is. The beliefs page shouldst not contain the Nicene Creed in King James English. Ruthlessly review each page and the features you've chosen through the lens of, "Does this make sense and is it helpful to people who've never been to our church?" But do consider how you'll communicated with your insiders. What other tool would work best for serving people who are already connected?: a custom mobile app a church management software with login a social media page or group If you want to build a website that truly reaches those disinterested in church, you'll have to radically move away from the norm of church websites. | Determine who your target audience is for the website. Don't settle on a pre-determined template with pages based on churchy terms, structured around a church worldview. Put yourself in the shoes of your target audience and try to identify the questions and apprehensions they might have about coming to a new church like yours. Address those issues directly. This action is complete when the website content has been carefully crafted based on the target audience. |  | 81 | 7 | 2015-02-03 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: standard 2017-11-15 content updated --pb 2019-12-09 content validated --pb 2020-12-14 changed Due in # Days from 105& to 88& --pb&
319 | 568 | 584 | Pick a website builder | Choose the app you'll use to build your website. | Websites can be built several different ways: built and coded from scratch (almost no planter should choose this option) fully custom design built using a website builder like Wordpress or SquareSpace ($$$) semi-custom design by modifying a template on Wordpress, SquareSpace, etc ($$) DIY using a website builder ($) Here's why you need to hire a designer, even if you have web design experience: the more time you spend on designing the new website, the less time you have with people. Hire a designer that can do 3 things for you: design a good looking site build in the functionality you need (online giving, calendar sync, social media buttons, etc.) help with the initial SEO (getting found by search engines - see subsequent PlanterPlan task) - a pretty site that can't be found isn't super helpful Designers are stereotypically overworked and unavailable when you need them most; find a designer with a reputation for good communication and on-time delivery. WARNING Before you ask your friend or relative to build your site for free, read <a href="https://www.churchplantingtactics.com/church-plant-website-by-buddy/">Don't Let Your Buddy Do Your Church Plant Website</a> [ChurchPlantingTactics.com]. | Ask for designer recommendations from colleagues. Review their work. Past performance is the best indicator of future results. Interview your short list of top picks. Consider the cost of their services versus their experience and talent. Enter contract with the best designer. This task is complete when you have entered contract with a web designer. |  | 88 | 14 | 2015-02-03 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: standard 2017-11-15 content update --pb 2019-12-09 content validated --pb 2020-04-15 new template download added --pb 2020-12-14 changed Due in # Days from 126& to 95& & Duration from 7 to 21& --pb&
320 | 570 | 584 | Write your website content | Do the hard work of composing content for each page of your website. | We strongly recommend writing the content outside of your website builder so you don't get sucked in and distracted by other tools and functions. But even before you begin writing, decide on your menu structure and page names. Keep your audience firmly in mind. Now start writing the actual content for the site. It should flow right out of your work on your Vision Frame and demographics (see previous PlanterPlan Milestones). Again, all of the content should be written through the lens of your target audience. Always avoid churchy language. WARNING When church plants miss website launch deadlines, our overwhelming experience is that it's because the planter hasn't written the content. It's almost never a matter of waiting on the designer to finish building the site. So set aside a realistic amount of time and discipline yourself to get it done on schedule. | Download Passion for Planting's <a href="/resources/item/393">Website Structure and Content Worksheet</a>. Draft your site map (menu and page structure). Draft content for each page. Keep it short - paragraphs should be no longer than 3 or 4 sentences. Go back and read your content through the eyes of your Average Target Family. Have at least 2 other people read it for typos and errors before it is published. This action is complete once you've written the content and has had it reviewed by at least 2 other people prior to being published. |  | 95 | 21 | 2015-02-03 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: standard 2015-11-15 content updated --pb 2019-12-09 content validated --pb 2020-12-14 changed Due in # Days from 135& to 120& & Duration from 7 to 46& --pb&
321 | 236 | 584 | Set up a church calendar | Choose which calendar software to use to compile and keep track of every important date and event for the new church. | Whether or not you'll be a program-driven church, there are things that happen in the life of your church each year. Keeping them all straight is important. Sub-calendars are key. If you will be using your church management software (the church database) for the master church calendar, you'll probably accomplish creating church sub-calendars by using different admin groups. If you use a Google calendar, simply click the drop-down arrow next to My calendars in the left-hand column and choose create new calendar for each sub-calendar. Other calendar systems typically have similar functionality. Church sub-calendars are a great way to keep everything organized at your church. Setting them up is relatively easy and it solves the following 3 problems. 1. Too Much Information The main reason for creating church sub-calendars is to 'control' who sees what. A church admin or senior leader needs to see everything, but that can be totally overwhelming for someone checking out the website. Or seeing everything could be totally inappropriate &ndash; the date & time of the next staff performance review for your worship leader isn't really everybody's business. Create sub-calendars so that every church event rolls up into one master church calendar. 2. Double-Booking Once your church is up and running, it's crazy how many times different teams will book events at the exact same time. It's tough for a guitar-playing dad to be at band practice and the youth group parent meeting at the same time. This becomes even more important for churches that have a 24/7 facility and have to manage who's using which room which night. 3. Over-Booking Maybe you think you haven't created an event-driven church. But once you overlay all the church sub-calendars above, what does that tell you about how busy you're asking people to be? Setting a reasonable pace for your leaders and your congregation is easier if you have the raw data in front of you. Possible Sub-Calendars Here is a list of sub-calendars you may want to create now or add later: Prayer Team: prayer events; reminders to send updates Fundraising: appointments; desserts or other events; reminders to send thank yous, etc Finances & Governance: annual budget preparation season; quarterly and annual Board meetings; annual report filing deadlines Discipleship/Small Groups: dates & times of small group meetings; leader training events Networking: appointments with civic leaders; reminders to follow up Community Service: events; planning meetings Marketing & Outreach: events/festivals; design & publication deadlines; online campaign run dates; etc Staffing: performance reviews; job interview dates Leadership & Training: retreats; leadership meetings; conferences Communications (Internal): newsletters; social media posts; serving schedule publication dates Preaching & Creative Team: sermon calendar; production deadlines; planning meetings Assimilation & Membership: discovery classes; membership classes; etc | Set up online calendar(s) and share with Management Team members, coach, staff and key leaders. Consider how it will interplay with your eventual church website (no one wants to enter every event twice). Add key dates to the calendar. This action is complete when you have set up the online calendar. |  | 102 | 7 | 2015-02-03 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: standard 2017-09-26 content overhauled --pb& 2020-01-24 content updated --pb 2020-12-14 changed Due in # Days from 56& to 102& & Duration from 14& to 7& --pb&
322 | 585 | 584 | Recruit a volunteer webmaster | Empower a website champion to ensure that your church website is up-to-date and functioning properly at all times. | How often have you seen things like this on a church website: in March someone goes to the website to check out your church and the home page says, "Come to our special Christmas Eve service!" What does that communicate to the potential guest? Your church website needs to be updated at least weekly, if not several times a week: post new events pull down past events post to the blog moderate blog comments post the sermon podcast or recording update software: themes, plugins, security patches, etc. etc. Content is King The added benefit of all the useful content is that your site will get ranked higher on search engine results. Which should result in more visibility and more web traffic. Your site will actually be penalized as irrelevant by search engines if it's been months since any fresh content was posted. Plus the top 3 organic results in a Google search get clicked about 20 to 1 over the ads; you want that coveted position! | Find someone who is tech-friendly and detail-oriented. Initially, it doesn't even have to be someone on the Launch Team, though that is preferable. Recruit that person to be the church's webmaster. Empower that person with access to the administrative side of the site and with contact information to all of the ministry leaders. The webmaster needs to be in the know on everything that is happening in the church. Maintain a close, healthy relationship with the webmaster through frequent communication. This action is complete when the new Webmaster has been granted administrative access to the website. |  | 105 | 21 | 2015-02-03 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: standard 2017-11-14 content seriously overhauled --pb 2019-12-09 content updated & links verified --pb 2020-12-14 changed Due in # Days from 126& to 120& --pb& 2024-02-16 added link, removed old link --pb
323 | 1407 | 584 | Shoot a welcome video for website | Create a video for your website aimed at welcoming people who are checking out the church online. | [content pending] |  |  | 102 | 21 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template:
324 | 1408 | 584 | Set up website privacy policy and cookie disclosure | Honor your website visitors and the law by creating proper disclosures about data collection, privacy and use of cookies. | [content pending] |  |  | 120 | 7 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template:
325 | 1409 | 584 | Set up website analytics | Get information that will help you refine and improve your website. | Website analytics reveal all kinds of things about your website: how many users visited your site how many pages they viewed which pages were most popular which city they're in which search phrase they used to find your site which website they clicked through to yours from etc. Armed with this information, you can improve your site so that it performs better. Google Analytics is the gold standard and provides the most insight. DIY website builders like SquareSpace, Wix & Weebly have a simplified version built in to their platform, but may also allow you to install Google Analytics. | Determine if your website platform has analytics built in. Whether it does or not, consider installing Google Analytics for the richest insight. Consider creating an automated weekly or monthly report to stay informed. This action is complete when you can see website analytics data collected from users of your site. |  | 120 | 7 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template:
326 | 586 | 584 | Optimize church website to get found by search engines | Commission a trusted volunteer to get the church website to show up on the first page of online search results. | When somebody is searching online, if your church doesn't show up on the first page of search results, you don't exist. Search Engine Optimization (SEO) is the half-art, half-science of getting on the first page. Google is the leader in this space, but it's an ever-changing beast. About the time you figure some stuff out, <a href="https://blog.hubspot.com/marketing/google-algorithm-visual-history-infographic">Google changes their algorithm</a> and previous tactics have diminishing returns. By and large, SEO tactics don't cost you anything but time. But it requires ongoing vigilance and content creation, which a lead pastor doesn't have time for. Find someone on your team or within your network of supporters that can learn about SEO, make the necessary changes, and keep stuff up-to-date. A great starting place is to have them search online for <a href="https://www.google.com/search?q=church+website+SEO"> Church Website SEO </a>. Set search results to show only articles from the last 12 months and read up on the latest and greatest. Here's a summary from articles we found in 2017 (effectiveness of these tactics subject to change without notice): Pick a responsive design (the site resizes to any screen size, especially mobile) Create useful content and publish new content regularly Compress media (don't use 10MB image files!) Host videos on Youtube and embed them in your site Include keyword phrases (reverse engineer what phrase people will search on where you want to show up on page 1) Include metadata on every page Put your church name, address & phone number on every page Embed a Google map on your contact page Submit your website to search engines (let them know you exist!) Create church pages on the major social media sites & try to get the same username across platforms Claim your local listings (see subsequent PlanterPlan task) Get launch team members to submit non-fluff reviews on those listings and on social media sites Use tools to analyze your progress and show you where to nip & tuck (read <a href="https://blog.hubspot.com/marketing/seo-analysis-tools">14 of the Best SEO Tools for Auditing & Monitoring Your Website in 2019</a>) | Recruit someone you trust to champion getting your church website onto the first page of search results. Have them read several recently-published articles on church website SEO. Empower them with access to your website builder tool and the church's social media pages. This action is complete once your champion has been empowered to make the necessary changes. | For further explanation, read the source articles: <a href="https://churchtechtoday.com/5-tips-improving-churches-seo-ranking/">5 Tips for Improving your Church's SEO Ranking</a> <a href="https://reachrightstudios.com/8-church-seo-best-practices-get-church-found-search/">8 Church SEO Best Practices to Get Your Church Found in Search</a> <a href="https://get.tithe.ly/blog/seo-basics-7-keys-to-optimizing-your-churchs-website">Church SEO: 6 Keys to Reach More People with Your Website</a> <a href="https://www.sharefaith.com/blog/2017/09/10-church-website-seo-friendly-tips/">10 Tips to Make Your Church Website SEO Friendly</a> <a href="https://www.semrush.com/blog/seo-myths/" rel="noopener">12 of the Biggest SEO Myths: Explained & Debunked</a> Also consider: <a href="https://offers.hubspot.com/seo-starter-pack">The Complete SEO Starter Pack</a> [Hubspot.com] | 120 | 14 | 2015-02-03 05:00 | 2024-02-16 15:34 | 2000-01-01 05:00 | template: standard 2017-11-16 content & hyperlinks overhauled --pb 2019-12-09 content updated & links validated --pb 2020-12-14 changed Due in # Days from 142& to 166& & Duration from 7 to 14& --pb&
327 | 594 | 614 | Kick off Facebook campaign | Create an integrated, ongoing approach to interacting with individuals and your community through Facebook. | Facebook is the world's most popular social media app. And as you've experienced, it changes all the time. But first and foremost, it's meant to be about people interacting. "Facebook is no longer just a stage for making announcements. It's your coffee table for building relationships." - <a href="https://churchm.ag/new-facebook-news-feed-will-affect-church-pages/">ChurchMag</a> Facebook Building Blocks You'll need each of the following: Your own personal account (do NOT create a profile with first name "[Name of]" and last name "Church"!) A church Page At least one Group related to your church Page You will log is as yourself, then create the Page and Group(s) which will set you as an admin for each of them. You can add other people on your team as admins to the Page and Group(s) as appropriate. The 2018 Newsfeedpocalypse Facebook is a marketing company masquerading as a social media platform. They make their billions from advertisers paying to put their ads and boosted content in your newsfeed. Several years prior, Facebook already intentionally reduced the amount of posts/content from businesses in people's newsfeeds. So they could increase ad revenue. But so many people complained about the number of ads and boosted posts in their newsfeeds that Facebook reduced that even further at the beginning of 2018. Basically, even if a user has 'liked' and even then 'followed' your church Page, nothing you post to your church Page will show up organically in their newsfeed. It is pay to play. Content is Still King But you still need to have a church Page because that's where people will check you out before their first visit. Your best bet is to post videos, 'go live' and start conversations. Engaging content that goes viral is your best bet for showing up organically in your fans' newsfeeds. Bullhorn-style announcements are dead. Create a rhythm for regularly posting content. Your church should be posting several times a week - but you can create the posts in batches and schedule them to publish throughout the week. | Find your favorite churches' and nonprofits' Pages and learn from what they've done well. Create a Facebook Page for your church. Create at least one Group to complement your Page. Recruit an outside support or Launch Team member to manage and post content to both. This action is complete when a Facebook Page and Group have been created for the church and a first post is made. | <a href="https://churchmarketinguniversity.com/facebook-thrive-guide-churches/">Facebook Thrive Guide for Churches</a> - churchmarketinguniversity.com <a href="https://churchtechtoday.com/facebook-changes-mean-meaningful-interactions-church-communities/">Facebook Changes could Mean More Meaningful Interactions for Church Communities</a> - churchtechtoday.com <a href="https://www.churchplantingtactics.com/church-page-vs-church-group/">Church Page vs Church Group on Facebook</a> on churchplantingtactics.com <a href="https://www.churchplantingtactics.com/create-church-facebook-page-content/">Easy Ideas to Create Church Facebook Page Content</a> on churchplantingtactics.com | 227 | 183 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-12-15 content updated --pb 2020-12-16 changed Due in # Days from 133& to 149& & Duration from 22& to 35& --pb&
328 | 1410 | 594 | Set up Facebook Pixel tracking code | Install the Facebook Pixel code on your website to maximize your social media opportunities. | Facebook Pixel is an analytics tool that associates your website visitors with their Facebook account. It tracks when they visited your website, which pages, etc. Facebook won't tell you exactly who those users are, but when you later place a Facebook ad, you can create custom ads for people that have already visited your church website. | Create a Business Manager account on Facebook. Add to that a Facebook Ad Account. Create your Facebook Pixel. Install the Pixel code on your website (find help below). This action is complete when you have fully installed the Pixel tracking code on your website. | <a href="https://get.tithe.ly/blog/facebook-ads-for-churches">Facebook Ads for Churches: A Step-by-Step Guide</a> by tithe.ly <a href="https://prochurchtools.com/pcp171/">Facebook Ads Tips for Churches from the Trenches</a> podcast by prochurchtools.com <a href="https://worshiptimes.org/how-to-use-your-churchs-facebook-like-a-pro/">How to Use Your Church's Facebook Like a Pro</a> by worshiptimes.org | 116 | 7 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template:
329 | 1411 | 594 | Initiate first boosted post | Create a social media post and pay to boost it to a custom audience you'll specify. | [content pending] |  |  | 120 | 29 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template:
330 | 1412 | 594 | Initiate first paid social media ad | Create an ad campaign on Facebook or other app to reach users in your area. | Your organic content on social media isn't being seen by very many. Pay to Play There was a time when Facebook users would see your church's content in their feeds. Now, even if they've liked your page and followed it, chances are very small they'll see anything that you post on the church's page. It has become a pay-to-play environment. Other platforms are following suit. Since you already installed the Facebook Pixel tracking code on your website (see previous PlanterPlan task), you can now use retargeting ads that will be specific to users that have already visited your church website. | This action is complete when you have published your first paid social media ad. |  | 181 | 29 | 2021-01-15 05:00 | 2021-01-26 05:00
331 | 587 | 614 | Get listed on Google, Yelp and Apple Maps | Make your church easy to find online by getting listed on various directory sites. | As a brand new church with no previous digital footprint, search engines will need a little help finding you before they'll serve your website and information up for people to find. One of the best ways to do that is get listed on the sites where people already go to look for things. Getting your church listed on these directories should be a non-negotiable: <a href="https://www.google.com/business/">Google My Business</a> (for Google Maps) <a href="https://www.bingplaces.com">Bing Places</a> <a href="https://businessconnect.apple.com/">Apple Maps</a> <a href="https://business.yelp.com/">Yelp</a> If you have a capable volunteer, you may want to get listed on these directories as well: <a href="https://www.churchfinder.com/church-staff/register">ChurchFinder</a> <a href="https://www.churchangel.com/members/">Church Angel</a> <a href="https://marketing.yellowpages.com/en/claim-your-listing?from=advertise-with-us-YP">Yellowpages</a> <a href="https://www.whitepages.com/">Whitepages</a> <a href="https://www.yellowbook.com/">Yellowbook</a> <a href="https://advertise.local.com/">local.com</a> <a href="https://www.citysearch.com/aboutcitysearch/advertise_with_us">City Search</a> [not free] Postcard Validation At least Google Maps and Bing Places will mail a postcard to the address you provided as an anti-fraud measure. For most church plants, that means the postcard is being addressed to the church but being mailed to the theater or school where you'll hold worship gatherings. So wait until you're on good terms with your facility's management and give them a heads up that the postcard is coming. KEEP GOOD RECORDS Make a list of every site where you added the church and any logins that were created to post those listings. If you ever change your worship gathering location, phone number, web address, etc. you'll need to go back and update each one of your listings. Otherwise, the old information will linger and haunt you for years. | Place free listings on the bare minimum 4 directories above. Make sure they are set up in such a way that the church is notified of anyone online reviews or comments. Consider finding a volunteer to place listings on other directories as well. Keep records of every site and every login created. This action is complete when the church has been listed on at least the 4 non-negotiable online directories. |  | 166 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-11-17 content updated --pb 2018-01-26 additional resource added --pb 2020-06-15 additional resource added --pb 2020-12-14 changed Due in # Days from 105& to 142& --pb&
332 | 617 | 614 | Jumpstart online ratings and reviews | Raise the church's website ranking by getting 50 reviews on each of a few important websites. | The democracy of the internet is significant in getting your website found. Search engines aren't just looking for your website content; they're trying to corroborate its credibility by looking for: social media references other websites that have linked to the church site map listings online ratings and reviews Another PlanterPlan task walks you through getting the church listed on several prominent directory-type websites. One of the first, best things you can do is to get your team to write positive but honest reviews on: Google Business (Google maps) your church's Facebook page Yelp! Initially, you need at least 6 positive reviews on each of these directories; but probably not the same exact six reviews just copied & pasted. On an ongoing basis, you'll need about 10:1 positive reviews to negative reviews. Consider posting a grace- and love-filled response to each negative review to demonstrate that the church is listening and that it cares. Disappearing Reviews Especially on Yelp!, if your team member creates a new account to leave the review and then doesn't use Yelp! any further, the review will likely be pulled down as fraudulent. So if your team member is creating a new online account to leave a review, coach them to leave other reviews for their favorite restaurants, shops, etc, to establish credibility as a reviewer. Press Releases In your local context, if your city, town or community has an online newspaper or community blog that is widely read, also consider submitting a press release to announce an outreach event or the grand opening. For an example, read <a href="https://www.fredericknewspost.com/news/lifestyle/religion/church-for-the-rest-of-us-collective-church-brings-alternative/article_c45fc11c-f62f-5477-bb60-5a6b00017dfa.html">this online article</a> that stemmed from a press release. A Case Study An established church finally got around to doing this only to find that on Yelp! there was already one review of the church. It had been posted 2 years prior and was extremely negative of the church. How many people decided not to visit that church because of that negative review? They will never know. | Confirm that your directory listings are live and accurate. Invite team members to leave reviews and ratings on the sites above; avoid having the exact same reviews by the same people on every site. Confirm that the church is getting notifications when each of the reviews are posted. This action is complete when at least 6 positive reviews have been posted on each of the sites above. | <a href="https://churchmarketinguniversity.com/church-google-review-link-generator/">Google Reviews Link Generator</a> on churchmarketinguniversity.com | 196 | 30 | 2015-02-03 05:00 | 2021-01-15 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2017-12-15 content updated --pb 2018-02-09 vendor subsection added --pb 2020-12-14 changed Due in # Days from 215& to 227& --pb& 2019-08-30 Truth Advertising replaced with MailWorks --pb 2018-03-16 additional resources subsection added --pb & 2020-01-24 content updated --pb
333 | 628 | 614 | Set up online re-marketing ads | Reach people in your community through targeted online ads. | Types of Online Ads There are two basic types of online ads regardless of which site you post them on: cost-per-thousand viewable impressions (CPM or vCPM) and pay-per-click (PPC) With CPM, you set a price you're willing to pay for each 1,000 views of your ad. This is an effective strategy to increase your brand awareness. With PPC, you do not pay unless someone clicks on your ad. This is a better strategy if you want to drive people to your church website Pricing Online ads are priced through a bidding system: you compete against other advertisers for your ads to show up to a specific audience. First, you'll define and refine your audience based on geography and even demographic information. Then within that audience you'll place your bids on specific keyword phrases. To figure out which keywords to bid on, ask yourself, "What will people be googling when we want our ads to appear?" or, "What keywords on their profile should trigger our ad?" There's an art to picking keyword phrases and you may have to experiment a little. Lastly, you'll set a budget for your entire campaign and/or a daily budget, then a max price per click or impression. If you bid higher than your competitors, your ads will appear for your audience. If you spend through your daily budget, your ads will stop appearing for that day. $10,000 per Month in Free Ads Once you get your church's 501c3 Determination Letter back from the IRS, you may be eligible for <a href="https://www.google.com/nonprofits/">Google for Nonprofits</a>. Among other things, they offer nonprofits $10,000 per month in free ads. For real! Messaging Your first instinct may be to promote the grand opening of your worship gatherings. While this is helpful, chances are good that these ads will reach already-churched people looking for a church. Consider placing ads around community needs. For example, if you are doing a <a href="https://www.ramseysolutions.com/ramseyplus/organization">Financial Peace Seminar</a>, place ads that target an audience searching online about debt, financial advisors, credit cards, foreclosure, etc. You could also place ads around felt-need sermon series such as parenting, marriage or sexuality. These types of ads are more likely to reach a non-churched audience. Advertising Sites Top advertising sites include: <a href="https://adwords.google.com/home/#?modal_active=none">Google Adwords</a> <a href="https://www.facebook.com/business/ads">Facebook Ads</a> (different than boosting a post, which is also a great idea) <a href="https://business.instagram.com/advertising">Instagram Ads</a> <a href="https://business.twitter.com/en/advertising.html">Twitter Ads</a> Track and Refine When you place online ads, be sure that you are tracking their effectiveness. You'll be provided analytics/metrics so that you can measure the results from your ads. Without measuring your effectiveness, you could be throwing money away without even knowing. Consider placing multiple ads, so that you can determine which ones are most effective. | Set your online ad budget. Determine which sites to place ads on. Design and write the ads. Publish the ads. Develop a plan for evaluating the effectiveness of the ads. This action is complete when you have placed targeted online ads. |  | 212 | 14 | 2015-02-03 05:00 | 2021-01-15 05:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content updated --pb 2018-11-19 content updated, title changed from "Develop a Discipleship Strategy"& --pb 2019-11-26 content updated --pb 2020-12-16 changed Due in # Days from 147& to 67& & Duration from 44& to 21& --pb&
334 | 627 | 614 | Conduct your mass marketing campaign | Plan and execute your mass marketing method(s) as broad 'air support' for your ground campaign. | One of your methods for getting the word out needs to be a mass marketing medium that blankets the community. Physical media that get to every door is still a powerful way invite people to the launch of your worship gatherings. Mass marketing is generally more expensive but requires no/low time investment from your team. It's critical to establish name recognition in the community prior to spending the money on a mass marketing campaign. If the first time they've heard of your church is reading the marketing piece, chances are high that it's going right in the trash. But if they get it and say to themselves, "Oh yeah, this is that church I ran into at the ______," it can be a very effective deal closer. Direct Mail Strongly consider conducting a direct mail campaign prior to the launch of worship gatherings. For many, it's one of the most expensive things they do during pre-launch. And many planters will tell you that it's one of the most effective things they did to invite people to the grand opening. Hire a company that specializes in church direct mail. They'll walk you through the entire process and make sure everything gets done on time for the least possible cost. And you'll be able to sleep at night. Here are some companies that have served our planters in the past: <a href="https://outreach.com/p4p">Outreach Marketing</a> --> <a href="https://www.d2design.com/">D2Design</a> <a href="https://mailworksii.com">MailWorks II</a> Door Hangers Depending on your context, door hangers put on every door may get you as high or higher a return on investment. Work with your graphic designer to design the door hangers and have them printed yourself at shops like: <a href="https://www.gotprint.com/products/door-hangers/order.html?fid=2682165">gotprint.com</a> <a href="https://www.printdirtcheap.com/en/door-hangers/categories/">printdirtcheap.com</a> THE TRAP in using door hangers is wanting to save money by using your Launch Team to put them out. Don't. You'll keep them so busy with door hangers that they will neglect outreach & inviting. So your two viable options are: recruit a missions team or youth group from a supporting church hire out the delivery from reputable vendors like <a href="https://www.gotdelivered.com">gotdelivered.com</a> | Commit to establish broad name recognition in the community through a "6 to stick" approach prior to spending significant money on a mass marketing campaign. Contract with vendor(s). Make sure you understand important deadlines and add them to a calendar with reminders. This action is complete when you have finalized the mass marketing campaign with the vendor. | <a href="https://truthadvertising.org/church-marketing-tips-what-kind-or-response-should-you-expect-from-your-direct-mail-postcard/">What Kind of Response Should You Expect from Your Direct Mail Postcard?</a> by truthadvertising.org --> <a href="https://www.churchplantingtactics.com/increase-your-response-rates-with-these-church-plant-postcard-design-secrets/">Increase Your Response Rates with These Church Plant Postcard Design Secrets</a> on churchplantingtactics.com <a href="https://www.churchplantingtactics.com/church-plant-postal-permits/">How Much Money CAN Church Plant Postal Permits Save You?</a> on churchplantingtactics.com <a href="https://www.churchplantingtactics.com/organize-a-church-plant-door-hanger-campaign/">How to Organize a Church Plant Door Hanger Campaign</a> on churchplantingtactics.com | 227 | 60 | 2015-02-03 05:00 | 2021-04-15 04:00 | 2000-01-01 05:00 | template: standard 2017-12-22 content overhauled --pb& 2020-01-24 content & links& validated --pb 2020-12-14 changed Due in # Days from 215 to 212& & Duration from 21& to 14& --pb&
335 | 1413 | 0 | PHASE V - WORSHIP GATHERINGS | [6 empty] | 2021-01-15 05:00 | 2021-01-15 05:00
336 | 704 | 1413 | Milestone: Select a Worship Gathering Facility | This milestone helps you choose the best facility for your worship gatherings. | Choosing the right facility for the church plant is no small feat. Ron Sylvia put it best: "We shape our buildings, and then our buildings shape us." This milestone will help the planter to think through the many aspects of selecting a facility and guide the planter in evaluating each available facility in order to choose the best fit. | --no steps-- |  | 93 | 62 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2019-12-17 content updated --pb 2020-12-14 changed Due in # Days from 37& to 32& & Duration from 7 to 1& --pb&
337 | 1414 | 704 | Sign the facility contract | Get the worship facility rental/lease agreement in writing signed by both parties. | Always get the contract in writing and signed. Always. Planters that go into a facility on a handshake regret it. The contract reduces chances for unmet expectations. And it protects you by clearly stating the terms. Ensure that anything discussed verbally is written into the contract such as: The rental price of the facility What time the church can enter the facility and what time the church must be out of the facility Specific dates the contract covers Storage requirements Food and drink policies Show the contract to others before you sign it: a friend in real estate, your coach, your Management Team, etc. | Have a draft contract reviewed by friends & colleagues with experience. Sign the contract and make sure to get a copy with their signature on it, too. File the fully signed contract with your important church legal paperwork. This action is complete when you have filed the fully executed/signed contract for a rental facility. | <a href="https://www.churchplantingtactics.com/5-church-plant-facility-lease-surprises-avoid/">5 Church Plant Facility Lease Surprises to Avoid</a> by churchplantingtactics.com <a href="How to Review a Worship Facility Lease (with FREE Worship Facility Lease Checklist)">How to Review a Worship Facility Lease (with FREE Worship Facility Lease Checklist)</a> by churchplantingtactics.com | 151 | 30 | 2021-01-15 05:00 | 2023-11-21 21:07 | 2000-01-01 05:00 | template: mirror content to Task ID #727
338 | 728 | 704 | Calculate how many services the facility dictates | Decide now whether you'll start with one, two, or more weekly services based on what the facility allows. | Deciding on how many services to start with isn't just a matter of personal preference. The factors that influence your decision include: Cost - If you are renting by the hour, two gatherings will cost more than one. Can you afford the extra cost? Time Constraints - Are there any limitations on service times (ex: when renting a movie theater, you may have to be out by 12pm)? Volunteer Staffing - Consider the impact on volunteers (children's ministry in particular) and your ability to recruit enough volunteers for two weekly gatherings. On the flip side, if you have only one gathering, your children's volunteers will be unable to participate in the worship gatherings with their families on weeks they serve. Attendance - The number of people you expect to reach on opening day and the expected attendance 3 months after opening day. Critical Mass - Don't let your seating be less than 50% full to avoid the where-is-everyone effect Facility size - How many people can the auditorium seat? How large is the parking lot? The children's area? Can one gathering handle the expected attendance? If you go with two gatherings, will there be critical mass in each? | Based on the facility, consider how many weekly worship gatherings are possible. Pray about gathering times and the impact that one or two gatherings may have on your launch team and volunteers. Pray about how your gathering time(s) will impact newcomers' ability to attend the gathering. Decide on how many weekly gatherings you will conduct and at what time they will be held. This action is complete when you have finalized the number of weekly worship gatherings and their start times. | <a href="https://www.executivepastoronline.com/virtual-capacity/">Virtual Capacity: Understanding The Effect Seating Capacity Has On Momentum</a> on executivepastoronline.com | 135 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2019-12-20 content updated --pb 2020-12-14 changed Due in # Days from 121& to 143& --pb&
339 | 730 | 704 | Purchase a church insurance policy | Bind a general liability insurance policy that protects the church and staff from unnecessary risk. | There are several types of insurance that you have to consider as a new church: General liability (aka multi-peril) Umbrella liability Worker's compensation Auto/vehicle Passion for Planting strongly recommends adding these common riders: Inland Marine (covers trailer contents in storage & transit) Sexual misconduct Directors & Officers (covers your Management Team/Board of Directors) Hiring Practices (covers lawsuits from disgruntled employees) Professional/Ministerial Counseling (covers lawsuits from people who don't like the pastor's advice) Get at least two quotes from different insurance companies. Start first with insurance carriers that specialize in churches. Timing You will be required to have a policy in place when you sign the facility contract, but you may want it sooner. You can get insurance as soon as you incorporate. That covers you from lawsuits that could happen even before you start worship gatherings. Specifically, it covers your Management Team and your own activities. Getting it that early can be trickier, since the primary policy will be based on a brick & mortar location. Often they'll let you start with the planter's residence as the 'church facility' until the worship gathering facility is identified. You decide which company to use and how much coverage to purchase, except that your landlord may have minimum requirements. The insurance policy may need to be updated several times prior to launch: when a facility contract is signed after equipment is purchased if a church trailer or vehicle is purchased when an office is rented To get a quote, be prepared to provide the insurance company with at least the following information about the facility: address of the facility the square footage of the area being used by the church the construction type of the building (e.g., masonry or wood) the age of the building whether the facility requires any specific coverages Portable Churches For church plants that are portable, covering the equipment will require an inland marine policy. This rider will cover the equipment while it is being used, stored and in transit. In some cases, the main policy itself will not cover the equipment when it is being transported. Also be sure to have an auto policy if the church purchases anything with a VIN & license plate: trailer, pickup, box truck, etc. Check with the insurance provider about whether they cover a volunteer's vehicle being used to haul the equipment. National Carriers Although using a local insurance agent provides networking and evangelistic opportunities, often local agents are unable to provide the type of insurance a church plant needs. You may find the following companies helpful. These national carriers provide additional benefits such as reduced rates for background checks. <a href="https://www.churchmutual.com/">Church Mutual</a> <a href="https://www.guideone.com/">Guide One</a> <a href="https://www.brotherhoodmutual.com/">Brotherhood Mutual</a> | Provide necessary information about the chosen facility. Get quotes from insurance companies. Choose and bind an insurance policy. This action is complete when you have bound applicable insurance policies for the church. | <a href="/resources/item/131">Church Insurance Basics</a> in the PlanterPlan library <a href="/resources/item/314">Risk Management And Insurance Coverage For The Newly Planted Church</a> from National Church Group Insurance Agency | 151 | 30 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-23 updated content --pb& 2019-12-20 content updated --pb 2020-12-14 changed Due in # Days from 133& to 150 & Duration from 7 to 15& --pb&
340 | 731 | 704 | Develop a facility layout map | Determine how you're going to use your facility for worship gatherings, from layout to setup to traffic flow. | After you finalize the facility contract, develop a plan for how the church will use the space. The vision may be clear in the your mind, but the workers that will be doing all the set up need more concrete details than that. Develop a detailed 'to scale' map showing the auditorium and children's areas as well as the interconnecting hallways. Note the location of all lobby tables (e.g., welcome table, information table, hospitality table) as well as the utilization of the stage, where the soundboard will go, etc. The objective of the map is to determine the most guest-friendly layout and flow as possible. Often you can get a map of the facility simply by asking. Schools or hotels may say they do not have maps available, but if you ask for a fire evacuation map they will be happy to provide one. Use that map as the base or background for you space utilization plan. | Get or create a scale drawing of the facility Tour the facility with a specific eye for: Location/number of electrical outlets Distance from parking lots to entry doors Location and distance to restrooms Location and distance to children's ministry (will parents feel safe leaving their kids? Is the location naturally 'safe?') Distance from projector to screen Which seats will be used in the auditorium Natural traffic flow through the facility including exits and restrooms Where to place the signs and tables Determine which entrance and which rooms will be used. Mark on the map where all of your equipment will go. This action is complete when you have a completed facility layout map. |  | 151 | 15 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-23 content updated --pb 2019-04-26 image added --pb 2019-07-15 image update & another added --pb 2020-12-16 changed Due in # Days from 182& to 172 --pb& 2020-01-13 replaced broken& gdurl& link to image; content updated --pb
341 | 736 | 1413 | Milestone: Initiate Ministry Teams | Create team structures and systems and begin identifying leaders and members for each team. | Team-based ministry is essential to a healthy and growing church. Initially you'll be able to carry out most of the processes needed to start the church. However, as the church grows, these processes will also grow. If you don't develop teams, your capacity will be the cap to church growth. It is easiest to develop a team-based strategy from the beginning rather than to shift later by necessity. Team-based ministry also clearly supports the biblical image of the Church as the Body of Christ, in which all members of the Body serve a role. Your job becomes one of equipping and training people to do ministry. This milestone walks you through building a teams structure, developing systems & processes to support those teams, and recruiting workers & leaders to each team. | Watch the Passion for Planting training video "<a href="/resources/item/257">Initiate Ministry Teams</a>" featuring Ed Stetzer. |  | 260 | 200 | 2000-01-01 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated, audience changed to coach --pb 2018-04-20 updated content, changed audience to planter --pb 2020-01-13 content validated --pb 2020-12-14 changed Due in # Days from 95& to 128 --pb&
342 | 737 | 736 | Call your coach about building a Leadership Matrix | Open a conversation with your coach about deciding which ministry teams to form and what the volunteer org chart will look like. | Each ministry and ministry team needs a leader. The leadership matrix is a simple tool that helps you see each volunteer and leadership position that needs to be filled for opening day. Sample issues to process with your coach: Keeping team structure simple Staff vs. volunteer leadership Staffing for growth Apprenticing How to utilize coaches | This action is complete when you have called your coach about building a leadership matrix. |  | 128 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2018-03-29 content overhauled --pb 2018-04-02 additional resources subsection added -pb 2018-07-25 Logan quote added --pb 2020-01-14 content validated --pb 2018-10-12 pushed due in # days out from 102 and duration from 7 --pb 2019-08-28 added James Clear quote --pb 2020-01-13 replaced broken& gdurl& link to image --pb 2020-12-14 changed Due in # Days from 224& to 228& --pb&
343 | 739 | 736 | Draft a list of desired ministry teams | Develop the list of ministry teams you'll need at the launch or worship gatherings to support the unique vision of the church. | Which ministry teams will you need to put together to pull off weekly worship gatherings? Now is the time to challenge past ministry team org charts, especially if you're coming from a ministry context that either didn't really use teams, or one that had dozens of ministry teams. What worked there may very well not work in this new church. Contextualize even the kinds of teams, what you call them, and what their responsibilities will be. The trick in starting from scratch is that the same kinds of jobs need to get done. It would be easy to let some important worship gathering functions fall through the cracks as you reinvent the wheel. To help you, Passion for Planting has created an exercise that will challenge you to group over 40 essential responsibilities and assign them to the ministry teams you'll use. Download the Ministry Team Responsibilities Template (<a href="/resources/item/174">MS Word</a> or <a href="/resources/item/372">Google Doc</a>) and get to work! You will use the resulting list to create the Leadership Matrix in the next PlanterPlan action | Review your Vision Frame , especially the Strategies you identified. Review your previously created Opening Day Expectations document. Download Passion for Planting's Ministry Team Responsibilities Template (<a href="/resources/item/174">MS Word</a> or <a href="/resources/item/372">Google Doc</a>). Rearrange the teams and responsibilities to match your stated strategies. Rename the teams and team roles to fit your unique context. This action is complete when you have drafted the list of initial ministry teams. |  | 135 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2018-06-01& gdoc& template added --pb& 2020-01-13 content updated --pb 2020-12-14 changed Due in # Days from 102& to 142& --pb&
344 | 740 | 736 | Craft a Leadership Matrix for Opening Day | Determine how many leaders and volunteers are needed to build out your ministry teams. | You need a big-picture view of all the church's ministry teams. You need to know who leads each team and what the teams are in charge of every week. Where do you go to see all of that in one place? Enter the Leadership Matrix, a chart/spreadsheet that helps you build all of that out. As you begin forming the people of the Launch Team into ministry teams, you'll use the Leadership Matrix to help place everyone based on their passions, gifts and abilities. And as you develop leaders, you can do the same for them. Work with your leaders to fully flesh out the serving roles on their teams. Once the roles are identified, work out how big of a bench or bullpen you'll need for each team to be fully staffed and allow for rotation. If everyone serves every week, burnout is not far behind. If you need 2 people to serve in a particular role every week, you need a bench of 3 to 5 people. Your Leadership Matrix contains the building blocks that you'll need to set up your volunteer scheduling software. | Review your previously created Ministry Team Responsibilities worksheet for the list of ministry teams. Download Passion for Planting's Leadership Matrix Template (<a href="/resources/item/156">MS Excel</a> or <a href="/resources/item/370">Google Sheet</a>) and follow the included instructions. Reference the <a href="/resources/item/159">Sample Leadership Matrix</a> for insight and inspiration. Send the completed Leadership Matrix to your coach for feedback. This action is complete when you have customized and completed the leadership and team structure of a Leadership Matrix. The specific workers and leaders will be recruited later. |  | 142 | 7 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-05 content validated --pb& 2020-01-14 content updated --pb 2020-12-14 changed Due in # Days from 109& to 149& --pb&
345 | 741 | 736 | Coaching Checkpoint: review and affirm Leadership Matrix | Review the planter's leadership matrix and provide feedback for how to better structure ministry teams. | The leadership matrix is a key tool to have in place for ensuring a healthy start of regular worship gatherings. The matrix is basically a spreadsheet with a list of ministry teams and each position needed to make the ministry team function. Initially the planter will have lots of holes to fill in this matrix. As the launch team grows and develops, the planter will begin plugging more people into these leadership roles. At that point, the leadership matrix becomes a coaching tool. Periodically, request the most updated matrix to ensure that the planter is continuing to plug people into leadership roles. As launch approaches, the leadership matrix serves as a tool to determine what outside help will be needed. At this point, ensure that every ministry team needed to accomplish the vision for Opening Day of worship gatherings is represented on the matrix. Also ensure the teams are structured for reproduction. In other words, each leader should have an apprentice leader (subordinate) and coach (superior). Finally, look through the matrix and determine if any ministry roles are missing that need to be added to the matrix. | Read over the leadership matrix provided by the planter. Affirm that all ministry teams needed to carry out the vision for Opening Day of worship gatherings are represented. Affirm that each ministry team is structured for reproduction. Affirm that each ministry role needed to make that team successful is listed. Determine how often to review the leadership matrix with the planter. Create a prompt in your calendar or to-do program as a reminder. This action is complete when you, the coach, have reviewed and affirmed the planter's Leadership Matrix. |  | 149 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-05 content validated --pb& 2020-01-14 content updated --pb 2020-12-14 changed Due in # Days from 224& to 228& --pb&
346 | 742 | 736 | Assign leader to each ministry team | Recruit a team leader for each ministry team to make sure teams are healthy and ready to execute. | Assign a team leader for each ministry team you put on your Leadership Matrix. Set expectations for team leaders in writing and communicate those to each leader. Use the Leadership Matrix spreadsheet, church management software or volunteer scheduling software to track who is leading which team(s). | Identify a person to lead each team. Get a commitment from each leader to own the processes in that team. Enter each leader's name in the Leadership Matrix or appropriate software. This action is complete when you have assigned team leaders to each ministry and ministry team. |  | 228 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-03-31 updated from 'plan' to 'strategy' --pb 2017-06-05 validated content & updated resource link --pb& 2020-01-14 content updated --pb 2020-12-14 changed Due in # Days from 231& to 204 & Duration from 21& to 38& --pb&
347 | 738 | 736 | Get your teams to write down their processes | Empower your teams and volunteer leaders to create healthy systems by writing down the processes they're in charge of. | At some level, you already know processes are important, even if only intuitively. How do you react when someone tells you, "That's the way we've always done it!"? "Use reproducible processes. What is obvious to you is quite likely not obvious to others. You may be able to lead a small group just by winging it and doing what comes naturally. However, if you look more carefully at what you have done, you may discover you are following a subconscious template of some kind. You just "know" to start with something relational, and then to move deeper. You just "know" when to encourage a quieter member of the group to speak. Examine your practices and discern the underlying principles. Then script out the principles and actions so you have a template for training others. Intuition is impossible to pass on to others; reproducible templates are easy to pass on to others. Learn how to translate the first into the second. Whatever you do, do it in a way that allows others to imitate it." Bob Logan on the <a href="https://sparks.fuller.edu/global-reflections/2018/04/11/essentials-for-church-planters-who-want-to-start-well/">Fuller Theological Seminary blog</a> In the same way that the human body is made up of systems (skeletal, muscular, etc), churches are made up of systems. Church systems are the groupings of like processes that work together for a common purpose. Every church has systems and processes for everything that gets done. Some systems are intentional and healthy, and some are ineffective and broken. But they're there. "You do not rise to the level of your goals. You fall to the level of your systems." James Clear, Atomic Habits Consider the following 4 possible scenarios at any church: Note that good systems are what move people from unskilled to skilled. Every thing that gets done at a church is part of some process. Most churches have over 100 different processes functioning all at once. At first you might be able to survive without formal processes. Before too long, though, a lack of healthy processes will stunt your growth. And it's easier to establish healthy processes before the launch of worship gatherings than to try and change established things later. You will want intentional, solid processes for everything eventually. But for legal, compliance and accountability reasons, you'll need tight processes right away for at least: Staff hiring Background checks for staff & children's workers Children's ministry check-in and check-out Offering counting and cash handling Reimbursements and other accounting processes It is also important early in the life of the church to establish reliable processes for: Groups Reproducing leaders Guest follow-up Communications to your team Marketing to your community, especially social media & web Worship gathering planning Commission and empower your teams to write down the various processes that they own. As you work with them, consider: Every process needs an owner, and teams are best suited to own processes Processes start with expectations/outcomes - describe what the process is designed to accomplish but allow them to find their own path to that outcome It's important to write each process down - it will force the owner to understand it That document becomes a training tool and reference manual for new volunteers Allow volunteers who use the process, especially new volunteers, to give raw, honest feedback on how the process could be improved The tyranny of the urgent will drive you to work harder. But things at the church won't improve until you take a step back to figure out how to work smarter. That looks like improving your systems and investing in people. | Describe to each team the importance of systems and processes. Identify the most important processes to start documenting. Communicate the goal or desired outcome of each process. Set due date expectations for having written processes in place. This action is complete when you have delegated the writing down of processes to your teams. | <a href="https://www.executivepastoronline.com/the-management-system/">The Management System</a> on executivepastoronline.com | 228 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-03-17 updated hyperlink in Action #4 to point to new Google Drive spreadsheet --pb 2017-06-02 content validated, resource link in Description updated, resource link in Action step removed in favor of reference to subsequent action --pb 2018-06-01& gdoc& template added --pb 2020-01-13 content validated --pb 2020-12-14 changed Due in # Days from 102& to 135& --pb&
348 | 744 | 736 | Identify and empower worship band | Develop a band that is able to create an environment of worship in a style appropriate for your context. | Form the initial worship band as far ahead of the launch of worship gatherings as possible. Bands need to gel, and developing that chemistry takes time. And they need to develop a basic repertoire of songs they know and can play together. Plus, how cool would it be if the band were available to play at outreach events in the community months before Launch Sunday? Non-Christians in the Band? Will you allow someone who hasn't yet chosen to follow Jesus to play in the band? Perhaps you wouldn't want the worship leader to be a not-yet-believer, but lots of drummers, bassists, etc. have played themselves into the Kingdom. Decide where you'll draw that line. Auditions? Work out with your worship team leader whether the church will require auditions to be on the worship team. In desperation, you may be tempted to let anyone on the team who shows interest. Whether you choose formal auditions, assess each person's musical skill; but more so their motivation for wanting to join the team. Some worship teams require aspiring team members to show up 4 weeks in a row to serve but not perform. That tends to weed out those that are more interested in the spotlight than servant leadership. | Decide what your typical ensemble will look like (which pieces you usually have in the band). Figure out how many people you'll need to run the team each week. Recruit a team leader. Provide them a coach and inspire them to find an apprentice quickly. Recruit people to fill the team. This action is complete when you have completed each of the subtasks that follow this task. | <a href="/resources/item/278">Sample Worship Team Philosophy and Expectations</a> by Passion for Planting | 204 | 38 | 2000-01-01 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-05 content updated --pb 2020-01-14 content updated --pb 2020-12-14 changed Due in # Days from 194& to 204& & Duration from 14& to 30 --pb&
349 | 745 | 744 | Recruit a worship team leader | Recruit a worship team leader who will be responsible to make things happen while equipping and caring for team members. | For your church to be healthy, you have to equip people to lead and take ownership of ministry teams. Work your Leadership Development strategies to identify someone who has both leadership potential and musical ability. Your worship team leader needs to quickly embrace the values of the church; they'll be responsible to live them out and communicate those values to team members. Consider writing out a job description and basic expectations you'd have of any worship team leader. Go over those with your candidate and be sure they understand what they're signing up for. Things they'll need to jump on right away are: recruiting team members choosing songs for initial repertoire finding a rehearsal location and setting dates for rehearsals scheduling volunteers so that there are no gaping holes in the band Welcome to the "Joe Planter" show! If you're the Lead Planter, don't try to pull off the dual role of preacher and worship leader. It's a bad idea for lots of reasons. Find a volunteer or hire a staff person for this important leadership role. | Spend time in prayer asking God to raise up leaders. Identify a person to lead the worship team. Communicate expectations to the leader. Get a commitment from the leader to own the processes and leadership of the team. This action is complete when you have recruited and trained a team leader. |  | 197 | 31 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-05 content validated --pb 2020-01-14 content updated --pb 2020-12-14 changed Due in # Days from 201& to 204& --pb&
350 | 748 | 744 | Set date for beginning rehearsals | Prepare for public worship gatherings by practicing with the band and sound technicians. | To gel and have good chemistry, the band and sound team have to practice together. Sound glitches, feedback, uncomfortable pauses, off-pitch singing, off-beat bands, etc. can all leave a negative impression on people attending the church. In order to eliminate as many of these problems as possible, insist that the band practice many times before the first public worship gathering. Regardless how good the band is, they won't sound good unless the sound team has practiced with them to be able to get the most out of the equipment. | Schedule at least two full rehearsals with the full sound system and sound team. Debrief after each rehearsal to discuss the needs of the band members and the sound team. This action is complete when the band has practiced with the sound team and both teams are ready to lead worship during public gatherings. |  | 204 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-05 content updated --pb 2020-01-14 content updated --pb 2020-12-14 changed Due in # Days from 130& to 135& --pb&
351 | 750 | 736 | Recruit a church management software champion | Find a detail-oriented, tech-savvy person to champion the cause of having important data that can be used for leadership decisions. | Going through the hard work of setting up a church management system (ChMS) will be a waste of time if it is not utilized and maintained religiously. There is a tech industry acronym that applies here: GIGO ( noun ) 1 garbage in = garbage out You will only get out of the system what you put into it. Find someone on your team to champion the data who: Is administratively-minded Is detail-oriented to a fault Never settles for 'good enough' Cares about guests at the church being lovingly welcomed and treated well Can be trusted with sensitive personal information and confidential prayer requests The Church Management System Champion should be tasked with: Making sure that all data is entered promptly, accurately, and consistently Making sure that staff and volunteers are following up with the assimilation workflow so that no guest falls through the cracks Producing ministry reports that empower informed leadership decisions Maintaining the software and data | Identify someone on the Launch Team who would make a good ChMS Champion. Cast the vision of what a healthy, functioning follow-up system looks like and why it is critical. Grant that person access to the ChMS. Set expectations for timeliness and confidentiality. This action is complete once the Church Management System Champion inputs data for the first time. |  | 135 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-05 content updated --pb 2020-01-14 content updated --pb 2020-12-14 changed Due in # Days from 231 to 235& & Duration from 21& to 14& --pb&
352 | 751 | 736 | Identify and empower communion/offering team | Recruit a team to be responsible for collecting offerings and serving communion. | Communion and offering are two key elements of worship in the church, regardless of frequency. They can also be misunderstood by people with no church background. Develop a clear process for: preparing and serving communion collecting & counting offerings communicating the mechanics and meaning to the target audience Develop a leader who will build a team to carry out these processes. | Decide how you're going to serve communion and collect the offering. Develop a leader and empower them to build the team. Ensure that leader trains the team on communion and offering processes. This action is complete when the communion and offering team has run the communion and offering processes at a preview service. |  | 235 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-05 content validated --pb 2020-01-14 content updated --pb 2020-12-14 changed Due in # Days from 224 to 228& --pb&
353 | 753 | 751 | Finalize communion and offering processes | Develop processes for communion and offering that are appropriate for your context and consistent with the beliefs and values of the church. | After thinking through how to communicate communion and offering to your target audience, finalize a process. It makes training volunteers easier to have the process in writing. As you consider finalizing the processes, be sure you can answer the following questions: Communion: Who will purchase communion supplies and ensure that they are brought to the worship gathering location? Who will prepare communion before the gathering? How will communion be communicated to your target audience? How will communion be distributed? Who will communicate this to the people in attendance? Don't forget to let people know what to do with communion cups if you use them. Who will schedule volunteers and how will the schedule be communicated? Offering: How will you communicate offering to the target audience? Is offering only for those who consider the church home? Will you exempt first-time guests? What will you use to collect offering? How will offering be collected? What is done with the offering after it is collected? Who will schedule volunteers and how will the schedule be communicated? | This action is complete when you have written out the processes for communion and offering to be ready to train the team. |  | 228 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-06 content validated --pb 2020-01-14 content updated --pb 2020-12-14 changed Due in # Days from 231& to 235& --pb&
354 | 755 | 751 | Train team on communion and offering processes | Ensure that volunteers understand the communion and offering processes so that they can take charge and run with it. | The best processes are meaningless without proper training. Everyone involved in the communion and offering processes needs to understand their role. The processes needs to be practiced at least once prior to the first worship gathering preview service to ensure it works and everyone is clear on their roles. Scalability You cannot know fully how many people to expect for opening Sunday. Be sure that the team is trained on what to do in case a larger than expected crowd arrives. Will your process break if you have double the amount of people you expected? Have your team think through a scalability plan for just such an eventuality. | Train team on communion and offering processes. Have a plan for scalability. Practice the processes at least once before the first worship gathering preview service. This action is complete when the team is trained and ready to implement communion and offering processes on the Opening Day of worship gatherings. |  | 235 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-06 content updated --pb 2018-12-12 additional resources subsection added --pb 2020-01-17 content updated --pb 2020-12-14 changed Due in # Days from 231& to 235& & Duration from 7 to 28& --pb&
355 | 756 | 736 | Identify and empower tech team | Form a technical team to oversee the audio/visual/lighting (AVL) production of worship services and events. | The tech team is responsible for sound, lighting and projection at the worship gatherings. The team may also be responsible for creating any videos or special content for use during church functions. Typically, the tech team requires special training or skill sets. You're going to need at least one very strong AVL tech leader. Ideally, you'll also identify a backup, or someone at a sponsor/network church that could provide expertise. Audio The setup of the soundboard and sound equipment before a worship gathering has a demanding schedule. The audio has to be the first thing that gets set up so the band has time to warm up and sound check. For that reason and others, your soundboard operator should also be the one that sets up the system that week. Video The projectionist should run through the song slides with the band as they warm up in case there are any last-minute changes. Lighting You may be able to get away with having your sound operator or projectionist oversee the lighting if there is only 1 or 2 changes during the worship gathering. But if there are multiple changes between scenes (elements of the gathering), that will demand a 3rd tech operator. Those lighting scene changes usually come with changes for sound and projection as well. | Determine the specific roles and responsibilities to be included in the tech team. Figure out how many people you'll need to run the team each week. Recruit a qualified team leader (see subtask). Provide them a coach and inspire them to find an apprentice quickly. Recruit people to fill the team. Train the tech team on setup and operation (see subtask). This action is complete when the initial tech team has practiced with the equipment once. | <a href="https://unseminary.com/its-too-loud-responding-to-volume-critics-at-your-church/">"It's Too Loud!": Responding to Volume Critics at Your Church</a> on unSeminary | 235 | 29 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-06 content updated --pb 2020-01-17 content updated --pb 2020-12-14 changed Due in # Days from 217& to 220& --pb&
356 | 757 | 756 | Recruit a tech team leader | Identify and empower a skilled, reliable leader for the tech team so that the AVL will run smoothly during the worship gatherings. | For your church to be healthy, you have to equip people to lead and take ownership of ministry teams. Work your Leadership Development strategies to identify someone who has both leadership potential and AVL experience. Your tech team leader needs to quickly embrace the values of the church; they'll be responsible to live them out and communicate those values to team members. Consider writing out a job description and basic expectations you'd have of any tech team leader. Go over those with your candidate and be sure they understand what they're signing up for. Things they'll need to jump on right away are: recruiting team members choosing and/or learning how to operate the AVL equipment coordinating with the worship leader scheduling volunteers so that there are no gaping holes in the schedule The leader of the Tech Team needs to have specialized skills in audio, video and lighting. But more important is their ability to build their team. | Spend time in prayer asking God to raise up leaders. Identify a person to lead the tech team. Communicate expectations to the leader. Get a commitment from the leader to own the processes and leadership of the team. This action is complete when you have recruited and empowered a team leader. |  | 220 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-06 content updated --pb 2020-12-14 changed Due in # Days from 231& to 235& --pb&
357 | 760 | 756 | Train Tech Team on Equipment Setup and Operation | Train volunteers to setup and operate the AVL equipment so that tech enhances the worship gatherings. | The best equipment and processes are meaningless if the workers aren't trained. Ensure that everyone involved in the Tech Team understands their role. Practice the processes at least once prior to the first preview service to ensure the process works and everyone is clear on their roles. All volunteers should be cross-trained to be able to fill in for other people who may be sick. Often tech people from other churches will be willing to come out, help you set everything up, and train your team on basic sound, lighting and video techniques. The vendor you purchase the AVL equipment from may also do on-site training for a fee &mdash; usually money well spent. | Train team on the set up and operation of the AVL equipment. Practice the processes at least once before the preview service. This action is complete when the Tech Team has been trained and is ready to set up and operate everything for the preview services and Opening Day. |  | 235 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-06 content updated --pb 2020-01-17 content updated --pb 2020-12-14 changed Due in # Days from 231& to 235& & Duration from 21& to 75& --pb&
358 | 761 | 736 | Identify and empower children's ministry team | Form an effective children's ministry team that leads many children to Christ. | If your new church is reaching young families, a thriving children's ministry will support entire families and potentially lead many children to Jesus. After all, the Kingdom belongs to such as these, right? "In the US, nearly 85% of conversions to Christ happen between the ages of 4 and 14" - <a href="https://childrensministryonline.com/the-4-14-window/">childrensministryonline.com</a> For Children's Sake Children are valuable in and of themselves. They aren't just the future of the Church, they are the Church of today, too. Resist the temptation to use children's ministry as bait to reach the parents. Of course, you want to see whole families come to Christ. But making children a means to an end can quickly devolve into babysitting that neglects their souls. A Little Extra Time Starting a children's ministry takes longer than starting most other teams. There are lots of layers and moving parts to a weekly children's ministry. Begin recruiting people for this ministry as soon as possible. This ministry team will is very often the largest and will require the most recruiting. And after they're recruited, they'll need to be trained. Preventing Child Abuse It is sad that in our day and age so much abuse happens anywhere. We owe it to the children Jesus entrusts to us to take significant measures to prevent and detect abuse. A non-negotiable for your ministry will be running background checks on all staff and any volunteer that works with minors. You should also arrange for your children's workers to take abuse awareness and reporting training. Have them do it up front and then require them to renew their training annually or even semi-annually. Your background check vendor and/or your church insurance company may provide training resources. | Subtasks that follow will walk you through each of these important steps: Recruit a team leader for the children's ministry. Provide them a coach and inspire them to find an apprentice quickly. Figure out how many people you'll need to run the team each week. Purchase or develop children's curriculum/programming. Develop children's ministry safety procedures. Determine process for conducting background checks. Train children's ministry leaders and team members. This action is complete when you have completed each of the subtasks that follow this task. |  | 235 | 75 | 2015-02-03 05:00 | 2022-04-07 04:00 | 2000-01-01 05:00 | template: standard 2017-06-06 content updated --pb 2020-01-17 content updated --pb 2020-12-14 changed Due in # Days from 187& to 190& & Duration from 14& to 30& --pb&
359 | 762 | 761 | Recruit a children's ministry team leader | Identify and empower a relational, reliable leader for the children's ministry team who can work through adults to get children's ministry done. | For your church to be healthy, you have to equip people to lead and take ownership of ministry teams. Work your Leadership Development strategies to identify someone who has both leadership potential and is a natural recruiter. Your children's ministry team leader needs to quickly embrace the values of the church; they'll be responsible to live them out and communicate those values to team members. Consider writing out a job description and basic expectations you'd have of any children's ministry team leader. Go over those with your candidate and be sure they understand what they're signing up for. Things they'll need to jump on right away are: recruiting team members choosing curriculum purchasing ministry equipment running background checks scheduling volunteers so that there are no gaping holes in the schedule You may be inclined to pick a team leader that is great with kids. While that is a plus, a children's ministry team leader needs to spend more time building teams and working with adult volunteers than they do working with the kids. | Subtasks that follow will walk you through each of these important steps: Recruit a team leader for the children's ministry. Purchase or develop children's curriculum/programming. Develop children's ministry safety procedures. Determine process for conducting background checks. Get a commitment from the leader to own the processes and leadership of the team. This action is complete when the team leader has completed each of the subtasks that follow this task. |  | 190 | 30 | 2015-02-03 05:00 | 2022-04-07 04:00 | 2000-01-01 05:00 | template: standard 2017-06-06 content updated --pb 2018-04-02 additional resources subsection added --pb 2020-01-17 content updated --pb 2020-06-24 Orange curriculum& additional resource added (points to P4P blog post) --pb 2020-12-14 changed Due in # Days from 201& to 204 --pb&
360 | 766 | 761 | Purchase or develop children's programming materials | Create a children's program at the worship gathering that supports the overall vision of the children's ministry. | The children's ministry team comes to life when the kids arrive! Lots of planning, preparation and training goes into making that happen. It's important that your church does children's ministry well for the children's sake. And doing it well doesn't have to mean flashy. It should be about fostering relationships with adults leaders they can trust, and helping them find and follow Jesus. Programming vs Curriculum There are several great models for children's ministry programming that will help you accomplish relationship. Which one you pick should be based on your philosophy for children's ministry and, ultimately, the church's Vision Frame . The curriculum is the tool you will choose will drive that style of programming. Resources and volunteers are limited in a new church. Don't choose a model or curriculum that stretches your volunteer base too thin. Do choose one that is scalable and allows for rapid growth. The children's ministry needs to grow with the congregation. Singing Worship music can also be a key part of Sunday morning children's programming. Many curriculae now incorporate worship into the lessons. Worship can be a challenge, particularly for older elementary children. Will you use live worship or recorded worship? Will you have interactive worship? Will you project lyrics? The answers to these questions will also impact what equipment you will need to purchase. | Review the demographics of your area as well as the Average Target Family document. Determine what the context of the average child in your area is like: are they from single or dual parent homes? is it common to be on reduced lunches at school? etc. Determine style of programming appropriate to your context. Determine the number of classes and what ages are in each class. Keep your volunteer staff in mind. Do not choose a model that stretches them to thin. Determine how Music will be used in each class or the ministry overall. This action is complete when the planter and the team leader have created a children's programming structure. | Church plant discount on <a href="https://church-planting.net/orange-loves-church-planters/">Orange Curriculum</a> <a href="https://churchleaders.com/children/childrens-ministry-articles/342123-how-to-choose-a-childrens-ministry-curriculum.html">How to </a><a href="https://churchleaders.com/children/childrens-ministry-articles/342123-how-to-choose-a-childrens-ministry-curriculum.html">Choose a Children's Ministry Curriculum</a> on churchleaders.com Free children's ministry curriculum: <a href="https://open.life.church/categories/314-kids">Life.Church Open</a> <a href="https://onestorycurriculum.com/">the Meeting House</a> <a href="https://www.childrens-ministry-deals.com/collections/free-childrens-ministry-curriculum">Children's Ministry Deals</a> <a href="https://www.childrens-ministry-deals.com/pages/kidmin-curriculum">10 Most Popular Children's Ministry Curriculum Options</a> on childrens-ministry-deals.com <a href="https://www.kidmintools.com/2014/06/30/the-huge-list-of-childrens-curriculum-providers/">The Huge List of Children's Ministry Curriculum Providers</a> on kidmintools.com --> | 204 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-06 content validated& & links updated --pb 2020-01-17 content updated --pb 2020-12-14 changed Due in # Days from 201& to 204& --pb&
361 | 767 | 761 | Develop children's ministry safety procedures | Develop a well-thought-out safety plan to ensure the safety of the kids in the care of your church. | Developing the safety procedures is an essential step in having a high-quality children's ministry. It only takes one incident to seriously damage a child. That incident will seriously damage the reputation and witness of your church, too. Take the facility in to consideration. Many rented facilities are not ideal for security. They require unique accommodations to ensure the safety of kids. The safety procedures must include a custom plan for ensuring the safety of kids in your location. This means thinking through: how kids are kept corralled in their rooms how to keep unauthorized adults out of the rooms (including parents) how to secure any exits or potential hiding places The plan should also include an application to volunteer to work with kids in any way. An application is an important first line of defense against would-be predators. Once you've created the safety plan, train volunteers to practice the procedures put in place. Do not take any shortcuts implementing this plan! | Develop an application process for volunteers. Watch <a href="https://www.youtube.com/watch?v=L2VsSgwbqlI">Church Safety for Kids 18 & Under</a> by Waypoint Church Partners Run background checks on all children's ministry volunteers (see subtask following). Adopt a "no volunteer alone with kids" policy, including a bathroom policy. Decide whether to adopt a policy for ratios of volunteers to kids. Example: the nursery will have a ratio of 4 kids to 1 volunteer. Decide if you will you close a room if you exceed those ratios. Train volunteers on safety procedures. Develop a system for sign-in and sign-out to ensure that all kids are returned to the right adults. As a part of the sign-in and sign-out process, create a plan for how to contact parents during the worship gathering in case of emergency. Determine safety procedures such as a Fire Escape and Disaster Plan . Create a way for everyone to easily identify children's ministry workers (ex: name tags with the volunteer's photo, t-shirts, or something similar). Write down all of these safety procedures. Include a brief summary of that plan in a Parent and Volunteer Handbook and training manuals. Add the detailed plan to the church's Policy Book. This action is complete when you have implemented safety procedures to protect the health and well-being of children in the church's care. |  | 204 | 7 | 2015-02-03 05:00 | 2022-04-07 04:00 | 2000-01-01 05:00 | template: standard 2017-06-06 content & links updated --pb 2018-03-28 additional resources subsection added --pb 2020-01-17 content updated --pb 2020-12-14 changed Due in # Days from 201& to 204& --pb&
362 | 768 | 761 | Determine process for conducting background checks | Pick a vendor and create a background check process to avoid preventable incidents and demonstrate that your church takes steps to prevent misconduct with children. | Jesus is serious about protecting children from harm. "If anyone causes one of these little ones&mdash;those who believe in me&mdash;to stumble, it would be better for them if a large millstone were hung around their neck and they were thrown into the sea." - Jesus (see Matt 18:6, Mark 9:42, Luke 17:2) It may be impossible to prevent every single case of physical and sexual abuse in our churches, but that shouldn't stop us from trying. The children are counting on us. Background Checks Child predators will appear to be very nice and normal &mdash; you won't be able to spot them. An important line of defense is running background checks on every adult who works with youth and children. Don't skip this step. Covenant to make it a non-negotiable for your church. Choose an All-Inclusive Search In the US, our levels of government aren't freely sharing criminal data yet. That may be good for the public's privacy rights, but it makes running background checks a little more complicated. Most providers will offer you a low-cost background check option that only checks the federal database. This is an inadequate background check . Don't be tempted to save a few bucks. Run an all-inclusive search that includes: federal state local/county registered offenders database The background check process is not perfect. An all-inclusive search gives you the best chance of preventing abuse in your church. Keep Good Records Modern background check vendors will email a link to the applicant where they will input all of their own sensitive information so you don't have it laying around on some paper form. Background check results will be accessible on the app's dashboard. Many will interface with the most popular church management software apps. Make sure only a very few trusted people have access to those records on a need-to-know basis. Foreign Nationals Running background checks on people who have recently immigrated to the United States presents a particular challenge. Other countries may or may not have effective background record keeping. Records sometimes do not travel across borders. Work with your background check vendor to navigate this if it comes up. | Choose a background check vendor; consider first the one(s) that integrate with your church management software. Sign up for their service and learn their system. Do the initial round of background checks for volunteers. This task is complete when you have run the initial round of background checks. | Vendors that have served our planters in the past: Checkr (for <a href="https://www.planningcenter.com/integrations/checkr">PlanningCenter</a> and <a href="https://pushpay.com/product/chms-software/">CCB</a>) <a href="https://www.protectmyministry.com/programs/">Protect My Ministry</a> <a href="https://www.group.com/background-checks/">Shepherd's Watch</a> <a href="https://www.vanderbloemen.com/blog/5-red-flags-during-a-background-check">5 Red Flags During a Background Check</a> by Vanderbloemen Search Group | 204 | 7 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-06 content and links updated --pb 2020-01-17 content updated --pb 2020-12-14 changed Due in # Days from 231& to 235& --pb&
363 | 773 | 761 | Train children's ministry leaders and team members | Equip volunteers with the knowledge, skills, resources and tools they need to live out their God-given calling to serve kids. | Training and equipping volunteers is an essential part of any children's ministry. Many volunteers will have a willing heart, but will need a leader to equip them so that they can succeed. It would be easy to let training slip through the cracks because of your busy schedule. Trust that making time will save you time in the long run. A well-trained volunteer staff will take on more ownership in the ministry and be more committed over the long haul. Training provides cohesiveness and stability, and it results in a well-balanced ministry. Really, Another Meeting? You may run into the perception among the volunteers that the training is "not necessary" or "just another meeting". Nothing could be further from the truth. So, create an environment of fun at your training events. Rather than just lecturing, considering leading the training as you would lead a children's class. This will give you the opportunity to demonstrate teaching principles as well as make it fun for everyone involved. Keep in mind people's busy schedules when deciding how often to do training events. Maybe break up the events into individual classroom/age-groups as well as one large group training. An effective way to provide decentralized training is through sending out a weekly e-mail that includes a training tip, video and/or upcoming events. Feedback Loop Evaluation is a crucial part of the training process. The ministry leader can't be in every classroom with the kids, nor will they be able to interact with every parent. You're going to need feedback from your workers to make improvements in the ministry. Let the volunteer staff to evaluate the team leader, too, so that the leader can grow and better serve the workers. Trainer, Train Thyself Training doesn't end with the volunteers. You have to be intentional about seeking out training as well. Consider these training avenues: find a local children's ministry coach/mentor read books, magazines and blogs to stay up to date with children's ministry attend a children's ministry conference or training each year | Decide what types of training you'll require and how often. Plan the initial training event. Include: how to use the curriculum what the safety procedures are policies for discipline how to create a welcoming environment Create feedback mechanisms to improve the ministry. Make a plan for volunteer appreciation. Create a training plan for the ministry leader to stay fresh. This action is complete when you have trained other leaders and team members in the children's ministry. | <a href="https://www.childrens-ministry-deals.com/pages/best-childrens-ministry-conferences">10 Best Children's Ministry Conferences</a> on childrens-ministry-deals.com | 235 | 14 | 2015-02-03 05:00 | 2022-04-07 04:00 | 2000-01-01 05:00 | template: standard 2017-06-07 content updated --pb 2020-01-17 content updated --pb 2020-12-14 changed Due in # Days from 231 to 235& & Duration from 21& to 28& --pb&
364 | 776 | 736 | Identify and empower hospitality team | Form a team that will serve guests at your worship gatherings well so that they have a great first impression and experience. | You only get to make a first impression once. Form a team who will connect with newcomers and provide them the information and resources they need to connect with the church. This team goes by a lot of different names depending on the congregation: Guest Services Team First Impressions Team Hospitality Team Greeter Team Call it what you will, the team is responsible for all the first touch or first contact with newcomers from the parking lot into the auditorium. This includes: parking lot attendants greeters refreshment servers or attendants info table attendants Your team should be full of people with high emotional intelligence &mdash; people who just naturally smile, adapt and connect well with others. Train your hospitality team to be aware of what their body language is sending to guests. And help them find the balance between being aloof and overly-eager. | Decide what to call the team. Determine what the team will be responsible for. Develop a leader and empower them to build the team. Figure out how many people you'll need to run the team each week. Recruit additional people to serve as parking lot attendants, greeters, hospitality hosts, etc. This action is complete when you have completed each of the subtasks that follow this task. |  | 213 | 72 | 2015-02-03 05:00 | 2021-01-18 05:00 | 2000-01-01 05:00 | template: standard 2017-06-07 content updated --pb 2020-01-17 content updated --pb 2020-12-14 changed Due in # Days from 210& to 213& --pb&
365 | 777 | 776 | Recruit hospitality team leader | Identify and empower a relational, reliable leader for the hospitality team so that every guest feels welcomed and accepted at the worship gatherings. | For your church to be healthy, you have to equip people to lead and take ownership of ministry teams. Work your Leadership Development strategies to identify someone who has both leadership potential and emotional intelligence. Your hospitality team leader needs to quickly embrace the values of the church; they'll be responsible to live them out and communicate those values to team members. Consider writing out a job description and basic expectations you'd have of any hospitality team leader. Go over those with your candidate and be sure they understand what they're signing up for. Things they'll need to jump on right away are: recruiting team members scheduling a training event scheduling volunteers so that there are no gaping holes in the schedule | Spend time in prayer asking God to raise up leaders. Identify a person to lead the Guest Services Team. Communicate expectations to the leader. Get a a commitment from the leader to own the processes and leadership of the team. This action is complete when you have recruited and trained a hospitality team leader. |  | 213 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-07 content updated --pb 2018-11-16 content updated to match Greg Curtis' content in our strategy template; moved to child task of "Issue Written Assimilation Strategy" from parent ID #776& --pb 2012-12-02 content updated --pb 2020-12-16 changed Due in # Days from 137& to 155 --pb&
366 | 781 | 776 | Train greeters | Train a team of greeters who will create a warm and friendly atmosphere for everyone attending the worship gathering. | The Lobby Has Moved The greeters out front and in the lobby used to be the first impression guests would have of your church. But by and large, guests who come have been stalking your church online for weeks or months. By the time the show up, the have heard sermons, seen social media posts, read the staff bios, etc. But they still need a friendly face when they show up. And that face sets the tone for their whole experience while they're there. Train in Emotional Intelligence (EQ) IQ is fixed from birth. But someone his is book smart doesn't necessarily make the best greeter. Any warm body out front won't do the trick. The good news is that EQ can be learned, and people who seem to have it naturally can get even better. Search online for blogs, podcasts and videos for your team. Effective greeter training will include: a basic outline of what to say and/or a few low-threat conversation starters underscoring the importance of eye contact and body language (as much as <a href="https://en.wikipedia.org/wiki/Nonverbal_communication">89% of what we communicate is nonverbal</a>) basic information about the church (location of restrooms, children's ministry classrooms) and whom to find if they don't know the answer escorting guests to places they're trying to find, never pointing making conversations with kids while escorting new families to the children's ministry area, introducing them to the teacher | Find training material for your greeters, especially covering EQ. Schedule a greeter training time, even if it is on a Sunday morning before the worship gathering. Train the greeters. This action is complete when you have trained the greeters. | <a href="https://unseminary.com/5-training-experiences-to-help-your-team-feel-like-first-time-guests/">5 Training Experiences to Help Your Team Feel Like First-time Guests</a> on unseminary.com | 228 | 14 | 2015-02-03 05:00 | 2021-03-26 04:00 | 2000-01-01 05:00 | template: standard 2017-06-07 content updated --pb 2020-01-20 content updated --pb 2020-12-14 changed Due in # Days from 238& to 228& & Duration from 21& to 28& --pb&
367 | 782 | 736 | Identify and empower set up and tear down team(s) | Recruit a set up and tear down team (or 2 separate teams) so that equipment throughout the facility is staged before the gathering and packed up afterward. | Set Up A set up team is responsible for unloading, plugging together, assembling and otherwise setting up all of the equipment required to carry out the regular worship gatherings: Lobby, including: info table (or similar) hospitality Children's Ministry Worship, including: AVL equipment Chairs Staging & backdrops Signage The team should be committed to being there early to transform the rented facility into a place for worship. Lead your team to arrive early enough not to be rushed through setup, but to be able to talk and have relational time with each other as well. All equipment should be completely set up well before people begin arriving. Tear Down A tear down team is responsible for the reverse of the above. They should not begin breaking down until after the bulk of the crowd has gone. This gives the team members relational time to connect with newcomers before becoming engrossed in tasks. The tear down team returns the facility to the same or better condition as when the set up team arrived. | Determine what the set up and tear down team(s) will be responsible for. Figure out how many people you'll need to run the team each week. Develop a leader and empower them to build the team. Recruit people to fill the teams. This action is complete when you have completed each of the subtasks that follow this task. |  | 228 | 29 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-06-09 content validated --pb 2020-01-20 content updated --pb 2020-12-14 changed Due in # Days from 224& to 213& --pb&
368 | 783 | 782 | Recruit set up and tear down team leader(s) | Identify and empower a resourceful, reliable leader for the set up and tear down team(s) so that all equipment gets set up properly and on time for the worship gatherings. | For your church to be healthy, you have to equip people to lead and take ownership of ministry teams. Work your Leadership Development strategies to identify someone who has both leadership potential and can recruit people to the team. Your set up and tear down team leader(s) should be more of a recruiter, people organizer and cheerleader than a skilled doer. Set up and tear down don't happen without a full team. Consider writing out a job description and basic expectations you'd have of any set up or tear down team leader. Go over those with your candidate(s) and be sure they understand what they're signing up for. Things they'll need to jump on right away are: recruiting team members scheduling a training event scheduling volunteers so that there are no gaping holes in the schedule | Spend time in prayer asking God to raise up leaders. Develop a leader and empower them to build the team. Communicate expectations to the leader. Get a commitment from the leader to own the processes and leadership of the team. This action is complete when you have recruited and trained set up and tear down team leader(s). |  | 213 | 14 | 2015-02-03 05:00 | 2022-02-08 05:00 | 2000-01-01 05:00 | template: standard 2017-06-09 content validated --pb 2020-12-14 changed Due in # Days from 238& to 228& --pb&
369 | 786 | 782 | Train team on set up and tear down | Train the set up and tear down team(s) to efficiently and safely unload, set up and reload equipment. | The first few times the team(s) sets up and tears down the equipment, it will take a long time. Over time, the team becomes more efficient and gets faster. This is why you have to train the team prior to the launch of worship gatherings. Preview services provide a great environment for this. Make sure that you have practiced setting up and tearing down once at a dry run/training event (see subsequent PlanterPlan task). Then work with team to execute the set up and tear down at all of the preview worship gatherings you have scheduled prior to the Opening Day of worship gatherings. Have your team create set up and tear down manuals that show what goes where and how things get loaded back into the truck/trailer. This makes training new volunteers easy and intentional. | Schedule a time to train the team (a dry run or practice gathering before the previews). Conduct the training. This action is complete when you have recruited and trained the initial set up and tear down team(s). |  | 228 | 14 | 2015-02-03 05:00 | 2020-12-14 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 content updated --pb& 2020-01-20 content updated --pb 2020-12-16 changed Due in # Days from 224& to 219& & Duration from 121& to 98& --pb&
370 | 1305 | 736 | Identify and empower safety team | Form a safety team to address safety issues and emergency response at worship gatherings. | One of your key responsibilities as the church planter is to provide a safe place for people to discover God. That word "safe" has several meanings: a safe place to ask questions without being judged a safe place to come as I am (clothing, language) without being looked down upon a safe place to bring my children knowing they will be loved and protected a safe place to worship without threat of physical harm You'll have to adopt a proactive (vs reactive) approach to safety and security. The safety team will be responsible for reducing and responding to safety threats during worship gatherings (#4 above). You need to have a plan and a team trained in security & response basics if you're faced with a medical emergency, act of violence or natural disaster. Your safety team leader should be someone with security, law enforcement and/or military experience. At least one team member should be medically trained in at least first aid and CPR. Your church planting network and/or church insurance company may be able to provide guides and training materials for you safety team. | Determine what the safety team will be responsible for. Figure out how many people you'll need to run the team each week. Develop a leader and empower them to build the team. Recruit people to fill the teams. This action is complete when you have completed each of the subtasks that follow this task. | <a href="/resources/item/392">Sample Church Emergency Response Plan</a> <a href="https://www.churchplantingtactics.com/how-to-form-a-church-security-team/">How to Form a Church Security Team</a> on churchplantingtactics.com (including a directory of useful links) <a href="https://www.brotherhoodmutual.com/resources/church-security/">Church Safety & Security Resources</a> on brotherhoodmutual.com <a href="https://www.churchplantingtactics.com/church-emergency-response-plan/">4 Keys to Creating a Church Emergency Response Plan</a> on churchplantingtactics.com <a href="https://www.youtube.com/watch?v=9lU2yXMvIog&t=1s">Church Safety: The Art of De-Escalation</a> by Waypoint Church Partners | 228 | 29 | 2020-01-24 05:00 | 2022-04-07 04:00 | 2000-01-01 05:00 | template: 2020-10-19 found Due in # Days & Duration fields empty, repopulated --PB 2020-12-14 changed Duration from 14& to 28& --pb& 2021-01-18 found Due in # Days & Duration fields empty, repopulated --PB
371 | 1306 | 1305 | Recruit a safety team leader | Identify and empower a qualified leader for creating, training and organizing a church safety team. | For your church to be healthy, you have to equip people to lead and take ownership of ministry teams. Work your Leadership Development strategies to identify someone who has leadership potential, experience in security/law enforcement/military and can recruit people to the team. Your safety team leader should be more of a recruiter, trainer, people organizer and cheerleader than a skilled doer. Consider writing out a job description and basic expectations you'd have of any safety team leader. Go over those with your candidate and be sure they understand what they're signing up for. Things they'll need to jump on right away are: developing a church emergency response plan recruiting team members, especially: current and former EMTs and firefighters those with CPR certification current or former medical professionals active or former law enforcement active or former military current or former security professionals finding or developing training materials scheduling a training event scheduling volunteers so that there are no gaping holes in the schedule | Spend time in prayer asking God to raise up leaders. Develop a leader and empower them to build the team. Communicate expectations to the leader. Get a commitment from the leader to own the processes and leadership of the team. This action is complete when you have recruited and trained a security team leader. |  | 213 | 14 | 2020-01-24 05:00 | 2022-04-07 04:00 | 2000-01-01 05:00 | template: 2020-10-19 found Due in # Days & Duration fields empty,& repopulated --PB 2021-01-18 found Due in # Days & Duration fields empty, repopulated --PB
372 | 1307 | 1305 | Train team members on safety and response | Train the safety team how to reduce threats to safety every week and respond to emergencies as they arise. | Banks regularly train their branch employees how to respond to robberies. They also take measures to reduce the likelihood they'll happen. But they also know that the employees have to decide ahead of time how they're going to react, or they could make some very bad impulsive decision in the heat of a robbery. The safety team members will require as much training as any other ministry team. The responsibilities of the role are weighty. Find experts or experienced church security team leaders to help with the training. Do lots of research. Don't wing it on training. | Find church safety training resources and materials. Find a church safety expert or someone with experience to train you and/or train the entire team. Schedule a time to train the team. Conduct the training. This action is complete when you have trained the initial safety team. |  | 228 | 14 | 2020-01-24 05:00 | 2022-04-07 04:00 | 2000-01-01 05:00 | template: 2021-01-18 found Due in # Days & Duration fields empty, repopulated --PB
373 | 808 | 1413 | Milestone: Get Startup Equipment | Plan, order and assemble the equipment you'll need to accomplish the vision God has given you for the worship gatherings. | Having equipment to carry out a worship gathering is a necessity in today's North American churches. With most plants holding worship gatherings in rented facilities, you'll have to buy everything from children's equipment to audio/visual/lighting (AVL) and sometimes even chairs. This milestone will walk you through figuring out what kind of equipment you'll need for the worship gatherings and managing ordering deadlines. | --no steps-- |  | 260 | 200 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2020-01-20 content updated --pb 2020-12-16 changed Due in # Days from 112& to 122& & Duration from 7 to 1& --pb & &
374 | 809 | 808 | Read this startup equipment overview | Wrap your brain around everything that's involved and at stake in ordering ministry equipment for the worship gatherings. | It's easy to get wrapped up in the excitement and details of buildings and gadgets. We can't let those things become the point of church. You can let your vision & mission drive your equipment choices, or let them drive your vision. Be proactive and intentional about the kind of equipment you'll use for worship gatherings. Keep the big picture in mind so you don't get lost in the weeds or sucked in to a scarcity mentality by reacting to perceived circumstances. Expectations You even get to contextualize your equipment needs. Don't buy an equipment package that is well above or below the means of the people you're reaching. Transportation and Storage Chances are good you'll have to get the equipment from storage to the facility and back each week. Common options include: volunteers pulling small- to medium-sized trailer(s) volunteers pulling large-sized trailer(s) volunteers driving a church-owned truck & trailer combo volunteers driving a church-owned box truck storing some or all of the equipment at the facility Opportunity Cost Too many planters try to save a few bucks by shopping for all of the ministry equipment themselves, only later to regret eating up the 80-90+ work hours they could have used out in the community or developing leaders. | Read the brief overview above. Watch the Passion for Planting training video "<a href="/resources/item/75">Obtain Startup Equipment</a>" featuring Ed Stetzer. This task is complete when you've read the content and watched the video. |  | 122 | 1 | 2000-01-01 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 updated content & links --pb& 2020-01-20 content updated --pb 2020-12-16 changed Due in # Days from 112& to 135& & Duration from 7 to 14& --pb&
375 | 810 | 808 | Develop a rough draft equipment list | Create an initial ballpark list of equipment to begin the purchasing process. | At this stage of the equipment process, don't get into model numbers and colors. You're just putting together a rough list of the kinds of things you would need to pull off a worship gathering that supports the vision. Start with a sample equipment list (see Actions below). Cross off things you won't need and add things you will. Quality Expectations Note on the list for each category or even each item whether you're looking for good, better or best quality. You need to communicate those expectations as you ask for pricing quotes. Get Quotes Use the list as the springboard for getting quotes from all-in-one equipment package vendors, like: <a title="ChurchPlant.com" href="https://www.churchplant.com">ChurchPlant.com</a> <a title="Portable Church Industries" href="https://www.portablechurch.com">Portable Church Industries</a> <a title="Churcn in a Box" href="https://www.churchinaboxsolutions.com">Church in a Box</a> --> <a title="Church on Wheels" href="https://www.churchonwheels.com">Church on Wheels</a> They will manage the entire process, build an integrated system, and save you tons of time for not much more than you'd spend doing it yourself. DIY Or you can use the list for delegating purchasing to your team. If you do manage your own list, find launch team members that have expertise in either equipment or project management. Beware of the time sink: many planters burn 80, 90 or more work hours managing the list themselves. That's time that you could used for disciple-making, community service and leadership development. Designing the AVL System The equipment package vendor will offer to travel to your site to see the facility and take specific measurements, etc. There are lots of environment factors to consider when putting together both a sound system, a projection system and potentially also a lighting system. Some sound considerations are: Is the room made of hard surfaces that will bounce sound around? Is the room wide or deep or both? What is the typical size of the band (ex: a simple 3-piece ensemble, or full band with 6 singers)? What type of sound are you going for? (ex: coffee house, rock, or club?) How skilled are your initial soundboard operators? How far is it from the stage to where the sound board will be? Are the sermons going to be recorded for podcast? Some projection considerations are: How much ambient light is in the room (ex: a gymnasium with skylights or a theater with no windows)? How far is it from the projector to the screen? How far is it from the projector to where the projectionist will sit? Is there room for rear projections (preferable), or will the projector need to be in front of the screen? What output jack does the computer used for projection have (e.g. HDMI, DVI, RJ-45)? ...and does that match the jack(s) on the projector? How much video will you be using? | Start with Passion for Planting's <a title="equipment list template" href="/resources/item/74">equipment list template</a> and/or an actual church plant equipment order from a friend. Add and remove items to get to the list that supports the vision. Note quality expectations for entire sections and/or individual items. Use the list to get quotes for equipment costs. This action is complete when you have a rough draft list of equipment. | <a href="https://www.churchplantingtactics.com/piecemeal-church-plant-equipment-package/">4 Reasons Not to Piecemeal a Church Plant Equipment Package</a> on churchplantingtactics.com | 135 | 14 | 2000-01-01 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 content & resource link updated --pb& 2020-01-20 content updated --pb 2020-12-16 changed Due in # Days from 112& to 142 & Duration from 7 to 14& --pb&
376 | 811 | 808 | Add dates and dollars to the equipment list | Using quotes from vendors for specific pieces of equipment, add cost figures and ordering lead times to your rough draft equipment list. | The total price tag for everything you dreamed of may surprise you. And the time it takes to get everything ordered, delivered and assembled is probably longer than you're thinking. As the vendors' quote(s) come in, or as your team leaders submit their wish lists, add dollar amounts to the rough draft equipment list. Keep a running total. Also add ordering lead times to the rough draft equipment list. Your all-in-one package vendor will need some time to order everything, assemble it, and get it in the trailer. And it's common for various pieces of AVL equipment to be back-ordered for 60 days regardless of whether you're using an equipment vendor or going DIY. Walk back from the dry run/training event you're planning (see subsequent PlanterPlan task) and add ordering deadline reminders to your calendar. Everyone needs to have practiced on the equipment before the first preview worship gathering. | Based on quotes, add dollar amounts to your rough draft equipment list. Add ordering lead times for items as well. This action is complete when you have reviewed the second-draft list and made both budgetary and deadline decisions. |  | 142 | 14 | 2000-01-01 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 content reviewed --pb& 2020-01-20 content updated --pb 2020-12-16 changed Due in # Days from 112& to 142 --pb&
377 | 812 | 808 | Determine spare equipment and supply list | Create a list of supplies, tools and equipment to have on hand that may very well avert a Sunday morning emergency. | You won't be able to have all of the spare parts, supplies and equipment you could ever possibly need. That would be expensive and wasteful. But you can have a common sense 'first aid' kit that has what you'll need to address the kinds of emergencies many church plants run into. Purchase Based on Risk There are two major components to risk: how much distraction a particular failure would cause, and how likely it is to happen. For example, the preacher's mic battery pack dying 5-minutes before the worship gathering starts wouldn't be unusual, and it would be a huge distraction. So have a box of batteries ready to go. In addition to batteries, here are other common items to consider: a roll of duct tape or gaff tape (fixes anything, right?) a roll of painter's tape (to temporarily mark things) a handful of zip ties a basic toolkit with screwdrivers, wrenches and a hammer; be sure it includes a tiny screwdriver for battery packs and other electronics scissors | Draft a list of spare equipment and tools to have on hand. Add desired spare parts to the equipment list. Put someone in charge of ordering those items. This action is complete when the spare parts, supplies and tools have been ordered. |  | 142 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 content reviewed --pb& 2020-01-20 content updated --pb 2020-12-16 changed Due in # Days from 126& to 151& & Duration from 7 to 14& --pb&
378 | 732 | 808 | Create a map for strategic sign placement | Make strategic decisions about where signs will go at the facility and nearby intersections, and create a map as reference for your signage team. | Location, Location, Location. The mantra of the Real Estate agent is very applicable to church signage. Unless you want your location to be invisible, be intentional about putting out the right number of signs at the right places. Drive the area surrounding the facility. By observing traffic patterns, determine the best locations to place signs. Consider high visibility areas as well as areas where drivers may be stopped at lights or stop signs. The orientation of your sign can be as important as the location of the sign. Often angling the sign toward traffic (like in a median strip) is more effective than having it point directly down the street. Here is a sample of a map showing where to place signage at major intersections around the facility: Here is a sample map showing where to place signage in front of the facility: | Become familiar with traffic patterns. Determine which intersections people are most likely to use when driving to your facility. Decide which intersections will include signs. Determine where in the intersections the signs will be most visible. Stand on the street opposite the worship gathering facility. Determine how much signage you'll need to make the entrance to the parking lot obvious, as well as where the main entrance to the facility is. Create a paper or <a href="https://mymaps.google.com">digital map</a> that marks where the signs should be set up each weekend. This action is completed when you have developed the map of sign locations. |  | 172 | 7 | 2015-02-03 05:00 | 2021-04-19 04:00 | 2000-01-01 05:00 | template: standard 2017-05-23 updated content --pb 2018-06-27 additional resources subsection added --pb 2020-01-13 content updated --pb 2020-12-16 changed Due in # Days from 196& to 186 --pb&
379 | 813 | 808 | Finalize the equipment list | Settle on the final list of equipment you will order. | You've worked up a rough draft, modified it and gotten quotes from vendors. If you're working with an equipment package vendor, you have probably gone back and forth on the quote a few times, adding and removing things. Now is the time to finalize all of that so you don't run out of time to order it. | Combine all equipment needs into one comprehensive list. Include purchase prices and lead times. Prayerfully finalize the list and begin ordering (see subsequent PlanterPlan tasks). This action is complete when you have distributed the finalized equipment list. |  | 151 | 14 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 content updated. --pb& 2020-01-20 content updated --pb 2020-12-16 changed Due in # Days from 182& to 186& & Duration from 7 to 50& --pb&
380 | 814 | 808 | Purchase equipment | Order all of the equipment in time for it to arrive for the dry run/practice service. | Some items, especially sound equipment, will take longer than others to get in-hand. Because it's expensive, you'll be tempted to wait until the last possible moment to order it. Don't! Unforeseen circumstances could set you up for an Opening Day catastrophe. Subtasks that follow will walk you through: soliciting donations through an online gift registry purchasing the audio/visual/lighting (AVL) equipment purchasing other non-AVL equipment for various ministries purchasing a presentation computer and software purchasing outdoor and indoor signs | Starting with your finalized equipment list, work through each of this task's subtasks. This action is complete when you have completed each of the subtasks that follow this task. |  | 260 | 200 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 content reviewed --pb& 2020-01-20 content updated --pb 2020-12-16 changed Due in # Days from 161& to 166& & Duration from 14& to 30 --pb&
381 | 818 | 814 | Solicit donations through online gift registry | List items you need in an online gift registry and invite everyone you know to purchase something off the list. | If you've ever done a baby registry or bridal/wedding registry, you know how this works. All of the major retailers provide this functionality, so all you have to do is build your list and then get it out there. As you build your registry, be sure to include both big-ticket items as well as $10 and $20 items. Your donors will self-select what they're passionate about and what they can afford. Be sure to put the list especially in front of your contacts at churches that declined to financially support you. Often, they wanted to support you but just didn't have the resources. And just as often, they figure out a way to spring for a portable crib or a subwoofer. Also be sure to put the list in front of your contacts at churches that have already supported you. They have skin in the game and want to see this new church started well. Lastly, include your Launch Team members on your distribution list. It's a great way for them to participate and increase their ownership. Email it out. Put it on social media. Text and call. And pray. | Create a registry or wish list at your favorite online retailer. Add an array of items from the finalized equipment list to the registry. Publish and promote the list. This task is complete when your first registry item is delivered to your home or office. |  | 166 | 30 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 content & hyperlinks updated --pb& 2020-01-20 content updated --pb 2020-12-16 changed Due in # Days from 180& to 183 --pb&
382 | 819 | 814 | Purchase AVL equipment | Order the AVL equipment earlier than you think you need to so that you get it all in time for the dry run/training event. | Contact your AVL equipment vendor(s) and officially place your orders. You will have to pay some or all of the invoice up front. | Order the AVL equipment from your finalized list to arrive before the dry run/practice service (see subsequent PlanterPlan task). Pay the required portion of the invoice up front. Confirm delivery dates and address. This action is complete when the AVL equipment is in hand. |  | 183 | 30 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 content updated --pb & 2020-01-20 content updated --pb
383 | 820 | 814 | Purchase non-AVL equipment | Purchase everything else from the finalized equipment not already donate through the registry or ordered from a vendor. | If you've contracted with an all-in-one equipment package vendor, these items will have been included in your quote. If you're going DIY, review your finalized equipment list and cross off everything that has already been purchased or donated. Now is the time to order everything that's left so you get it in time. | Figure out what's left to purchase on the finalized equipment list. Delegate items to team leads, launch team members and/or staff. This action is complete when you have submitted the reimbursement requests with receipts for each outstanding item on the equipment list. |  | 183 | 30 | 2015-02-03 05:00 | 2020-01-20 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 content updated --pb& 2020-01-21 content updated --pb 2020-12-16 changed Due in # Days from 224& to 196& & Duration from 14& to 7& --pb 2021-01-18 changed Due in # Days from 196 to 212 & Duration from 7 back to 14 --pb
384 | 834 | 814 | Purchase presentation computer and software | Get the hardware and software you need to project lyrics, announcement, sermon slides, etc. | Hardware If you can swing it, buy a laptop that will be devoted to Sunday projection. If it needs to be a staff computer, be sure to create another user account so that the projectionist doesn't have accidental access to sensitive church files. Whichever you use, disable screen savers, pop-up notifications, and software auto-updates which can interfere with a smooth worship gathering. Portability is key. It's going to be traveling quite a bit whether it's between the worship facility and a staff member's home or packed into the equipment trailer. Setting up a whole desktop computer station each week isn't realistic. Be sure the computer you use has enough power to run the software you choose. You can go to each vendor's site and find their hardware requirements. Also consider the computer's output: if your projector is VGA but the computer only has an HDMI out port, you're going to need some kind of adapter. Software Here are common apps designed specifically for church projection: Up-front Purchase: <a href="https://renewedvision.com/propresenter/">ProPresenter</a> <a href="https://mediashout.com/">Mediashout</a> <a href="https://www.easyworship.com/">EasyWorship</a> Subscription-based: <a href="https://faithlife.com/products/proclaim">Proclaim</a> Involve your worship leader and/or tech team in choosing the software. This is a great place to honor your volunteers by letting them use what they are familiar with (as long as it can handle what you need from a production standpoint). | Pick your presentation software. Purchase a computer to run the presentation software. Load the presentation software on the computer. This action is complete when you have purchased the presentation software and loaded it on the presentation computer. |  | 183 | 30 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-27 contents & links updated --pb 2019-07-15 contents updated --pb& 2020-01-21 content & links validated --pb 2020-12-16 changed Due in # Days from 198& to 198 --pb
385 | 734 | 814 | Purchase outdoor signs | Design and order signage that will direct motorist to your parking lot and pedestrians from your parking lot to your main entrance. | Outdoor signage accomplishes many important things: it helps people find your worship gathering location it communicates that you are expecting guests and have thought of them your branding sets a tone for what the worship gathering will be like Design Common options for outdoor signs are: flag-style banners A-frames vinyl banners yard signs Be strategic about how they'll be designed. Some sign shops will provide free or paid design services, but you may want the designer who created your branding to design them for a consistent look and feel. Important things to consider when designing the signs: the faster the speed limit of the road, the larger the font must be don't put too much on the sign: consider including only the location, directional arrow, web address, and logo be double careful which way the arrows point; double-sided signs will have left-pointing arrow on one side and a right-pointing arrow on the other Ordering Also be strategic about how many you'll order. Usually the price per sign gets cheaper when you order several of the same. And signs have a relatively short lifespan (breakage and theft), so consider ordering an extra sign or two for backup. Keep in mind what kind of base(s) you'll need for the signs: For flag-style banners, grass stakes are convenient, but the property owner may not allow them; and if you live where the ground freezes hard in the winter, you'll have a challenge For flag-style banners, cross bases are multi-purpose but provide less stability, especially in windy conditions; get sandbags or similar weights to keep the signs where you want them spinning bases for either of the above helps with breezes, but may also turn the banner in the wrong direction A-frames are a highly effective, low-cost option, but also prove to be stolen the most; high winds may still knock these over | Watch the Passion for Planting training video "<a href="/resources/item/238">Utilize Signage</a>" featuring Ed Stetzer. Decide which and how many signs to put outside your facility. Compare sign company pricing. Order and design the signs. Follow up, follow up, follow up. Make sure the signs will arrive before they are needed. The sign industry is notorious for missing deadlines. This action is complete when you have approved the final designs and the signs are in production. | <a href="https://www.executivepastoronline.com/follow-the-signs/">Follow the Signs!</a> by ExecutivePastorOnline.com | 186 | 14 | 2000-01-01 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-23 updated content --pb& 2020-01-13 content updated --pb 2020-12-16 changed Due in # Days from 196& to 186 --pb&
386 | 735 | 814 | Purchase interior signs | Design and order indoor signage that will give people directions and make them feel like less of an outsider. | Remember the last time you walked through an airport under construction or had to follow a driving detour and you got lost because the signage was vague, missing or misleading? How did that make you feel? You can't overlook interior signage. We get so familiar with our own facilities, we think it's obvious where everything is. Always look at your signage from the perspective of the first-time guest. Remember what it's like to feel like an outsider. Good interior signage puts guests at ease. At a minimum, you'll need signs that: point to the children's area (if you have one) mark the welcome/information table (or similar) point to the main service provide directions to the restrooms Put out enough signs that at least one sign can be seen from any given spot in your usable common areas. | Become familiar with the flow of your facility: Where do/would people tend to go first naturally? Which rooms are hard to find? What hallway is long enough to create ambiguity as to where the room at the other end is? Is the facility's native restroom signage large enough to be clear & effective? Decide which and how many signs to put out inside your facility. Compare sign company pricing. Order and design the signs. Follow up, follow up, follow up. Make sure the signs will arrive before they are needed. The sign industry is notorious for missing deadlines. This action is complete when you have your indoor signage in hand. |  | 186 | 14 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-06-05 content & links validated --pb 2020-12-16 changed Due in # Days from 238& to 235& & Duration from 150& to 114& --pb&
387 | 1298 | 808 | Add equipment and trailer to insurance policy | Add newly purchased equipment and transportation to the insurance policy so that they're covered in the event of a loss. | One church planter showed up to the RV storage lot on Sunday morning to find that the church's trailer full of equipment had been stolen. What a rough way to start a Sunday! But it got worse. He called the insurance company to file a claim, and all they could say was, "What trailer?" That was the moment the planter remembered that he'd never circled back and added it to the insurance policy. The insurance had been purchased months before when finalizing the facility lease. Increasing your replacement coverage is an easy phone call to your church insurance agent. Including a truck or trailer (anything with a VIN) will require adding an auto policy to your church insurance, which is also usually easy to do. Be sure to ask your agent about whether the contents in the trailer are covered for loss while in transit. Some insurance carriers may require you to purchase an "Inland Marine" rider for that. | Call your insurance agent and let them know about your recent purchases. Provide invoices or other documentation to substantiate the replacement value. Get the policy change in writing. Don't forget to pay the premium increase! This action is complete when you get written confirmation that the equipment and trailer are now covered by your church insurance policy. | <a href="https://www.churchplantingtactics.com/insuring-church-plant-trailers/">Insuring Church Plant Trailers</a> on churchplantingtactics.com | 196 | 7 | 2019-11-01 04:00 | 2020-01-21 05:00 | 2000-01-01 05:00 | template: 2019-12-10 date fields found empty 2019-12-11 date fields re-entered manually --pb 2020-12-14 changed Duration from 7 to 14& --pb&
388 | 821 | 808 | Conduct a dry run prior to first preview | Stage, assemble and test all of the equipment to be ready for the first preview service (worship gathering). | After you order all of your equipment, you have to assemble it and practice setting it up the first time. A dry run or practice service is that event. Have no expectation that you'll run an actual worship gathering. Just have everyone show up and learn how to set everything up and plug everything in. Be sure that everything is practiced once, from AVL to signs to coffee pots to whatever. Of course, you can break for a minute and offering a devotional thought, cast vision and/or sign a song. But the setup will take twice to three times as long as normal, so don't try this the morning of your first preview service. While you're at it, assign someone on each team to label and/or color code things to make the weekly set up easier. Buy a label maker, different colors of duct tape, and different colored permanent markers. | Plan a date and book a facility for the dry run. It's best if you can be in your same facility where you'll gather for worship. Invite everyone on your Launch Team to come, even if they won't have anything to do with set up most weeks. Cross-training is invaluable. Get all of the equipment there. Unwrap and unbox items as much as you can ahead of time. Put it all together and test to make sure it works. Jot down all of the things you need to buy to fill any gaps. This action is complete when you have staged, assembled, and tested all of the ministry equipment. |  | 212 | 14 | 2015-02-03 05:00 | 2021-01-18 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 content updated --pb& 2020-01-21 content updated --pb 2020-12-16 changed Due in # Days from 224& to 219& & Duration from 14& to 7& --pb&
389 | 822 | 808 | Make sure equipment fits into storage space | Make sure everything fits into the rolling carts, and that the carts fit into your trailer or truck. | If you've purchased an equipment package from an all-in-one vendor, this has been done for you. If you've piece-mealed your package together and ordered or built your own rolling carts, you have to make sure they accommodate all the rest of your equipment. And you have to make sure your rolling carts actually fit into whatever your larger storage is: typically a trailer, a box truck or an on-site closet. Real-World Woes One planter had been stockpiling all of the equipment in a storage unit as it came in. But when he finally moved the equipment from the storage unit into the trailer, it didn't fit. He had to purchase a bigger trailer (and lose money on reselling the first one), or buy a second trailer (and try to find more volunteers to tow it every week). Another planter measured the trailer that was given to the church and ordered custom-made rolling carts based on measurements he took. Unfortunately, he hadn't taken into account that as the carts roll up on a slanted ramp, they're taller that when they're on a flat surface. He'd ordered them too tall! They wouldn't actually load onto the trailer. So he had to re-order new carts or order a different trailer, either of which costs thousands of dollars. | Make sure you have all of your equipment at the dry run/practice service (see previous PlanterPlan task). After tearing it all down, load all the equipment into the appropriate bins, totes and rolling carts. Load the trailer or storage unit to be sure all of the carts fit. This action is complete when you have fit all of the equipment into its carts and fit the carts into your storage. |  | 219 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2018-08-21 shortened name --pb 2020-12-16 changed Due in # Days from 245& to 211& & Duration from 45& to 52& --pb&
390 | 693 | 1413 | Milestone: Determine Assimilation Strategy | Create a system for intentionally getting people relationally connected and sold out to the vision of the church. | The assimilation process can make or break a new church in the first few years. The excitement and novelty of a brand-new church will draw more guests than perhaps at any other time in the life of a congregation. The guests need to make friends and catch the vision. If you don't get them connected, they'll keep moving and you will have lost precious opportunity. This milestone will walk you through setting up a written strategy to facilitate and reinforce the assimilation process. |  |  | 181 | 150 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated, audience changed to coach --pb 2019-01-11 Due in # Days corrected from 28 to 138 --pb 2012-12-02 content updated --pb 2020-12-16 changed Due in # Days from 138& to 141 --pb& &
391 | 1213 | 693 | Read this assimilation overview | Brief yourself on what goes into an Assimilation Strategy and the process you'll follow to create one. | Assimilation is the process where someone moves from being your guest to being an active participant in the life of the church. An assimilation strategy is designed to move people forward along a clear, simple process to get and keep them connected to your church community. There will be a lot to think through and work through, but the goal is to have a process that is easy to understand with uncomplicated next steps. If it's confusing, they won't know what to do, what's expected, or (more importantly) how to get others to come along the path, too. The 'Why' Are they visitors or guests? Your answer will determine much of how you approach assimilation. Everyone who shows up is coming from a different place. They may be in a great season of life or really hurting. Develop the attitude that anyone who comes to the new church is under the church's spiritual care. Simply sending a newcomer a welcome letter will not cut it. You need repeatable processes that create opportunities to learn people's stories and help them connect relationally. Prepare for the Spike In the first few weeks, the you should see lots of first-time guests. You'll spend a disproportionate amount of time in the first few weeks following up with new people. The tasks in this milestone will help you put together a team to help. You will also need to prepare sermons and creative content ahead of time so you have extra bandwidth. Keeping Everything Straight If you're following up with 5 families, you can probably just remember all that in your head. But if you have 30 or even 50 families, that system will come down like a house of cards. Your team members won't be able to share the load and new families will fall through the cracks. This Milestone The tasks in this milestone will walk you step-by-step through crafting an assimilation strategy that makes sense for your church. Your assimilation strategy will contain: A system for getting guests connected into both a group and a serving team A process for getting contact information so follow-up can happen Benchmarks for measuring effectiveness | Read the brief description above. Read one or more of the Additional Resources listed below. This task is finished when you've read the content above and at least one additional resource. | <a href="https://www.gregcurtis-assimilation.com/blog/2017/1/11/the-first-principal-of-assimilation">The Four Ingredients of an Assimilation Strategy</a> by Greg Curtis <a href="https://www.visionroom.com/4-areas-drive-effective-church-assimilation/">4 Areas That Drive Effective Church Assimilation</a> by Auxano's visionroom.com <a href="https://thomrainer.com/2014/01/6-ways-to-evaluate-your-churchs-strategy-to-assimilate-new-believers/">6 Ways to Evaluate Your Church's Strategy to Assimilate New Believers</a> by Thom Rainer --> <a href="https://a.co/d/e2qU9yC">Church Growth Flywheel: 5 Practical Systems to Drive Growth at Your Church</a> by Rich Birch <a href="https://a.co/d/iuV95c1">People are the Mission: How Churches can Welcome Guests without Compromising the Gospel</a> by Danny Franks | 135 | 1 | 2018-08-28 04:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: 2018-10-12 new task --pb 2019-12-10 date fields found empty 2019-12-11 date fields re-entered manually --pb & 2019-12-20 content updated --pb
392 | 694 | 693 | Call your coach about assimilation | Open a conversation with your coach about getting people plugged in to the life of your church. | Assimilation is an important strategy for connecting people with God and growing the church. Discuss assimilation with your coach and get their feedback. Sample issues to process with your coach: Gauging where people are at spiritually and crafting next steps The relationship between assimilation and disciple-making Typical process breakdown points Keeping track of everyone Keeping the follow-up system relational Activating benchwarmers | This action is complete when you have called your coach about assimilation. |  | 141 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 changed plan to strategy --pb 2017-12-26 content updated --pb 2018-05-15 additional resources subsection added --pb 2018-06-01 gdoc template added --pb 2020-12-16 changed Due in # Days from 143& to 155& & Duration from 7 to 14& --pb& 2018-11-16 content updated to match Greg Curtis' content in our strategy template; moved additional resource to task #780 --pb 2012-12-02 content validated --pb
393 | 695 | 693 | Craft an Assimilation Strategy | Write down specific strategies toward a repeatable process that gets people plugged in to the life of the church. | People don't intrinsically know how to get plugged in to the life of your church. In too many churches, the regulars don't even know how to tell a guest what they can do to get connected. A clear, intentional strategy can keep things simple for your guests and empower your regulars to help others get connected. Using the Assimilation Strategy Template (<a href="/resources/item/320">MS Word</a> or <a href="/resources/item/381">Google Doc</a>), you will work through the following: A system for getting guests connected into both a small group and a serving team A process for getting contact information so follow-up can happen Benchmarks for measuring effectiveness | Download Passion for Planting's Assimilation Strategy Template (<a href="/resources/item/320">MS Word</a> or <a href="/resources/item/381">Google Doc</a>). Work through the content above and subsequent PlanterPlan subtasks; record your thoughts & decisions in the template. Finalize your Assimilation Strategy. Send the completed Assimilation Strategy to your coach for feedback. This action is complete when you have submitted your written Assimilation Strategy to your coach. |  | 181 | 150 | 2000-01-01 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-26 content updated --pb 2018-04-20 moved to Implement Assimilation milestone --pb 2018-10-12 outdented from child to parent task --pb 2019-12-05 content and links validated --pb 2020-12-14 changed Due in # Days from 133& to 74& & Duration from 14& to 30& --pb& 2021-10-05 content updated --pb 2022-11-03& Added church planter discount link to Planning Center option -- NZ 2022-11-21 update links --sc &
394 | 780 | 695 | Design the "One Place" for guest connections | Create a central location for guests to turn in connection cards and get more information about next steps. | Through the announcements, handouts, your greeters and the connection card itself, there should be exactly One Place you direct guests to go so they can turn in their connection card and get information about the "One Program" (see subsequent task). Consider what kind of gift you might hand out as people turn in their connection cards. Make it desirable and something that connects with your church's values. When designing the "One Place", take aesthetics into consideration. You will want it to communicate a welcoming environment that people feel comfortable approaching. Have a table with a huge banner or a pop-up tent (or the like) and use signage to clearly communicate the location of the One Place. It should be obvious to newcomers where to go for getting connected. Choose your best greeters (people with a smile who enjoy other people) to staff the One Place. Train them to explain the One Program and warmly invite guests to attend to get information and ask their big questions. Challenge them to have a super-high collection rate for the connection cards - if the cards don't get turned in, following becomes nearly impossible. | Design a welcoming environment and give it a name (ex: connection tent, info table, etc). Strategize what signs you'll need to draw attention to the One Place. Choose and/or prepare the gifts that will be provided to guests. Determine how you'll train your best greeters to staff the One Place. This action is complete when the One Place has been designed. | <a href="https://s3-us-west-2.amazonaws.com/church-marketing-university/CMU_Guest-Gift-Guide_V1.pdf">Guest Gift Guide</a> on churchmarketinguniversity.com | 155 | 14 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-06-07 content updated; generational/cultural reference to Seinfeld removed --pb 2020-01-17 content updated --pb 2020-12-14 changed Due in # Days from 224& to 228& --pb& 2021-03-26 additional resources subsection added --pb
395 | 681 | 695 | Create the "One Program" event for guest connections | Brand your "One Program" guest connections event and craft a plan for what to say and do at the event. | Even though you've posted mission & vision on your website and share it from the platform, people still benefit from interacting with the story and details of the church in a relational environment. And people will have questions about theology or practice or all kinds of things. A group event allows you to lead through all of that and get the newest people to meet each other. It's been called different things over the years: Welcome to ChurchName ChurchName 101 Making ChurchName My Home Pizza with the Pastor Next Steps with Steve ...and the list goes on And it has taken lots of formats, too: a 1-hour seminar with Q&A a catered half-day event a structured but casual group conversation over a meal a 15-minute high-energy 'party' immediately following the worship gathering ...and again, the list goes on Now is the time to make those decisions, develop the content and get the first one on the calendar. Most of all, you want to have clear ways for the attenders to get further connected to the church. These will be the "Two Placements" in your Assimilation Strategy , typically somewhere they can find community and somewhere to serve and use their gifts. | Determine the aim and desired outcomes of the event. Decide on a format. Choose a name for the event. Include this "One Program" in your Assimilation Strategy Template . Put the first event on the church calendar and publish it to where it can be found. Create speaker's notes, slides, handouts, workbooks, and/or anything you'll use at the event. This action is complete when the content and resources for the event have been finalized. |  | 155 | 14 | 2015-02-03 05:00 | 2021-07-27 04:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content updated --pb 2019-12-03 content updated --pb 2020-12-14 changed Due in # Days from 161& to 74& & Duration from 7 to 14& --pb&
396 | 1251 | 695 | Determine the "Two Processes" for connecting guests | Create a clear step-by-step plan for moving guests from showing up at the "One Program" to both community and Christian service. | Once guests to your church have participated in the "One Program", you'll want to quickly move them into community and service environments which will relationally connect them to your congregation. People are wired up differently and have different life circumstances, so they might do not pursue both initially. Ultimately, you want dual placement for every guest, but getting them connected to one of the two is a huge step in the right direction. So, you need one process that will help people get plugged in to whatever your group structure is (see PlanterPlan task <a href="/projects/project-tasks/[[project_id]]/all-tasks/670">Issue Written Groups Strategy</a> for more). Your process might include emails, phone calls, texts and/or handwritten notes, etc. You also need one process that will help people get plugged in to a serving team (see PlanterPlan task <a href="/projects/project-tasks/[[project_id]]/all-tasks/740">Develop a Leadership Matrix for Opening Day</a> for more). Again, your process must include specific followup steps your teams take to invite people to explore and participate. For both processes, you need to include every step your team(s) will take, from data entry to communicating with the guests. All communications need to make it abundantly clear what simple next step you're asking the reader/listener to take. If it's confusing, they'll be much less likely to take any step. Err on the side of too much follow-up. It can take people hearing the call to action several times before it really registers and they take that simple next step. Don't assume because you've emailed them once that they 'get it'. Your plan should be politely and lovingly persistent. | Review your church Strategies , developed in a prior PlanterPlan task, to make sure your "Two Placements" agree with your Vision Frame. Hammer out a process for each of the "Two Placements" and include the details in your Assimilation Strategy Template . This task is complete when you have detailed processes that include specific steps with deadlines and who's doing each step. |  | 155 | 14 | 2000-01-01 05:00 | 2021-07-27 04:00 | 2000-01-01 05:00 | template: 2018-11-19 new task --pb 2019-12-05 content updated --pb
397 | 697 | 695 | Set assimilation benchmarks | Choose measures that will reveal the effectiveness of your Assimilation Strategy and set numeric expectations. | You need an easy way to track assimilation at your church. It's imperative that you have your finger on the pulse of how things are working because it affects people. And you need to be able to spot breakdowns so that they can be fixed. What percentage of your guests next year will get placed into a group or serving team? Both? How would you even know? You'll need to record guests in your church management software. You'll also need to keep track of who participates in each small group and serves on each ministry team. Then you'll be able to pull reports that reveal your single and dual placement rates over any given time period. What percentages will you strive for? How will you communicate that to your Followup Team and inspire them toward it? Something else worth measuring is how many new believers stay connected. If half of people who say 'yes' to Jesus have left your church within 6 months, you've got an urgent opportunity to fix something. | Set numeric goals for the percentages of single and dual placement of guests. Figure out how to use your ChMS to track and report your placement percentages. Make someone the owner of collecting the data and creating regular reports. Include these details in your written assimilation strategy. This action is complete when you have set assimilation benchmarks. |  | 155 | 14 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2018-11-19 content updated to match Greg Curtis' assimilation content and our new strategy template& --pb 2012-12-02 content updated --pb 2020-12-16 changed Due in # Days from 150& to 162 --pb&
398 | 698 | 693 | Coaching Checkpoint: review and affirm Assimilation Strategy | Review the planter's Assimilation Strategy document and provide feedback on the ideas for getting people relationally connected to the new church. | The planter has prayed and thought through effective strategies for following up with guests and getting them plugged in to the life of the church. Those strategies, tools and goals will be compiled into an Assimilation Strategy document, which should include: Design for the "One Place" guests will be directed to turn in their connections cards (info booth or the like) Plan for the "One Program" events where guests will get more information and be invited into next steps Steps for the "Two Processes" the church will use to get guests connected into a group and a serving team Benchmarks to know whether guest connections are happening | Review the planter's written Assimilation Strategy. Affirm that the strategy for following up with guests is practical and sufficient. Provide other feedback to the planter as appropriate. This action is complete when you, the coach, have reviewed and affirmed the planter's Assimilation Strategy. |  | 162 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 changed plan to strategy --pb 2017-12-26 content updated --pb
399 | 699 | 1413 | Milestone: Implement Assimilation Strategy | Pull the trigger on the strategies you laid out in the previous Milestone to develop repeatable processes for getting people plugged in to your church. | Now that the assimilation strategy has been carefully crafted to consider the various entry points, kinds of people showing up, and how to follow up with each, it is time to recruit and empower a team to execute the strategy. |  |  | 181 | 150 | 2015-02-03 05:00 | 2017-12-26 05:00 | 2000-01-01 05:00 | template: standard 2017-05-19 changed plan to strategy --pb 2019-12-03 additional resources subsection added --pb 2019-12-05 content validated --pb 2021-01-28 content updated --pb
400 | 701 | 699 | Build out followup processes in church management software | Customize the church management software settings and infrastructure so that it is ready, then empower and train your key leaders to use it. | Your church management software (ChMS) is powerful and solves many challenges of a new church that doesn't have a physical church office. If all you do with the ChMS is keep contact information, you have a very expensive address book on your hands. Recruit someone to be your ChMS champion and empower them to spend time setting it up the way your church will use it. ChMS solutions aren't written only for church plants, so there will be features that you will use, and some you won't (like room and equipment reservations). At a minimum, you need to set up the following processes: Assimilation Processes - Take the assimilation strategy and incorporate it into the ChMS. Its workflow or process queues will prompt you to take next actions steps to follow up with guests and new members. Small Groups Processes - Each small group should be entered into the ChMS. Record key information such as group leader, participants, time of meeting, and meeting location. In addition, develop a process to follow up with people that expresses interest in small groups. Ministry Team Processes - Each ministry team should be entered into the ChMS. Record key information such as team leader, serving roles, team members, etc. In addition, develop a process to follow up with people that expresses interest in serving on that team. Church Calendar - All of the events from the various groups, teams and worship gatherings should roll up to one master church calendar. Figure out how this calendar will get used in conjunction with the church website calendar and any other publicly published calendars. You will also need to create user accounts for other staff and key volunteer leaders. Your ChMS will allow you to grant them various levels of access to different parts of the software. For instance, not every leader needs access to financial records and giving history. Lastly, you'll need to introduce them to the tool and make a case for why it's important to use. Give them some pointers on how to use it and make sure they know where the help files and training videos can be found so they can train themselves further. | Set up assimilation processes in the ChMS, including followup for groups and ministry team interest. Configure the master calendar. Create other users and grant them appropriate levels of access. Provide them live training or point them to help files for their areas of responsibility. This action is complete when other users have begun using the church management software. | <a href="https://churchmarketinguniversity.com/church-email-funnels/">Next Step Funnels</a> on churchmarketinguniversity.com | 171 | 14 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-26 content update --pb 2018-01-17 new blog resource link added --pb 2018-11-19 content updated --pb 2019-12-05 content updated --pb 2020-12-16 changed Due in # Days from 168& to 171 --pb
401 | 702 | 699 | Develop a connection card | Draft and print a communication card to be used at worship gatherings as a key element of the assimilation strategy. | The connection card (AKA communication card, welcome card) is an important tool in the followup process. If you don't collect contact information, you won't be able to follow up with guests. Have an intentional plan for getting the card into everyone's hands at each worship gathering along with a pen for filling it out. What to Ask For Be sure to only include information on the card that you are going to use. People are more sensitive to privacy concerns and and increasingly hesitant to disclose every bit of information you may be asking for. Place the most important information on the card at the top. Consider adding a check box for 'new contact info' so that regulars don't feel obligated to fill out the entire card each week. Common connection card elements are: Name Mobile number Email Address Next steps Prayer Request | Read the brief post <a href="https://chucklawless.com/2015/08/why-i-may-not-fill-out-a-visitors-card-in-your-church/">Why I May Not Fill Out a Visitor's Card in Your Church</a> by Chuck Lawless Decide what elements to include on the connection card. Design the connection card. Print the connection card. This action is complete when the connection cards have been printed. | <a href="https://www.nucleus.church/blog/church-connection-card-examples/">7 Perfect Church Connection Card Examples</a> by ProChurchTools <a href="https://www.evangelismcoach.org/8-church-connection-card-templates/">8 Church Connection Card Templates</a> by EvangelismCoach <a href="https://churchmarketingsucks.com/2014/10/church-visitor-cards/">Church Visitor Cards: How to Connect & Follow Up</a> by ChurchMarketingSucks | 171 | 14 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-26 content updated --pb 2018-11-19 content updated, title changed from "Schedule Post-launch Newcomer Gatherings" --pb 2019-12-05 content validated --pb
402 | 700 | 699 | Write guest followup communication templates | Write out what each email, text, letter and phone call should say so that followup communication is ready to send. | One of the first things your Connections Team should do to build out the assimilation strategy is to write the copy for each planned followup communication. That way the system is ready to fire when they begin practicing followup on guests. They should be practicing on people that show up to launch team meetings and preview services. The church management software (ChMS) you chose may have placeholder text or factory default messages, but they'll need tweaking before they're ready to go out. Don't make the mistake one planter did when the very first guests at their preview services got followup emails that said, "Thanks for visiting NameofChurch. Sincerely, NameofPastor." Wherever possible, include merge fields in the correspondence. That allows you to press send once but each recipient on the list gets an email, text or letter with their first name on it as if it had been personalized to them. Check your ChMS or communication software's help files and test, test, test. Include a Call to Action Each communication, whether it's an email, text, phone call or whatever, should focus on getting the reader to take one clear next step. That could include: Follow us on social media Let us know how we can pray for you Come to our newcomers event Leave us an online review Come back next Sunday You get the idea. If you include more than one call to action, chances plummet that they'll take any action at all. Keep it to just one. | Write the copy for each followup text, email, letter and phone call specified in the Assimilation Strategy. Review each to make sure it's written with the audience in mind. Review each to make sure appropriate merge fields are included for a personal touch. Send yourself or a teammate a test of each followup message; review and adjust the templates as necessary. This task is complete when all of the followup communication has been written and each communication channel has been tested. | <a href="https://church-marketing-university.s3-us-west-2.amazonaws.com/Church-Email-Funnels.zip">Church Email Funnel [templates]</a> from churchmarketinguniversity.com | 171 | 14 | 2015-02-03 05:00 | 2021-01-28 05:00 | 2000-01-01 05:00 | template: standard 2017-12-26 content updated --pb 2018-11-19 title changed from "Implement Church Mgmt System" --pb 2019-12-03 additional resources subsection added -pb 2019-12-05 content updated --pb 2020-12-16 changed Due in # Days from 168& to 171 --pb&
403 | 1419 | 699 | Set up kids' pre-registration on website |  |  |  |  | 181 | 14 | 2021-01-15 05:00 | 2021-01-15 05:00 | 2000-01-01 05:00 | template:
404 | 1252 | 699 | Write scripts for announcing guest connections | Decide in advance what & how you'll announce the connection cards and the "One Place" where guests will turn the cards in. | The connection card is the weakest link in your followup system. If you don't get their contact info, it's going to be pretty hard to follow up. Be sure to ask people multiple times during the worship gathering to fill out the card. Don't make the mistake of only mentioning the card during the opening welcome statement! People will come in late and miss the announcement. Find ways to mention the card three or more times during the gathering. For example, mention the card during the opening welcome, during the sermon, and during the announcement time. Include in your announcement what the church will be doing with the information. Transparency is key to creating trust with the cards. Also give them clear instructions on how and when to turn the cards in at the "One Place". | Review the Assimilation Strategy you created in the previous PlanterPlan Milestone. Consider the typical building blocks of your weekly worship gatherings to determine strategic times to announce the connection cards and the "One Place". Write at least 2 different scripts for stage announcements and make sure they get to the person doing the announcements. This task is complete when you have finalized at least 2 announcement scripts for the guest connection process. |  | 178 | 7 | 2018-11-19 05:00 | 2019-12-05 05:00 | 2000-01-01 05:00 | template: 2018-11-20 new task --pb 2019-12-05 content updated --pb 2020-12-11 changed Due in # Days from 52& to 159 --pb&
405 | 703 | 699 | Get recurring "One Program" guest connection events on the calendar | Calendarize the "One Program" events that will create easy onramps to your church for guests. | The "One Program" events you dreamed up in your Assimilation Strategy will remain a dream until they get on the church calendar. Plan a rhythm, like second Sundays, so that everyone can count on when the next event will be. It's also important to get the calendar events published online where people can find them for reference/more information. Consider inviting a few of your regulars to show up to each event as bridge-builders. | Put several meetings on the calendar in the first few weeks after launch. Put more meetings on the calendar with regular recurrence: once a month, every-other month, etc... Invite a friend to find the events online to test their accessibility. This action is complete when an ongoing schedule of "One Program" events have been added to the church calendar. |  | 181 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-22 content & resource links updated --pb 2020-12-16 changed Due in # Days from 217& to 151& & Duration from 180& to 30 --pb & &
406 | 823 | 1413 | Milestone: Prepare for Teaching and Preaching | Create sermon prep systems and plan ahead for both sermons series and individual sermons. | This milestone will walk you through planning months worth of sermon topics at a time and challenge to completely prep your first sermon series well in advance of Launch Sunday. |  |  | 260 | 200 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-28 content overhauled --pb 2018-07-30 new resource link added --pb 2020-12-16 changed Due in # Days from 217& to 160& & Duration from 7 to 1& --pb & & 2020-01-24 content validated --pb
407 | 824 | 823 | Read this teaching and preaching overview | Brief yourself on what goes into sermon planning and writing that reaches the unconvinced. | According to a <a href="https://news.gallup.com/poll/208529/sermon-content-appeals-churchgoers.aspx">2017 Gallup poll</a>, the top 2 reasons people attend churches are: sermons that teach scripture sermons that connect religion to real life Preaching matters. "&hellip;those for whom sermons were being dumbed down aren't dumb. They are interested in the truth or else they'd be out golfing." -Ed Stetzer Preaching to the Unconvinced Church plants should be full of people who don't necessarily buy in to this whole 'God thing'. Preaching with this in mind requires an awareness and sensitivity that many pastors have not yet developed. In the video below, Dr. Ed Stetzer has some great thoughts to help you understand how you can prepare to reach the disconnected and introduce them to Jesus Christ. <a href="https://multiplication.org/product/preaching-to-the-unconvinced/">Preaching to the Unconvinced</a> by Vince Antonucci on Exponential.org <a href="https://multiplication.org/product/sermons-for-the-unconvinced/">Sermons for the Unconvinced</a> by Vince Antonucci on Exponential.org <a href="https://outreachmagazine.com/features/18123-preach-for-seekers-without-dumbing-down.html">Seeker Comprehensible Preaching&hellip; Without Dumbing Down</a> by Ed Stetzer on ChristianityToday.com <a href="https://careynieuwhof.com/episode197/">How To Preach In A Way That Reaches Unchurched People And Maintains Biblical Integrity</a> on CareyNieuwhof.com Styles of Preaching And God has placed within you a teaching style which is unique to you. But be sensitive to the people God brings to you and leverage your style to maximize the impact you have. <a href="https://www.propreacher.com/5-styles-of-preachers/">The 5 Styles of Preachers - Which Are You?</a> on ProPreacher.com <a href="https://churchleaders.com/pastors/pastor-articles/162679-11-kinds-of-preacher-which-one-are-you.html">11 Kinds of Preacher: Which One Are You?</a> on ChurchLeaders.com Sharing Ministry You need to plan your sermon topics out months in advance and begin drafting each sermon weeks in advance. When you do that, you reduce panic and 11th-hour just-barely sermons. You also let others participate in the worship planning process, giving them time to give their best on song slides, videos, music practice, etc. You also need to prepare ahead in a special way for the Launch. The first several weeks after launch will be very busy like no other time in the life of your church. You're going to need the extra bandwidth for bolstering team leaders, following up with the flood of guests, and counseling hurting people (among other things). Writing your entire first sermon series well in advance and then brushing it up in the week leading up to preaching it will give you some extra breathing room. Preaching in an Age of Tech Another thing you need to be aware of as you plan sermons is that everyone who comes has access to the sermons of all the best preachers in the country. Don't feel like you have to compete with or mimic them, but know that the bar is set high, so continue to grow in preaching with excellence. Also know that with smart phones in hand during the sermon, they can fact check your claims while you're still preaching. Be sure you've done your homework and checked your own facts. | Familiarize yourself with the topics above. Watch the Passion for Planting training video "<a href="/resources/item/213">Prepare for Teaching / Preaching</a>" featuring Ed Stetzer. This task is finished when you've read the content above and the supplemental blogs, and watched the video(s). |  | 160 | 1 | 2000-01-01 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-05-31 content updated, audience changed to coach --pb& 2020-01-24 content validated --pb 2020-12-16 changed Due in # Days from 200& to 166& --pb
408 | 825 | 823 | Call your coach about sermon planning & writing | Open a conversation with your coach about writing sermons and planning a sermon calendar. | Writing sermons is an important part of casting vision and discipling the new church. There are a lot of weekly demands on you. In the early days, you'll often shoulder a greater portion of the work until volunteer leaders are trained and equipped. Because of this reality, it is important to work ahead on your sermon writing. Sample issues to process with your coach: Philosophy of preaching Incorporating your primary gift in your preaching Beliefs about the power of preaching in church planting Creating culture through preaching Which sermon series to launch with How far in advance to plan sermons Creative ways to deliver messages Coordinating your planning with the worship and creative arts teams Protecting your sermon writing time Making your sermons practical Soberly gauging your preaching ability | This action is complete when you have called your coach about sermon planning and writing. |  | 166 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-28 content updated --pb 2020-01-24 content validated --pb 2020-06-26 changed title from "plan first 3 months' sermon topics" --pb 2020-12-16 changed Due in # Days from 231& to 180& --pb
409 | 826 | 823 | Craft a sermon calendar | Well prior to your launch, plan the first 3 months of sermon topics so that you can include others in the process and get ahead of the curve. | As you think through how best to make disciples, cast vision, and develop the culture of the new church, plan out the first 3 months' sermons. The grand opening is a unique time in the life of the church. You never get another chance for this church to be brand new again. So bathe this in prayer, and maybe take a day or two away for planning. Put significant time and effort into your preaching calendar. The first year of the church will determine its trajectory for may years to come. | Contact other planters and your coach about how they cast vision at their grand opening. Brainstorm potential sermon series and topics; keep in mind the season of the church and your Vision Frame. Pray about each series and topic. Using the <a href="/resources/item/355">Preaching Calendar Template</a>, write down the topics for at least the first 3 months. Send the list to your coach and get some feedback. Make adjustments. This action is complete when you have gotten feedback on your schedule of sermon topics for the first 3 months. |  | 180 | 14 | 2000-01-01 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-28 content updated --pb& 2020-01-24 content updated --pb 2020-12-16 changed Due in # Days from 245& to 211& --pb
410 | 669 | 823 | Plan church-wide financial stewardship training/series during the first year | Plan a financial stewardship lesson or series during the first year of the new church to make generosity and giving part of the new church's DNA. | When you do an effective job of reaching people with little or no church background, their giving disciplines won't be fully developed immediately. Helping them grow in generosity and stewardship will help them, and it will help fuel the mission of the church. The members and attenders of this new church should participate in its financial life. Financial stewardship training is a matter of discipleship. Conducting that training during the first year will help the congregation understand the cost of what they are undertaking. It may even be a good outreach event to serve people in your community who are struggling financially. Consider these financial training resources: <a href="https://www.ramseysolutions.com/ramseyplus/organization">Financial Peace University</a> <a href="https://goodsensemovement.org/">Good Sense</a> <a href="https://www.crown.org/">Crown Financial Ministry</a> | Discern the attitude of your congregation about giving. Select an appropriate financial training resource or plan your own sermon series. Put the sermon/training date(s) on the calendar. This task is complete when you have put the first financial stewardship training/series on the church calendar. |  | 180 | 14 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content updated --pb 2018-03-28 content overhauled --pb 2018-05-07 added& google& doc template version --pb 2019-11-26 content updated --pb 2020-12-11 changed Due in # Days from 147 to 60& & Duration from 14& to 7& --pb& 2020-12-22 While merging it with Decide When To Start Groups I cut a couple sentences that didn't seem necessary. --sc
411 | 827 | 823 | Write all of the sermons for your opening series | Finalize each sermon for your first series at least 6 weeks before the Opening Day of worship gatherings. | Be as prepared as possible for the influx of new people to the church. There will be tons of new people to follow up with and connect with. There are few better ways to love those newcomers than to set aside priority time to follow up with them. The best way to make sure you have that bandwidth is writing sermons ahead of time. Whether you manuscript sermons or build detailed outlines, now is the time to do it. Plus, it's a good discipline to write sermons in advance. If you can start with this discipline, it will be easier to keep it going. Avoid short-changing the sermon when busy weeks or crises arise. | Schedule time to write all of the sermons for your opening series. Write them. Send them to your coach and get some feedback. This action is complete when you have written the first sermon series. |  | 211 | 45 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-28 content updated --pb 2020-12-16 changed Due in # Days from 238& to 188& --pb &
412 | 828 | 823 | Coaching Checkpoint: review and affirm sermon schedule | Review the planter's sermon calendar and provide feedback on the appropriateness and pace of the topics. | The planter has prayerfully created a list of sermons for at least the first 3 months of the new church. Review the sermons and provide feedback to the planter. Specifically, the sermons topics should provide opportunity to cast the vision for the new church and to connect well with the planter's context. | Review the planter's sermon calendar. Provide feedback to the planter. This action is complete when you, the coach, have reviewed and affirmed the planter's sermon calendar. |  | 188 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-27 content updated --pb 2020-12-16 changed Due in # Days from 208& to 213& & Duration from 77 to 92& --pb&
413 | 829 | 1413 | Milestone: Develop Worship Planning System | Create systems and structures to foster an engaging worship environment that is attractive to believers and seekers alike. | Putting together worship services for a new church is a prime opportunity for creativity and innovation. You get to "do church" in a way that is informed by your context and your Vision Frame. There isn't yet any "we've always done it that way" resistance. But especially since people on your Launch Team are coming from all different experiences of church, you can't just wing it or fall back on defaults. No one will have the same defaults as you. This milestone will challenge you to create repeatable processes to craft inspiring and spiritually engaging worship gatherings. And it will walk you through some very practical things you'll need to prepare in advance of your preview services. |  |  | 260 | 200 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-27 content updated --pb 2020-01-21 content validated --pb 2020-12-16 changed Due in # Days from 180& to 161& --pb
414 | 830 | 829 | Decide on the worship gathering atmosphere | Choose an intentional mood, tone and environment for your worship gatherings. | The atmosphere of the worship gathering will have a huge impact on how the unchurched feel about the new church, and even how they feel about God. And it plays into how easy or difficult it is for everyone there to connect with God. When you visit someone's home, they can make you feel welcome or unwelcome by the setup of the furniture, the relative cleanliness, and by the things they say and do. Similarly, you need to be conscious of guests and do what makes guests feel comfortable over what makes the church comfortable. This is an important exercise. Most pastors are wired up more for vision, theory and theology, while the majority of the general population is geared much more toward the tangible and sensory. Plan worship gatherings that intentionally engage people on both levels. A lot goes into creating the atmosphere, including: The Physical Environment Each of these communicate in subtle ways whether you've expected guests or not, and whether you expect people to experience God that day or not: Facility layout - space for people to hang out & chat, how chairs are arranged, how the stage is set up Outdoor and interior signage - information and context cues for guests Aesthetics - banners, drapes, backdrops, colors, etc. Lighting Aroma - nightclubs and school gymnatoriums may need a little work Bathrooms - cleanliness, location, comfort Style of Music For both background music and the worship songs, does the music style reflect local culture and preference, or does it reflect a churchy preference? Mood and Tone Through the things you do and say, the atmosphere of the service can be: fun and humorous serious and thoughtful happy and celebratory Warm and emotive etc... Assumptions Through the things you do and say, you also communicate in subtle ways who is 'in' and who is 'out'. If you provide no explanation or context for the things that are done during the worship gathering, unchurched people will be confused at best or made to feel unwelcome at worst. In the same way, the little hints dropped from the platform can be confusing or un-inclusive: "You remember the story of Jesus and the 10 lepers&hellip;" - the unchurched and dechurched probably don't "You know how when you're praying&hellip;" - someone who's never prayed can't relate to this "First Thessalonians 3:12 says&hellip;" - Biblical literacy is very low and some won't know that this is a scripture reference, or even that scripture is broken down into books, chapters and verses Alignment is Key Consider each of these elements and be intentional with each. They should all work together in agreement. How jolting would it be to tell a joke right after a reverent silence cued up by a deep, thought-provoking element? Don't feel locked into one mood, but know that the atmosphere communicates the church's personality and affects how people engage during the gathering. | Describe the atmosphere that would connect best with your community and your average target family. Make intentional decision about each of the items above. Base your initial sermon series and facility layout on those choices. Communicate them to the worship leader and others involved in the creative process. Remind the volunteers and leaders before the service what the feel should be. This action is complete when you have determined the desired worship service atmosphere for the initial services. |  | 161 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-27 content updated, Due in # of Days changed from 208 to 201 --pb& 2020-01-21 content validated --pb 2020-12-16 changed Due in # Days from 208& to 168& --pb
415 | 831 | 829 | Develop framework for typical worship gathering | Decide what will go into the typical order of service so that there's a common understanding and expectation for your teams. | There will be lots of people involved in planning and executing the weekly worship gatherings. Having a standard framework allows more people to be included in the process. You don't want to get locked into doing the same old thing every week, but you also don't want all of your teams left guessing from week to week what they'll have to do. Creating a typical order of service or framework allows you to train your teams, gain efficiencies, and deviate for an intentional purpose. Common elements of a worship gathering include: Welcome Message/Sermon Worship songs Announcements Communion Offering Special Element (video or song) Liturgical Element (responsive reading or scripture reading) Prayer But don't feel locked into only doing these things or having to do all of them every week. | Create a list of all the elements you'll include in the typical worship gathering. Decide how much time you'll typically spend on each element. Share this with the worship planning team so you can develop a weekly service schedule. If you use worship service planning software, have a team member build a template based on your framework. This action is complete when you have finalized the framework of a typical worship gathering. |  | 168 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-27 content updated; due in # of days changed from 180 to 208 --pb 2019-08-19 title changed from "Implement Process for Planning Worship Gatherings" --pb 2020-12-16 changed Due in # Days from 168& to 171 --pb 2020-02-25 additional resources subsection added --pb& 2020-01-21 content updated & links validated --pb 2020-12-16 changed Due in # Days from 208& to 168& --pb
416 | 832 | 829 | Implement collaborative process for planning worship gatherings | Create a system for planning worship gatherings that includes other people and provides enough time for collaboration. | Regardless of what you include in each worship gathering, you need a process in place that includes the worship leader, projectionist, bulletin designer and anyone else involved in preparing various elements and creative aspects of the gatherings. Nothing cripples creativity like having no time to create. The process for planning the gatherings should include ample time for creative elements to be crafted or prepared. Don't wait until Saturday night to provide the sermon topic & notes to the worship leader and the people who will be making up the slides and the bulletin. Create a calendar that plans out your worship gatherings at least 6 months in advance. Then create a rhythm for reviewing the plan at each week's creative team meeting. For example, Community Christian Church outlines in their book, <a href="https://read.amazon.com/kp/embed?asin=B000SEIA2I&preview=newtab&linkCode=kpe&ref_=cm_sw_r_kb_dp_iO4jEbJ0JWK9W">The Big Idea</a>, that each week they: Introduce the sermon series roughly 13 weeks out Plan the gathering that is 9 weeks out Check the status of pieces being created for the gathering 5 weeks out Outline the sermon that is 3 weeks out Review the manuscript of the sermon that is 2 weeks out Put final touches on the gathering that is 1 week out Choose a software tool that supports this process. You could use a collaborative spreadsheet (like <a href="https://sheets.google.com">Google Sheets</a>), but the following solutions make your life easier with song databases, volunteer scheduling and more: Planning Center <a href="https://www.planningcenter.com/services">Services</a> Church Community Builder <a href="https://pushpay.com/product/chms-software/">Schedules</a> Tithely CMS <a href="https://get.tithe.ly/product/church-management">Worship Planning</a> <a href="https://worshipplanning.com">WorshipPlanning.com</a> | Decide how far in advance sermon topics & notes will be provided to others involved in the planning process. Choose a software tool to support the planning process. Schedule a regular creative team meeting and invite contributors. This action is complete when you have planned the the first worship gathering using these new processes. | <a href="https://www.executivepastoronline.com/service-planning-and-design-operating-procedure/">Service Planning and Design Operating Procedure</a> on executivepastoronline.com | 168 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-06-15 content & blog links updated (former post by Furtick expired) --pb 2017-12-27 content re-updated --pb 2018-06-27 new 'additional resource' added --pb& 2020-01-21 content updated & links validated --pb 2020-12-16 changed Due in # Days from 180& to 168& --pb
417 | 833 | 829 | Create an evaluation process for worship gatherings | Create a system to continually improve your regular worship gatherings. | Evaluation is an important part of ministry. Evaluation is the time in where you learn, grow, and better prepare for the next time. Spend time with staff and key leaders every week debriefing the worship gathering. Each element should be evaluated for how well it connected. There is a spiritual element to the worship gathering that must be evaluated as well. Remember that the goal of the worship gathering is to worship God, make disciple and preach the good news to not-yet-believers; it's not to entertain or keep people happy. The result of a solid evaluation process will be a culture of excellence that cares about the quality of the worship gathering. It also reinforces intentionality in the planning process. | Determine the 'win' for a worship gathering. Determine which elements will be evaluated and what questions you'll ask. Create a reusable worship gathering evaluation form. Schedule a regular evaluation meeting and invite contributors. This action is complete when you have invited contributors to the first evaluation meeting. | <a href="https://unseminary.com/4-frameworks-for-church-service-review-meetings-and-20-evaluation-questions/">4 Frameworks for Church Service Review Meetings</a> [Unseminary] <a href="https://chucklawless.com/2022/05/7-ways-to-evaluate-this-past-weekends-worship-service/">How to Evaluate Your Church's Worship Service</a> [Chuck Lawless] <a href="https://careynieuwhof.com/5-pro-tips-on-how-to-get-amazing-sermon-feedback/">5 Pro Tips On How To Get Amazing Sermon Feedback</a> [Carey Nieuwhof] | 168 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-27 content and links updated --pb 2018-02-09 removed link to PCO Project (product discontinued) 2018-04-20 moved Equipment milestone --pb 2020-12-16 changed Due in # Days from 152& to 183& & Duration from 21& to 30 --pb& 2018-08-21 made child/subordinate to 814 --pb & 2020-01-20 content validated, LiveWorship& link removed --pb
418 | 837 | 829 | Design a printed or electronic bulletin | Create a bulletin/program design that will let newcomers know what to expect throughout the worship gathering. | Call it whatever you want, some version of a bulletin is a great way to make guests feel at home. It can also provide them with information about the church and/or upcoming events that may interest them. And it can be a great vehicle for delivering a connection card to everyone. Using a shell allows you to have professional graphics on the cover but print custom content each week. In-House Design Some planters have their graphic designer create a bulletin shell that is a theme for a season or whole year, or one that is simply branded with the church logo. These can be printed in large quantities at a local print shop on online printers like <a href="https://www.gotprint.com/products/brochures/info.html">GotPrint.com</a> Alternatively, you can print the entire program on plain paper in color or B&W each week. The small disadvantage here is that few if any home printers can print to the edge of the paper, so there will always be a white boarder around any artwork. Bulletins that 'bleed to the edge' look cleaner and more professional. Stock Design A great place to order pre-printed program shells is <a href="https://www.outreach.com/Church-Bulletins/">Outreach Marketing</a>. They provide templates for printing your own internal contents each week. Electronic Another option, which can supplement or replace your printed bulletin, is to post it electronically. <a href="https://www.bible.com/events#section1">The Bible App</a> events feature is a great, free tool. There are other tools available, too. The biggest consideration in going digital is helping people find it. Post it on your website as a menu option that redirects to the electronic bulletin and/or make a vanity URL that will redirect over to your bulletin (ex: www.xyzchurch.com/bulletin). You can also experiment with QR codes on announcement slides. Whatever you do, make it short for ease of thumb typing and simple for ease of remembering. | Decide whether or not you'll use some version of a bulletin/program. Decide whether to design or purchase a pre-printed program 'shell'. Enlist the aid of a designer to lay out the internal contents template. Lay out the content for the first preview service. This action is complete when the template has been designed and the bulletins are printed or published for your first preview service. |  | 198 | 14 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2020-01-21 content updated --pb 2020-12-16 changed Due in # Days from 208& to 211& --pb
419 | 1420 | 829 | Get a streaming license | Purchase a copyright license that covers worship music streamed during your online services, honors Christian composers, and keeps your church in copyright compliance. | Rather than the church having to get written permission to perform every piece of music, there are licensing agencies that provide blanket permissions for the church. United States Copyright Law provides that any music (live or recorded) performed during the course of a regular worship gathering (typically Sunday morning, Wednesday night, etc.) is exempt from copyright licensing. However, churches are required to clear the copyrights for any music used outside of worship gatherings. That includes, but is not limited to online streaming of the worship music performed during service . That's right: you can't stream the worship performance from your worship gatherings legally without a copyright license. People watching online aren't technically at your place or worship, so that falls outside of the freedom of religion exemption. Providers we're aware of are: CCLI <a href="https://us.ccli.com/streaming/">Streaming or Streaming PLUS</a> license Church Copyright Solutions <a href="https://christiancopyrightsolutions.com/worshipcast/">WORSHIPcast</a> license | Determine which license(s) you need. Obtain the licenses individually or in a bundle. This action is complete when you have purchased the appropriate license(s). |  | 128 | 7 | 2021-01-15 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template:
420 | 372 | 829 | Get a copyright license for printed music (CCLI) | Purchase a copyright license that covers printed copyrighted material, honors Christian composers, and keeps your church in copyright compliance. | As Christians, it is imperative that we and the church respect copyright laws. A copyright license allows a church to reproduce printed music and lyrics in accordance with copyright laws, and honor our brothers and sisters who have labored to create the music. Rather than the church having to get written permission to use every piece of music, there are licensing agencies that provide blanket permissions for the church. Printed music and lyrics are protected by copyright law: song sheets for musicians printed lyrics in bulletins projected lyrics on screen (song slides) Unless you are only going to use music that your church writes itself, you need a CCLI license. <a href="https://us.ccli.com">Christian Copyright Licensing International</a> (CCLI) provides copyright licensing. Jury Duty They require reporting of the songs that are being reproduced, but only in a 'jury-duty' fashion. Several churches are selected each year to participate in a 6-month reporting period where usage reporting is completed online. Other churches are encouraged to keep some kind of record, but will not need to report. Song Sheets for Your Band CCLI also offers another very useful service for an extra fee called <a href="https://songselect.ccli.com"> SongSelect</a>. This service provides chord charts and lead sheets online for thousands of worship songs. You can can quickly transpose to any key and then print right from your browser. And you can sync the lyrics right into your projection software. This will save your worship leader tons of administrative time. | Purchase a <a href="https://us.ccli.com">CCLI</a> license. Recommended: Subscribe to the <a href="https://songselect.ccli.com">SongSelect</a> service while obtaining the CCLI license. This action is complete when you have purchased the CCLI license. | <a href="https://www.churchlawandtax.com/web/2014/october/understanding-worship-music-copyright-law.html?paging=off">Understanding Worship Music Copyright Law</a> on churchlawandtax.com | 128 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard Pat is more familiar with the latest& processes here - please review/update.& ----ds 2017-05-26 content updated --pb 2020-12-16 changed Due in # Days from 210& to 213& --pb 2020-01-21 content & links updated --pb 2021-01-26 moved streaming license info to new task specific to streaming --pb
421 | 373 | 829 | Get a copyright license for performed music | Purchase a copyright license that covers music performed outside of worship gatherings to keep your church in copyright compliance. | Rather than the church having to get written permission to perform every piece of music, there are licensing agencies that provide blanket permissions for the church. United States Copyright Law provides that any music (live or recorded) performed during the course of a regular worship gathering (typically Sunday morning, Wednesday night, etc.) is exempt from public performance licensing. However, churches are required to clear the copyrights for any music used outside of worship gatherings. That includes, but is not limited to: canned music played before or after the service youth functions banquets/award ceremonies concert events Bundled or a la Carte Consider what copyright licenses you'll purchase based on your performance needs. Every piece you will use will be covered by one of the following: <a href="https://christiancopyrightsolutions.com/performmusic/">PERFORMmusic</a> Facilities License (includes all 3 below) BMI (<a href="https://www.bmi.com/">Broadcast Music, Inc</a>) ASCAP (<a href="https://www.ascap.com/">American Society of Composers, Authors and Publishers</a>) SESAC <a href="https://www.sesac.com/">Society of European Stage Authors & Composers</a> are organizations that can assist with copyright licensing | Determine which license(s) you need. Obtain the licenses individually or in a bundle. This action is complete when you have purchased the appropriate license(s). |  | 213 | 7 | 2015-02-03 05:00 | 2021-01-26 05:00 | 2000-01-01 05:00 | template: standard Pat is more familiar with the latest& processes here - please review/update.& ----ds 2017-05-26 content updated --pb 2020-12-16 changed Due in # Days from 210& to 213& --pb 2020-01-21 content & links updated --pb
422 | 374 | 829 | Get a copyright license for projecting movies | Purchase a copyright license that covers projecting movies and movie clips during services and outreach events. | The Federal copyright act provides that videos released For Home Use Only (as most videos for sale or rent are) can only be shown in private homes to family and close friends. So you can't just rent something from Redbox and shoot it up on a screen at a church event or worship gathering. The following licenses are available: <a href="https://us.cvli.com">CVLI</a> (annual blanket copyright coverage for titles from 1,000+ producers) <a href="https://www.swank.com/religious-organizations/">Swank</a> (for a single full-length movie showing) | Determine which licenses are required. Obtain the licenses. This action is complete when you have selected and purchased the appropriate license(s). |  | 213 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2020-12-16 changed Due in # Days from 245& to 71& & Duration from 196& to 21& --pb&
423 | 840 | 829 | Conduct the first preview service | Conduct scheduled preview services (worship gatherings) to create excitement with the launch team and community, and to practice everything prior to a full public launch. | A prior PlanterPlan task walked you through scheduling preview services. Now it is time to pull them together. During the preview service, describe what they're about from the platform so that you'll get more grace and patience when something inevitably goes wrong. That's why you're doing this now instead of figuring out these weak spots on Launch Sunday For the first preview service, do your level best to have all the systems, equipment and teams in place that you would for the Opening Day of worship gatherings. If some piece is simply not coming together at the last minute, then confess it from the platform and set an expectation of when it will be added. Who Should Be Invited Friends, family, neighbors and co-workers could and should be coming to these previews. You may or may not want to advertise the preview services directly, but you should coach & encourage your team to invite people through word-of-mouth. An Important Opportunity Have a clear call to action or next step for everyone, especially guests, to take. Don't miss the opportunity to build some excitement and relational momentum. Debrief Practice your evaluation process to record learnings and jot down things that need to be changed or purchased before the next preview service. Debrief the Launch Team in a way that is exciting and congratulatory. | Train and empower all ministry teams to fully execute at the preview services. Encourage Launch Team members to invite friends, family, neighbors and co-workers. Conduct the first full preview service. Get feedback through your worship gathering evaluation process. Debrief your Launch Team and celebrate this major milestone! This action is complete when you have debriefed the launch team after the first preview service. |  | 211 | 30 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-28 content updated --pb& 2020-01-24 content updated --pb 2020-12-16 changed Due in # Days from 237& to 241& & Duration from 27 to 28& --pb&
424 | 842 | 1413 | Milestone: Make Final Preparations | Prevent important aspects of the Opening Day of worship gatherings from falling apart or getting overlooked. | This milestone will walk you through making a list and checking it twice. The last 5% of any project is the hardest to complete. With all of the things that need to happen for the Opening Day of worship gatherings, it would be easy to overlook something or not give it the attention it requires. Creating a checklist will help you think concretely about all of the different people, roles, tasks, equipment, etc... that need to be ready. Reviewing all of the strategic work and planning you did earlier in the planting process will remind you of what's important and will help you connect all of the busy work back to the vision & mission of the church. |  |  | 260 | 200 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-28 content udpated --pb 2019-08-19 title changed from "Review Assimilation Strategy" --pb 2020-12-16 changed Due in # Days from 217& to 220& --pb & 2020-01-24 content updated --pb
425 | 843 | 842 | Test your assimilation followup processes | Circle back to your Assimilation Strategy to make sure that all the pieces are in place and your team is ready to execute. | Now is the time to test drive your assimilation strategies to uncover any breakdowns, incomplete pieces or training gaps. Use the following questions to drill the followup team to help them be ready: Is the invitation to fill out the connection card script written? Does that invitation include clear instruction for how guests are to turn the card in? Is mention of the connection card planned at least 3 times during the worship gathering? Review the church's connection card. Does the followup software have a process built for each inquiry option on the card? (ex: I want info about...) Create a practice guest profile with a valid email address and your mobile number, and then send it through the followup process. Did each team member get notified of their followup task(s)? Did the practice guest receive each of the followup messages? Is there any placeholder or default text in any of the followup messages? Run a report on the followup process. Can you see that the practice profile has made it through the process? How will the followup system scale if you had 100 guests to follow up with the first Sunday? The followup system cannot fail in the first several months of the church. | Review your Assimilation Strategy document. Using the questions above as a springboard, work with your followup team to poke holes in the system and try to break it. Empower your followup team to fix anything that is incomplete or broken. This action is complete when you have thoroughly tested the assimilation processes and made the necessary updates to ensure they will work on the Opening Day of worship gatherings. |  | 220 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-06-20 resource links updated --pb 2017-12-29 content updated --pb 2020-12-16 changed Due in # Days from 237& to 241& --pb & 2020-01-24 content updated --pb
426 | 849 | 842 | Pre-address predictable post-launch challenges | Set goals and pre-address predictable challenges that will come in the first months of the regular worship gatherings. | The Opening Day of worship gatherings isn't the finish line; it's the starting line. What a shame it would be to arrive at Opening Day and have no plans or vision for the next Sunday! A vision for the future will help you proactively shape the future. Don't become so consumed in pre-launch activity that you miss looking beyond the Opening Day. Here are 4 predictable things that will happen if you have no post-launch goals: You Lose Focus - healthy, growing churches are always looking to the future and how to reach for the next level. If you've never thought past Launch Sunday, you'll soon find yourself wandering aimlessly, or worse: following a clear path to a lesser future. People Don't Stick - you'll will see an influx of guests. Whether they stick or not will be influenced by the consistency of your followup processes and by your road map for the first year after launch. If you're not reviewing the effectiveness of your followup and/or don't have clear onramps for people to get connected, you'll find yourself with a big back door. Money Gets Tight - you can run into financial problems in the months after launch if you're not watching projected cash flow and bank account balances. How are you doing against your budget? You need to know, both for budgeted expenses AND budgeted income. Momentum Stalls - if you make Launch Sunday your goal, people will be prone to take their foot off the gas pedal soon after the grand opening. That's exactly when you need everyone leaning in. Deal with these challenges by naming them and heading them off at the pass during the pre-launch phase. Once the excitement of the Opening Day of worship gatherings begins to dwindle, you should already be casting vision for next steps. Provide needed encouragement to the troops and lead the charge. | Talk with several other seasoned planters about their experience, challenges and recommendations regarding the months after they launched worship gatherings. What were their biggest challenges? What would they do differently? Make a list of predictable challenges that will occur during your first three months. Begin proactively preparing your Launch Team for these obstacles. Identify at least 3 specific and measurable things that you could do during the first three months to proactively address your predicted challenges. This action is complete when you have written out immediate post-launch expectations. |  | 227 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content updated --pb& 2020-01-24 content updated --pb 2020-12-16 changed Due in # Days from 223& to 227& --pb
427 | 850 | 842 | Create a Year-One scorecard | Set goals and measures for the year following the launch of worship gatherings. | The traditional scorecard for the American church is butts, bucks & buildings; an incomplete scorecard at best. You get the chance now to create a better scorecard that helps shape and reinforce the DNA of this new church. What gets measured gets done. Reverse engineer what health looks like at the first anniversary of the Opening Day of worship gatherings and create metrics and reports around those things. Look back to your Vision Frame and consider the 'vision proper'. That was an early exercise in dreaming about where the church should be headed. What are the steps you'd need to take to get closer to that preferred future? What could you measure between the Opening Day of worship gatherings and the first anniversary that would keep you on track? Consider setting goals in the following broad categories: Small groups Community Service Baptisms Attendance Diversity Assimilation Offerings Generosity (giving money and people away) Ministry Teams Leadership Church Planting Whatever your scorecard, consider the trade-off: measuring anything creates administrative burden. There are literally hundreds of things you could measure, but you'd have to hire extra staff just to measure stuff. Choose the things that are most important, balancing information against the cost of measurement. Work with your church management software champion to create reports or dashboards that will show you month to month how the church is doing. Enforcing this discipline will help you in a couple of ways: You'll have information to make better decisions The first reports will quickly show whether you have adequate systems in place to measure the right things; if they don't reflect what you know to be true, your team has some infrastructure to build out | Prayerfully consider what is to be measured over the first year of the church. Establish a baseline - where is the church on each these measures right now? Prayerfully set S.M.A.R.T. goals for where the Spirit is calling you to be at the first anniversary. Work with your ChMS champion to create monthly reports or a monthly dashboard that will measure your progress. This action is complete when you have established goals for each metric and reviewed them with your coach and Management Team (oversight). | <a href="https://exponential.org/scorecard-reveal/">What Does Your Church's Scorecard Reveal?</a> a bibliography of books, blog posts & podcasts by Exponential.org <a href="https://www.churchplantingtactics.com/3-reasons-create-ministry-reports/">3 Reasons to Create Ministry Reports</a> by ChurchPlantingTactics.com <a href="https://churchmetrics.com">ChurchMetrics.com</a> - a free scorecard tool from Life Church | 227 | 7 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content updated --pb 2019-11-20 title updated from "Get Everyone Praying" --pb 2020-12-16 changed Due in # Days from 230& to 234& --pb & 2020-01-24 content updated --pb
428 | 1300 | 842 | Plan a Launch Team celebration event | Plan something shortly after the Opening Day of worship gatherings to celebrate the people that worked so hard to call the gatherings into existence. | Your Launch Team has been working hard. Celebrate their efforts and sacrifice by planning some kind of thank-you event. Here are some creative ideas: Cater a lunch or dinner Reserve the party room at the local pizza place Cater a picnic Bring in 2 or 3 food trucks immediately following service BUT NO POTLUCKS! They already worked hard enough. Here's what one planter sent to his team via text: "You're Invited! If you consider yourself a part of the [Name of Church] Team, we would love to bless you with a free fun morning at the pumpkin patch. Bring your family to [Name of Patch] on Saturday at 10 am. We'll meet you at the gate and pay for your entry. Thank you for being part of the team!" You're Fired! A celebration event like this is a great time to disband the Launch Team. Their job was to launch the weekly worship gatherings, and now that's done. The Launch Team should dissolve into the congregation at large and begin identifying with other ongoing serving teams. | Choose a Launch Team celebration event to be held shortly after launch. Recruit a detail-oriented relative or supporter (NOT someone on the Launch Team) to organize everything. Invite your Launch Team and their families to come and enjoy. Consider formally disbanding the Launch Team at the event. This action is complete when you have invited your Launch Team to the planned celebration event. |  | 234 | 14 | 2019-11-01 04:00 | 2020-01-29 05:00 | 2000-01-01 05:00 | template:
429 | 851 | 842 | Plan a prayer event around the grand opening | Engage the Prayer Team and Launch Team in praying during the lead up to the Opening Day of worship gatherings. | Spiritual warfare is real. But the prayers of the righteous are powerful and effective. Covenant with yourself to do something to elevate the temperature of prayer in the weeks leading up to the Opening Day of worship gatherings. Here are a couple of ideas: Prayer Walk - get together and pray through the community and/or around the facility Prayer Vigil - orchestrate constant prayer over 24 hours (or some other period of time); <a href="https://www.signupgenius.com">SignUpGenius.com</a> can be a helpful tool Prayer Campaign - orchestrate prayer over a week or month on given days or at specific times each day Choose the one (or combination) that best suits your people, prayer teams and particular situation. | Decide how to get everyone praying and when you want it to happen - include length, start time, end time and communication channel(s). Cast vision for the event amongst your Prayer Team and Launch Team. Make it easy to sign up. Conduct the prayer event. This action is complete when people have begun signing up for the prayer event. |  | 234 | 14 | 2015-02-03 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content validated --pb& 2020-01-24 content updated --pb 2020-12-16 changed Due in # Days from 252& to 260& --pb
430 | 1421 | 842 | Get well-wishers to come on 2nd or 3rd Sunday | Guard your team's morale by inviting well-wishers to come that week instead of on launch Sunday. | There was once a new church that saw 193 people show up on Opening Day. This was significantly more people than they were expecting, so they figured the following Sunday they'd see a dip in attendance, but when only 33 people showed up the following Sunday, they were devastated. They knew not everyone from Opening Day Sunday would return the following week, but seeing only 17% return made them wonder what they did wrong. They felt rejected. The chief reason this church plant saw such a drastic dip in attendance after Opening Day was not because the preaching was boring or the worship was horrendous. It was because so many well-wishers came on that first Sunday. These well-wishers were friends and family who came to show their support of the new church. However, come week two, they were back worshipping at their own churches. While there's nothing wrong with well-wishers attending worship gatherings to show their support, unless they're coming to serve, invite them to visit on the 2nd and 3rd Sunday instead of Opening Day. That way when attendance dips those subsequent weeks, the well-wishers will be there to help with critical mass. | Develop a list of potential well-wishers (parents, financial supporters, friends from other churches). Contact these potential well-wishers, inviting them to pray for your opening day and to attend on the 2nd or 3rd Sunday instead of launch Sunday. This action is complete once you've invited well-wishers to visit on a Sunday that's not opening day. |  | 234 | 7 | 2021-01-15 05:00 | 2022-05-16 04:00 | 2000-01-01 05:00 | template: 2022-05-16 tweaked content --pb
431 | 848 | 842 | Review the Launch Sunday Checklist with your teams | Use your customized Launch Sunday Checklist to lovingly drill your teams to make sure everything is in place and ready. | There are so many moving parts, processes and systems that need to be in place for Launch Sunday that it would be easy for something to slip through the cracks. Help your teams cover all their bases by reviewing all of those processes and systems with them. Use Passion for Planting's Launch Sunday Checklist as a helping tool for your teams. Review it all together at a Launch Team meeting or review it individually with each ministry team. Optionally, you could send a copy to each of the team leaders, have them review their section with their team and then report back to you. The end result will be a list of things that need to be addressed - the completed checklist becomes a handy to-do list for your ministry teams. Make sure anything missing or broken gets fixed. | Download and review Passion for Planting's <a href="/resources/item/147">Launch Sunday Checklist</a> with your team(s). Cross off all the items that have been completed. Make a list of items that need to be addressed and assign each to a specific person. Empower your teams to make the necessary changes. This action is complete when you have reviewed all the items on the checklist and ensured plans are in place for everything that needs to happen between now and the Opening Day of worship gatherings. |  | 241 | 7 | 2000-01-01 05:00 | 2020-12-16 05:00 | 2000-01-01 05:00 | template: standard 2017-12-29 content updated --pb 2020-12-16 changed Due in # Days from 223& to 227& --pb &
432 | 852 | 1413 | Milestone: Launch In-Person Worship Gatherings | The Opening Day of worship gatherings is an exciting day. Celebrate God! Bring Him the Glory and Honor for what He has done. |  |  |  | 260 | 7 | 2015-02-03 05:00 | 2021-01-15 05:00 | 2000-01-01 05:00 | template: standard 2017-12-27 content & links completely overhauled --pb 2018-07-13 updated& due in # of days from 14 to 30 and& duration from 188 to 30 --pb 2018-07-20 updated vendors --pb 2021-10-05 content updated --pb 2019-03-21 updated vendors --pb 2019-11-19 updated content --pb 2021-01-18 due in days changed from 30 to 74 and duration from 30 to 14 --pb 2022-11-21 updated links --sc

## Sheet1
CSV column | Supabase column | Migration notes
sequence_within_template | position | re calculated to have different number
id | id | auto-create a UUID when creating the row in supabase
task_parent_id | parent_task_id | copy
title | title | copy
purpose | purpose | copy
description | description | copy
actions | actions | copy
additional_resources | resources | need to break up into list form
days from start | days_from_start_until_due | copy
duration | default_duration | not duration_days; copy
created_at | created_at | auto generated when creating row in supabase
updated_at | last_modified | auto generated when creating row in supabase
published_at | published | set default to false -> need to publish again?
notes | admin_notes | notes are only visible to the org's admins